## GRANT SUMMARY
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
GRAND SUMMARY
Priced Bill Of Quantities
Transfer the Contract Summary of Contract Value to the Form of Tender
S/N | BILL NO | DESCRIPTION | BOQ AMOUNT | BOQ AMOUNT | REVISED VALUE AFTER V.O 1 | Addition | Omission | Savings Excluding V.O 1 | EXPECTED REVISED BOQ VALUE AFTER A/O |  | ADDITION AMOUNT/VARIATION | SAVING AMOUNT | % |  |  | CLAUSES | Appendix
1 | BILL NO 1 | PRELIMINARIES | 227580 | 227580 | 227580 | 224532 | 124800 | -99732 | 327312 | 99732 |  | -99732 | -43.8228 | 8.545% | 8.545% |  | Bill No 1. (PRELIMINARIES)
[6 empty] | 0 | 124800 | 124800 | 102780
2 | BILL NO 2 | DAY WORKS | 88252.5 | 88252.5 | 88252.5 |  | 88252.5 | 88252.5 | 0 | 88252.5 |  | 88262.5 | 100 | 0% | 0% |  | Bill No 2. (DAY WORK)
3 | BILL NO 3 | PROVISIONAL SUM | 200000 | 200000 |  |  | 200000 | 200000 |  | -200000 |  | 200000 | 100 | 0% |  |  | Bill No 3. (PROVISIONAL SUM)
4 | BILL NO 4 | NEW HOUSING UNIT (20 UNITS) | 1965370.94 | [11 empty] | 42.16%
|  | SUBSTRUCTURE WORKS |  | 947257 | 947257 | 41896.539 | 291914.7084 | 250018.1695 | 697238.8305 | -447220.661 |  | 291914.7084 | 26.3939 | 18.2% |  | 12.1 | 20 NEW ADD QTY | 311793.254
[6 empty] | 0 | 311793.254 | 311793.254 | 635463.746
|  | SUPERSTRUCTURE WORKS |  | 1018113.94 | 1018113.94 | 23100 | 123401.5 | 100301.5 | 917812.44 | 817510.94 | 23100 | 123401.5 | 9.8517 | 23.96% |  | 12.2 | GRAND SUM. ADD. (Bill No. 4 & 7)
[6 empty] | 0 | 85157 | 85157 | 932956.94
5 | BILL NO 4 | EXTERNAL WORKS AND EXTERNAL SERVICES | 28455 | 28455 | 28455 | 0 | 2100 | 2100 | 26355 | 26355 |  | 2100 | 7.3801 | 0.6881% | 0.6881% |  | BIll No 4 (20 NHI EXXTERNAL WORK)
[7 empty] | 0 | 0 | 28455
6 | BILL NO 5 | MAINTENANCE WORKS FOR THE EXISTING HOUSING UNITS (29 NO) | 1436308.607 | 1436308.607 | 1436308.607 | 11890 | 9991.805 | -1898.195 | 1438206.802 | 1440104.997 | 11890 | 9991.805 | -0.13216 | 37.55% | 37.55% | 12.2 | ADD. WORK (29 - MHU)
[6 empty] | 43723 | 9991.8 | -33731.8 | 1470040.45
7 | BILL NO 6 | PROTECTION AND STORM WATER DRAINAGE | 265674.675 | 265674.675 | 265674.675 | 11318 | 70280.7 | 58962.7 | 206711.975 | -147749.275 |  | 58962.7 | 22.1936 | 5.397% | 5.397% |  | ADD. WORK ON CHANNEL
[6 empty] | 0 | 103282.2 | 103282.2 | 162392.475
8 | BILL NO 7 | 3 NUMBER HOUSING UNITS | 239991.025 | [11 empty] | 5.658%
|  | SUBSTRUCTURE WORKS |  | 36105 | 36105 | 11250 | 10515.156 | -734.844 | 36839.844 | 37574.688 |  | 10515.156 | -2.0353 | 0.9618% |  | 12.1 | 20 NHU ADD. QTY/ Bill No 7. (3 NHU)
[6 empty] | 0 | 10515.096 | 10515.096 | 25589.904
|  | SUPERSTRUCTURE WORK |  | 203886.025 | 203886.025 | 1111.44 | 25110 | 23998.56 | 179887.465 | 155888.905 | 1111.44 | 25110 | 11.7706 | 4.696% |  | 12.2 | SUM. OF ADD. WORKS (Bill No 4 & 7)
[7 empty] | 12000 | 12000 | 204997.44
[14 empty] | #REF! | #REF!
746627.8095
Total Contract Value |  |  | 4451632.747 | 4451632.747 | 4251632.747 | 325097.979 | 746366.3694 | 621268.3905 | 3830364.3565 | 621268.3905 | 36101.44 | 710526.3695
[6 empty] | 421268.3905 |  |  | 621268.3905 |  |  | 710526.3695
1367634.7599
|  |  |  | CONTRACT PRICE |  |  |  |  | CLAIMABLE |  |  | ADD/OMISSION IMPACT |  | 336267.29 |  | 19525
[14 empty] | 115915.29 |  | 624800 | 4455164.3565
|  | PERCENTAGE |  | AMOUNT |  |  |  |  | PERCENTAGE | 1242536.781 |  | 746627.8095
| Addition/Omission and Change Order Impact | CONTRACT TOTAL VALUE |  | 4451632.747 |  |  |  |  | 100% | 0 | [6 empty] | -3531.6095
|  | CLAIMABLE TOTAL AMOUNT |  | 3830364.3565 |  |  |  |  | 86.04%
|  | ADDITION OMMISSION IMPACT |  | 710526.3695 |  |  |  |  | 15.96%
|  | ADDITIONAL WORK BILL NO. 5 |  | 1111.44 |  |  |  |  | 4.975% |  |  | 221463.44
|  | CHANGE ORDER -2 |  | 220352
|  | NET FINANCIAL IMPACT |  | 4051827.7965 |  |  |  |  | 91.02%
| Progress Impact | OVERALL FINANCIAL IMPACT | [6 empty] | 8.981%
|  | CLAIMED TO DATE AGAINST CONTRACT |  | 2193954.35 |  |  |  |  | 49.28% |  |  | 53.28%
|  | CLAIMED AGAINST CLAIMABLE VALUE |  | 2193954.35 |  |  |  |  | 57.28%
|  | CLAIMABLE AMOUNT - BILL 11 (13-04-26) |  | 110000 |  |  |  |  | 2.471%
[9 empty] | 10.46% |  |  | 16.22%
|  | Progres Against Contract Vs Revised Value | [6 empty] | Planned VS Actual Cost |  |  | Planned Vs Actual Progress
[6 empty] | 43723 | 745791.85 | 902068.25 | 3562675.955

## Copy of Copy of GRANT SUMMARY (hidden)
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
GRAND SUMMARY
Priced Bill Of Quantities
Transfer the Contract Summary of Contract Value to the Form of Tender
S/N | BILL NO | DESCRIPTION | BOQ AMOUNT | BOQ AMOUNT | REVISED VALUE AFTER V.O 1 | Addition | Omission | Savings Excluding V.O 1 | EXPECTED REVISED BOQ VALUE AFTER A/O |  | ADDITION AMOUNT/VARIATION | SAVING AMOUNT | % |  |  | CLAUSES | Appendix
1 | BILL NO 1 | PRELIMINARIES | 227580 | 227580 | 227580 | 0 | 124800 | 124800 | 102780 | -124800 |  | 124800 | 54.8379 | 2.859% | 2.859% |  | Bill No 1. (PRELIMINARIES)
2 | BILL NO 2 | DAY WORKS | 88252.5 | 88252.5 | 88252.5 | 0 | 88252.5 | 88252.5 | 0 | 88252.5 |  | 88262.5 | 100 | 0% | 0% |  | Bill No 2. (DAY WORK)
3 | BILL NO 3 | PROVISIONAL SUM | 200000 | 200000 | 0 | 0 | 200000 | 200000 | 0 | -200000 |  | 200000 | 100 | 0% |  |  | Bill No 3. (PROVISIONAL SUM)
4 | BILL NO 4 | NEW HOUSING UNIT (20 UNITS) | 1965370.94 | [11 empty] | 44.93%
|  | SUBSTRUCTURE WORKS |  | 947257 | 947257 | 41896.539 | 291914.7084 | 250018.1695 | 697238.8305 | -447220.661 |  | 291914.7084 | 26.3939 | 19.4% |  | 12.1 | 20 NEW ADD QTY
|  | SUPERSTRUCTURE WORKS |  | 1018113.94 | 1018113.94 | 23100 | 123401.5 | 100301.5 | 917812.44 | 817510.94 | 23100 | 123401.5 | 9.8517 | 25.53% |  | 12.2 | GRAND SUM. ADD. (Bill No. 4 & 7)
5 | BILL NO 4 | EXTERNAL WORKS AND EXTERNAL SERVICES | 28455 | 28455 | 28455 | 0 | 2100 | 2100 | 26355 | 26355 |  | 2100 | 7.3801 | 0.7332% | 0.7332% |  | BIll No 4 (20 NHI EXXTERNAL WORK)
6 | BILL NO 5 | MAINTENANCE WORKS FOR THE EXISTING HOUSING UNITS (29 NO) | 1436308.607 | 1436308.607 | 1436308.607 | 11890 | 9991.805 | -1898.195 | 1438206.802 | 1440104.997 | 11890 | 9991.805 | -0.13216 | 40.01% | 40.01% | 12.2 | ADD. WORK (29 - MHU)
7 | BILL NO 6 | PROTECTION AND STORM WATER DRAINAGE | 265674.675 | 265674.675 | 265674.675 | 0 | 70280.7 | 70280.7 | 195393.975 | -125113.275 |  | 70280.7 | 26.4537 | 5.436% | 5.436% |  | ADD. WORK ON CHANNEL
8 | BILL NO 7 | 3 NUMBER HOUSING UNITS | 239991.025 | [11 empty] | 6.029%
|  | SUBSTRUCTURE WORKS |  | 36105 | 36105 | 11250 | 10515.156 | -734.844 | 36839.844 | 37574.688 |  | 10515.156 | -2.0353 | 1.025% |  | 12.1 | 20 NHU ADD. QTY/ Bill No 7. (3 NHU)
|  | SUPERSTRUCTURE WORK |  | 203886.025 | 203886.025 | 1111.44 | 25110 | 23998.56 | 179887.465 | 155888.905 | 1111.44 | 25110 | 11.7706 | 5.004% |  | 12.2 | SUM. OF ADD. WORKS (Bill No 4 & 7)
[14 empty] | #REF! | #REF!
982477.8095
Total Contract Value |  |  | 4451632.747 | 4451632.747 | 4251632.747 | 89247.979 | 946366.3694 | 857118.3905 | 3594514.3565 | 857118.3905 | 36101.44 | 946376.3695
[6 empty] | 857118.3905 |  |  | 857118.3905 |  |  | 946376.3695
1803484.7599
|  |  |  | CONTRACT PRICE |  |  |  |  | CLAIMABLE |  |  | ADD/OMISSION IMPACT |  | 336267.29 |  | 19525
[14 empty] | 115915.29 |  | 624800 | 4219314.3565
|  | PERCENTAGE |  | AMOUNT |  |  |  |  | PERCENTAGE | 1714236.781 |  | 982477.8095
| Addition/Omission and Change Order Impact | CONTRACT TOTAL VALUE |  | 4451632.747 |  |  |  |  | 100% | 0 | [6 empty] | 232318.3905
|  | CLAIMABLE TOTAL AMOUNT |  | 3594514.3565 |  |  |  |  | 80.75%
|  | ADDITION OMMISSION IMPACT |  | 946376.3695 |  |  |  |  | 21.26%
|  | ADDITIONAL WORK BILL NO. 5 |  | 1111.44 |  |  |  |  | 4.975% |  |  | 221463.44
|  | CHANGE ORDER -2 |  | 220352
|  | NET FINANCIAL IMPACT |  | 3815977.7965 |  |  |  |  | 85.72%
| Progress Impact | OVERALL FINANCIAL IMPACT | [6 empty] | 14.28%
|  | CLAIMED TO DATE AGAINST CONTRACT |  | 2193954.35 |  |  |  |  | 49.28% |  |  | 55.16%
|  | CLAIMED AGAINST CLAIMABLE VALUE |  | 2193954.35 |  |  |  |  | 61.04%
|  | CLAIMABLE AMOUNT - BILL 11 (13-04-26) |  | 110000 |  |  |  |  | 2.471%
[9 empty] | 14.22% |  |  | 14.34%
|  | Progres Against Contract Vs Revised Value | [6 empty] | Planned VS Actual Cost |  |  | Planned Vs Actual Progress

## 1ST SCENARIOS. BILL 6 ACTUAL (hidden)
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
GRAND SUMMARY
Priced Bill Of Quantities
Transfer the Contract Summary of Contract Value to the Form of Tender
S/N | BILL NO | DESCRIPTION | BOQ AMOUNT | BOQ AMOUNT | REVISED VALUE AFTER V.O 1 | Addition | Omission | Savings Excluding V.O 1 | EXPECTED REVISED BOQ VALUE AFTER A/O | AMOUNT CLAIMED AS PER BILL NO. 12 |  | ADDITION AMOUNT/VARIATION | SAVING AMOUNT | % |  |  | CLAUSES | Appendix
1 | BILL NO 1 | PRELIMINARIES | 227580 | 227580 | 227580 | 0 | 124800 | 124800 | 102780 | 75255.52 | -124800 |  | 124800 | 54.8379 | 3.049% | 3.049% |  | Bill No 1. (PRELIMINARIES)
2 | BILL NO 2 | DAY WORKS | 88252.5 | 88252.5 | 88252.5 | 0 | 88252.5 | 88252.5 | 0 | 0 | 88252.5 |  | 88262.5 | 100 | 0% | 0% |  | Bill No 2. (DAY WORK)
3 | BILL NO 3 | PROVISIONAL SUM | 200000 | 200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | -200000 |  | 200000 | 100 | 0% |  |  | Bill No 3. (PROVISIONAL SUM)
4 | BILL NO 4 | NEW HOUSING UNIT (20 UNITS) | 1965370.94 | [12 empty] | 45.4%
|  | SUBSTRUCTURE WORKS |  | 947257 | 947257 | 0 | 311793.254 | 311793.254 | 635463.746 | 635463.746 | -323670.492 |  | 291914.7084 | 32.9154 | 18.85% |  | 12.1 | 20 NEW ADD QTY
|  | SUPERSTRUCTURE WORKS |  | 1018113.94 | 1018113.94 | 0 | 123401.5 | 123401.5 | 894712.44 | 384919.876 | 771310.94 | 23100 | 123401.5 | 12.1206 | 26.54% |  | 12.2 | GRAND SUM. ADD. (Bill No. 4 & 7)
5 | BILL NO 4 | EXTERNAL WORKS AND EXTERNAL SERVICES | 28455 | 28455 | 28455 |  | 2100 | 2100 | 26355 | 0 | 26355 |  | 2100 | 7.3801 | 0.7819% | 0.7819% |  | BIll No 4 (20 NHI EXXTERNAL WORK)
6 | BILL NO 5 | MAINTENANCE WORKS FOR THE EXISTING HOUSING UNITS (29 NO) | 1436308.607 | 1436308.607 | 1436308.607 | 11890 | 9991.805 | -1898.195 | 1438206.802 | 1386819.283 | 1440104.997 | 11890 | 9991.805 | -0.13216 | 42.67% | 42.67% | 12.2 | ADD. WORK (29 - MHU)
7 | BILL NO 6 | PROTECTION AND STORM WATER DRAINAGE | 265674.675 | 265674.675 | 265674.675 | 0 | 186375.1174 | 186375.1174 | 79299.5575 | 6120.135 | 107075.5599 |  | 186375.1174 | 70.1516 | 2.353% | 2.353% |  | ADD. WORK ON CHANNEL
8 | BILL NO 7 | 3 NUMBER HOUSING UNITS | 239991.025 | [12 empty] | 5.751%
|  | SUBSTRUCTURE WORKS |  | 36105 | 36105 | 0 | 10515.096 | 10515.096 | 25589.904 | 25589.904 | 15074.808 |  | 10515.156 | 29.1237 | 0.7592% |  | 12.1 | 20 NHU ADD. QTY/ Bill No 7. (3 NHU)
|  | SUPERSTRUCTURE WORK |  | 203886.025 | 203886.025 | 0 | 35625.156 | 35625.156 | 168260.869 | 28323 | 132635.713 | 1111.44 | 25110 | 17.4731 | 4.992% |  | 12.2 | SUM. OF ADD. WORKS (Bill No 4 & 7)
Total Contract Value |  |  | 4451632.747 | 4451632.747 | 4251632.747 | 11890 | 1092854.4285 | 1080964.4285 | 3370668.3185 | 2542491.464 | 1080964.4285 | 36101.44 | 1062470.7869
[6 empty] | 1080964.4285 |  |  | 1080964.4285 |  |  |  | 1062470.7869
2173818.8569
|  |  |  | CONTRACT PRICE |  |  |  |  | CLAIMABLE |  |  |  | ADD/OMISSION IMPACT |  | 336267.29 |  | 19525
[15 empty] | 115915.29 |  | 624800 | 3995468.3185
|  | PERCENTAGE |  | AMOUNT |  |  |  |  | PERCENTAGE |  | 2161928.8569 |  | #REF!
| Addition/Omission and Change Order Impact | CONTRACT TOTAL VALUE |  | 4451632.747 |  |  |  |  | 100% |  | 0 | [6 empty] | 456164.4285
|  | CLAIMABLE TOTAL AMOUNT |  | 3370668.3185 |  |  |  |  | 75.72%
|  | ADDITION OMMISSION IMPACT |  | 1062470.7869 |  |  |  |  | 23.87%
|  | ADDITIONAL WORK BILL NO. 5 |  | 1111.44 |  |  |  |  | 4.975% |  |  |  | 221463.44
|  | CHANGE ORDER -2 |  | 220352
|  | NET FINANCIAL IMPACT |  | 3592131.7585 |  |  |  |  | 80.69%
| Progress Impact | OVERALL FINANCIAL IMPACT | [6 empty] | 19.31%
|  | CLAIMED TO DATE AGAINST CONTRACT |  | 2193954.35 |  |  |  |  | 49.28% |  |  |  | 57.19%
|  | CLAIMED AGAINST CLAIMABLE VALUE |  | 2193954.35 |  |  |  |  | 65.09%
|  | CLAIMABLE AMOUNT - BILL 11 (13-04-26) |  | 110000 |  |  |  |  | 2.471%
[9 empty] | 18.28% |  |  |  | 12.31%
|  | Progres Against Contract Vs Revised Value | [6 empty] | Planned VS Actual Cost |  |  |  | Planned Vs Actual Progress
4451632.747
33780.1384
[8 empty] | 614.1843 | 0

## 2ND GRAND SUMMARY (All Addition (hidden)
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
GRAND SUMMARY
Priced Bill Of Quantities
Transfer the Contract Summary of Contract Value to the Form of Tender
S/N | BILL NO | DESCRIPTION | BOQ AMOUNT | BOQ AMOUNT | REVISED VALUE AFTER V.O 1 | Addition | Omission | Savings Excluding V.O 1 | EXPECTED REVISED BOQ VALUE AFTER A/O | AMOUNT CLAIMED AS PER BILL NO. 12 |  | ADDITION AMOUNT/VARIATION | SAVING AMOUNT | % |  |  | CLAUSES | Appendix
1 | BILL NO 1 | PRELIMINARIES | 227580 | 227580 | 227580 | 0 | 124800 | 124800 | 102780 | 75255.52 | -124800 |  | 124800 | 54.8379 | 2.759% | 2.759% |  | Bill No 1. (PRELIMINARIES)
2 | BILL NO 2 | DAY WORKS | 88252.5 | 88252.5 | 88252.5 | 0 | 88252.5 | 88252.5 | 0 | 0 | 88252.5 |  | 88262.5 | 100 | 0% | 0% |  | Bill No 2. (DAY WORK)
3 | BILL NO 3 | PROVISIONAL SUM | 200000 | 200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | -200000 |  | 200000 | 100 | 0% |  |  | Bill No 3. (PROVISIONAL SUM)
4 | BILL NO 4 | NEW HOUSING UNIT (20 UNITS) | 1965370.94 | [12 empty] | 45.27%
|  | SUBSTRUCTURE WORKS |  | 947257 | 947257 | 41896.539 | 311793.254 | 269896.715 | 677360.285 | 635463.746 | -407463.5699 |  | 291914.7084 | 28.4924 | 18.18% |  | 12.1 | 20 NEW ADD QTY
|  | SUPERSTRUCTURE WORKS |  | 1018113.94 | 1018113.94 | 114450.2438 | 123401.5 | 8951.2562 | 1009162.6838 | 384919.876 | 1000211.4277 | 23100 | 123401.5 | 0.8792 | 27.09% |  | 12.2 | GRAND SUM. ADD. (Bill No. 4 & 7) | -8951.2562
5 | BILL NO 4 | EXTERNAL WORKS AND EXTERNAL SERVICES | 28455 | 28455 | 28455 |  | 2100 | 2100 | 26355 | 0 | 26355 |  | 2100 | 7.3801 | 0.7074% | 0.7074% |  | BIll No 4 (20 NHI EXXTERNAL WORK)
6 | BILL NO 5 | MAINTENANCE WORKS FOR THE EXISTING HOUSING UNITS (29 NO) | 1436308.607 | 1436308.607 | 1436308.607 | 11890 | 9991.805 | -1898.195 | 1438206.802 | 1386819.283 | 1440104.997 | 11890 | 9991.805 | -0.13216 | 38.6% | 38.6% | 12.2 | ADD. WORK (29 - MHU)
7 | BILL NO 6 | PROTECTION AND STORM WATER DRAINAGE | 265674.675 | 265674.675 | 265674.675 | 0 | 0 | 0 | 265674.675 | 6120.135 | -265674.675 |  | 0 | 0 | 7.131% | 7.131% |  | ADD. WORK ON CHANNEL
8 | BILL NO 7 | 3 NUMBER HOUSING UNITS | 239991.025 | [12 empty] | 5.535%
|  | SUBSTRUCTURE WORKS |  | 36105 | 36105 | 11250 | 10515.096 | -734.904 | 36839.904 | 25589.904 | 37574.808 |  | 10515.156 | -2.0355 | 0.9888% |  | 12.1 | 20 NHU ADD. QTY/ Bill No 7. (3 NHU)
|  | SUPERSTRUCTURE WORK |  | 203886.025 | 203886.025 | 1111.44 | 35625.156 | 34513.716 | 169372.309 | 28323 | 134858.593 | 1111.44 | 25110 | 16.9279 | 4.546% |  | 12.2 | SUM. OF ADD. WORKS (Bill No 4 & 7)
Total Contract Value |  |  | 4451632.747 | 4451632.747 | 4251632.747 | 180598.2228 | 906479.311 | 725881.0882 | 3725751.6588 | 2542491.464 | 725881.0882 | 36101.44 | 876095.6695
[6 empty] | 725881.0882 |  |  | 725881.0882 |  |  |  | 876095.6695
1632360.3992
|  |  |  | CONTRACT PRICE |  |  |  |  | CLAIMABLE |  |  |  | ADD/OMISSION IMPACT |  | 336267.29 |  | 19525
[15 empty] | 115915.29 |  | 624800 | 4350551.6588
|  | PERCENTAGE |  | AMOUNT |  |  |  |  | PERCENTAGE |  | 1451762.1764 |  | #REF!
| Addition/Omission and Change Order Impact | CONTRACT TOTAL VALUE |  | 4451632.747 |  |  |  |  | 100% |  | 0 | [6 empty] | 101081.0882
|  | CLAIMABLE TOTAL AMOUNT |  | 3725751.6588 |  |  |  |  | 83.69%
|  | ADDITION OMMISSION IMPACT |  | 876095.6695 |  |  |  |  | 19.68%
|  | ADDITIONAL WORK BILL NO. 5 |  | 1111.44 |  |  |  |  | 4.975% |  |  |  | 221463.44
|  | CHANGE ORDER -2 |  | 220352
|  | NET FINANCIAL IMPACT |  | 3947215.0988 |  |  |  |  | 88.67%
| Progress Impact | OVERALL FINANCIAL IMPACT | [6 empty] | 11.33%
|  | CLAIMED TO DATE AGAINST CONTRACT |  | 2193954.35 |  |  |  |  | 49.28% |  |  |  | 54.09%
|  | CLAIMED AGAINST CLAIMABLE VALUE |  | 2193954.35 |  |  |  |  | 58.89%
|  | CLAIMABLE AMOUNT - BILL 11 (13-04-26) |  | 110000 |  |  |  |  | 2.471%
[9 empty] | 12.07% |  |  |  | 15.41%
|  | Progres Against Contract Vs Revised Value | [6 empty] | Planned VS Actual Cost |  |  |  | Planned Vs Actual Progress
4451632.747
22683.784
[8 empty] | 412.4324 | 0

## 3RD GRAND SUMMARY (Consultant S (hidden)
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
GRAND SUMMARY
Priced Bill Of Quantities
Transfer the Contract Summary of Contract Value to the Form of Tender
S/N | BILL NO | DESCRIPTION | BOQ AMOUNT | BOQ AMOUNT | REVISED VALUE AFTER V.O 1 | Addition | Omission | Savings Excluding V.O 1 | EXPECTED REVISED BOQ VALUE AFTER A/O | AMOUNT CLAIMED AS PER BILL NO. 12 |  | ADDITION AMOUNT/VARIATION | SAVING AMOUNT | % |  |  | CLAUSES | Appendix
1 | BILL NO 1 | PRELIMINARIES | 227580 | 227580 | 227580 | 0 | 124800 | 124800 | 102780 | 75255.52 | -124800 |  | 124800 | 54.8379 | 2.889% | 2.889% |  | Bill No 1. (PRELIMINARIES)
2 | BILL NO 2 | DAY WORKS | 88252.5 | 88252.5 | 88252.5 | 0 | 88252.5 | 88252.5 | 0 | 0 | 88252.5 |  | 88262.5 | 100 | 0% | 0% |  | Bill No 2. (DAY WORK)
3 | BILL NO 3 | PROVISIONAL SUM | 200000 | 200000 | 0 | 0 | 200000 | 200000 | 0 | 0 | -200000 |  | 200000 | 100 | 0% |  |  | Bill No 3. (PROVISIONAL SUM)
4 | BILL NO 4 | NEW HOUSING UNIT (20 UNITS) | 1965370.94 | [12 empty] | 43.02%
|  | SUBSTRUCTURE WORKS |  | 947257 | 947257 | 0 | 311793.254 | 311793.254 | 635463.746 | 635463.746 | -323670.492 |  | 291914.7084 | 32.9154 | 17.86% |  | 12.1 | 20 NEW ADD QTY
|  | SUPERSTRUCTURE WORKS |  | 1018113.94 | 1018113.94 | 0 | 123401.5 | 123401.5 | 894712.44 | 384919.876 | 771310.94 | 23100 | 123401.5 | 12.1206 | 25.15% |  | 12.2 | GRAND SUM. ADD. (Bill No. 4 & 7)
5 | BILL NO 4 | EXTERNAL WORKS AND EXTERNAL SERVICES | 28455 | 28455 | 28455 |  | 2100 | 2100 | 26355 | 0 | 26355 |  | 2100 | 7.3801 | 0.7409% | 0.7409% |  | BIll No 4 (20 NHI EXXTERNAL WORK)
6 | BILL NO 5 | MAINTENANCE WORKS FOR THE EXISTING HOUSING UNITS (29 NO) | 1436308.607 | 1436308.607 | 1436308.607 | 11890 | 9991.805 | -1898.195 | 1438206.802 | 1386819.283 | 1440104.997 | 11890 | 9991.805 | -0.13216 | 40.43% | 40.43% | 12.2 | ADD. WORK (29 - MHU)
7 | BILL NO 6 | PROTECTION AND STORM WATER DRAINAGE | 265674.675 | 265674.675 | 265674.675 | 0 | 0 | 0 | 265674.675 | 6120.135 | -265674.675 |  | 0 | 0 | 7.469% | 7.469% |  | ADD. WORK ON CHANNEL
8 | BILL NO 7 | 3 NUMBER HOUSING UNITS | 239991.025 | [12 empty] | 5.45%
|  | SUBSTRUCTURE WORKS |  | 36105 | 36105 | 0 | 10515.096 | 10515.096 | 25589.904 | 25589.904 | 15074.808 |  | 10515.156 | 29.1237 | 0.7194% |  | 12.1 | 20 NHU ADD. QTY/ Bill No 7. (3 NHU)
|  | SUPERSTRUCTURE WORK |  | 203886.025 | 203886.025 | 0 | 35625.156 | 35625.156 | 168260.869 | 28323 | 132635.713 | 1111.44 | 25110 | 17.4731 | 4.73% |  | 12.2 | SUM. OF ADD. WORKS (Bill No 4 & 7)
Total Contract Value |  |  | 4451632.747 | 4451632.747 | 4251632.747 | 11890 | 906479.311 | 894589.311 | 3557043.436 | 2542491.464 | 894589.311 | 36101.44 | 876095.6695
[6 empty] | 894589.311 |  |  | 894589.311 |  |  |  | 876095.6695
1801068.622
|  |  |  | CONTRACT PRICE |  |  |  |  | CLAIMABLE |  |  |  | ADD/OMISSION IMPACT |  | 336267.29 |  | 19525
[15 empty] | 115915.29 |  | 624800 | 4181843.436
|  | PERCENTAGE |  | AMOUNT |  |  |  |  | PERCENTAGE |  | 1789178.622 |  | #REF!
| Addition/Omission and Change Order Impact | CONTRACT TOTAL VALUE |  | 4451632.747 |  |  |  |  | 100% |  | 0 | [6 empty] | 269789.311
|  | CLAIMABLE TOTAL AMOUNT |  | 3557043.436 |  |  |  |  | 79.9%
|  | ADDITION OMMISSION IMPACT |  | 876095.6695 |  |  |  |  | 19.68%
|  | ADDITIONAL WORK BILL NO. 5 |  | 1111.44 |  |  |  |  | 4.975% |  |  |  | 221463.44
|  | CHANGE ORDER -2 |  | 220352
|  | NET FINANCIAL IMPACT |  | 3778506.876 |  |  |  |  | 84.88%
| Progress Impact | OVERALL FINANCIAL IMPACT | [6 empty] | 15.12%
|  | CLAIMED TO DATE AGAINST CONTRACT |  | 2193954.35 |  |  |  |  | 49.28% |  |  |  | 55.48%
|  | CLAIMED AGAINST CLAIMABLE VALUE |  | 2193954.35 |  |  |  |  | 61.68%
|  | CLAIMABLE AMOUNT - BILL 11 (13-04-26) |  | 110000 |  |  |  |  | 2.471%
[9 empty] | 14.87% |  |  |  | 14.02%
|  | Progres Against Contract Vs Revised Value | [6 empty] | Planned VS Actual Cost |  |  |  | Planned Vs Actual Progress
4451632.747
27955.916
[8 empty] | 508.2894 | 0

## Sheet38 (hidden)
S/N | DESCRIPTION OF WORK | UOM | QTY | RATE | AMOUNT
1 | MAINTENANCE EXTENSION | SQM | 1760 | 447.71 | 787969.6
2 | REVISED DOORS
| D1 - ALUM. DOOR | NR | 20 | 1300 | 26000
| D2 - ALUM. DOOR | NR | 20 | 400 | 8000
821969.6

## SUMMARY
S/N | DESCRIPTION | BOQ AMOUNT | REVISED AMOUNT (CLAIMABLE) |  | OMISSION AMOUNT (SAVINGS) | ADDITION AMOUNT | ENQUIRY ON ITEM OF WORK (AMOUNT)
BILL NO 1 | PRELIMINARIES | 227580 | 102780 |  | 124800 |  | -------------
BILL NO 2 | DAY WORK | 88252.5 | 0 |  | 88262.5 |  | -------------
BILL NO 3 | PROVISIONAL SUM | 200000 | 0 |  | 200000 |  | -------------
SUBSTRUCTURE WORK
BILL NO 4 | 20 NEW HOUSING UNIT | 947257 | 656066.0415 |  | 291914.7084 |  | -------------
BILL NO 5 | MAINTENANCE HOUSING UNIT - 29 UNIT | 1436308.607 | 1426316.802 |  | 9991.805 | 11890 | -------------
BILL NO 6 | PROTECTION AND STORM WATER DRAINAGE | 265674.675 |  |  | 265674.675 |  | -------------
BILL NO 7 | 3 NEW HOUSING UNIT | 36105 | 25589.844 |  | 10515.156 |  | -------------
SUPERSTRUCTURE WORK
BILL NO 4 | 20 NEW HOUSING UNIT | 1018113.94 | 894712.44 |  | 123401.5 | 23100
BILL NO 7 | 3 NEW HOUSING UNIT | 203886.025 | 181521 |  | 25110 | 1111.44 | -------------
BILL NO 4 | EXTERNAL WORK (20 NEW HOUSING UNIT) | 28455 | 26355 |  | 2100 |  | -------------
|  | 4451632.747 | 3313341.1276 | 1138291.6194 | 1141770.3444

## SUMMARY OF BILL NO. (4 - 7) (hidden)
BILL NO 4 (20 NEW HOUSING UNIT)
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | ADDITION AMOUNT | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| SUBSTRUCTURE WORKS | [5 empty] | 0 |  | 0 |  | #VALUE! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #VALUE!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #VALUE!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #VALUE!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #VALUE!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #VALUE!
SUPERSTRUCTURE WORK | [6 empty] | 0 |  | 0 |  |  | #VALUE!
SUB - TOTAL
| SUBSTRUCTURE | [5 empty] | 0 | 0 | 0 |  | #VALUE! | #REF!
| SUPERSTRUCTURE | [5 empty] | 0 |  | 0 |  | 0 | #VALUE!
20 NEW HOUSING UNITS | [6 empty] | 0 | 0 | 0 |  | #VALUE! | #REF!
BILLL NO 4 (EXTERNAL WORKS)
Item Code | Item Name | Item Details | Additional Information | UOM | Unit Price In Figure | BOQ QTY | BOQ Amount | Revised QTY | Revised Amount (CLAIMABLE) | Addition/Omission Quantity | ADDITION AMOUNT | OMISSION
EW11 | External Works General Site Works | Design and Build Shaded Car Parking of 20 numbers with Solar Panel Canopy | Allow for the Contractor to design and build the Shaded Car Park for houses with Solar Panel Canopy as per Engineer Employer Instruction. | no | 105 | 20 | 2100 | 0 | 0 | 20 |  | 2100
EXTERNAL WORK (20 NEW HOUSING UNIT) | [6 empty] | 2100 |  | 0 |  | 0 | 2100
BILL NO 5 (MAINTENANCE OF 29 HOUSING UNITS)
Item Code | Item Name | Item Details | Additional Information | UOM | BOQ Qty | Revised QTY | Unit Price In Figure-OMR | BOQ Total Amount-OMR | Revised Amount (Claimable) | Saving Quantities | ADDITION AMOUNT | Savings Amount
EX7 | External Works Lump sum | Dewatering | Allow for keeping excavations free from underground surface or running water from whatever source | Item | 29 | 29 | 252 | 7308 | 0 | 29 |  | 7308
P8 | Sanitary Wares and Fittings | shower tray | Supply and install white glazed shower tray size 70x70 with the necessary fittings and plumbing darins including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 29 | 12.6 | 365.4 | 0 | 29 |  | 365.4
E2 | Electrical Engineering Installation | Contractor to provide full Solar system | The contractor to Design and Provide the solar system including all materials and supply and fix it to be compatible with the MCCP and DBs at the houses and get the approvals from the ClientEngineer before executing any work | Item | 29 | 0 | 0 | - | 0 | 29 |  | 0
E5 | Electrical Engineering Installation | Sub Main Distribution Board | The contractor to add a new DB for the New Caravans to be weatherproof GRP IP 65 . | Item | 29 | 29 | 62.566 | 1814.414 | 0 | 29 |  | 1814.414
E25 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commission of the following lighting fixtures Emergency light | Item | 29 | 29 | 17.379 | 503.991 | 0 | 29 |  | 503.991
G1 | Sundrie | Sundrie Items | Any other works not specifically enumerated under the works in this bill but indicated in the drawings or required to complete the work in manner of respect to handover the project in working and safe conditions to the residents specification or needed to complete the work. | Item | 29 | 29 | 52.138 | 1512.002 | 1512.002 | 0
BIL NO 5 - MAINTENANCE WORK | [7 empty] | 11503.807 | 1512.002 |  | 0 | 9991.805
BILL NO 6 (STORM WATER AND PROTECTION)
Item Code | Item Name | Item Details | Additional Information | Unit | Qty | Unit Price in Figure | Omission work | Total Price in Figure
PSW9 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 0 to 2m | m3 | 9180 | 0.7 | 6426 | 6426
PSW10 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 2m to 2m | m3 | 12615 | 1.575 | 19868.625 | 19868.625
PSW11 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 3m to 4m | m3 | 3090 | 2.1 | 6489 | 6489
PSW12 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth more than 4m | m3 | 4080 | 4.2 | 17136 | 17136
PSW13 | 3 Granular Subbase Aggregate Base Course and Stabilized Base Courses. | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Aggregate Base Course Class B | m3 | 1500 | 2.1 | 3150 | 0
PSW14 | 4 Bituminous Pavement | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Bituminous Prime Coat Application rate 1.5 KgSq.m | m3 | 4050 | 2.1 | 8505 | 0
PSW15 | Asphalt Road | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Bituminous Wearing Course Class B | m3 | 280 | 12.6 | 3528 | 0
PSW18 | Concrete and Concrete Structures | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Concrete Class 35 in box culverts wing walls apron slab retaining walls and debris foundations. | m3 | 375 | 12.6 | 4725 | 0
PSW20 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | High tensile steel bar factory epoxy coated reinforcement of any diameter | Ton | 55 | 94.5 | 5197.5 | 0
PSW22 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Tar or bituminous paint Type II 2 coats for surfaces in contact with earth in all structures | m2 | 1420 | 1.05 | 1491 | 0
PSW23 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Membrane Waterproofing Geotextile 4mm thickness | m2 | 15500 | 1.05 | 16275 | 0
PSW25 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 300mm | m | 315 | 3.15 | 992.25 | 992.25
PSW26 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 400mm | m | 1270 | 2.1 | 2667 | 2667
PSW27 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 500mm | m | 345 | 1.575 | 543.375 | 543.375
PSW28 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 600mm | m | 865 | 1.575 | 1362.375 | 1362.375
PSW29 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 700mm | m | 1090 | 2.1 | 2289 | 2289
PSW30 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 800mm | m | 460 | 2.1 | 966 | 966
PSW31 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 900mm | m | 130 | 3.15 | 409.5 | 409.5
PSW32 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 1200mm | m | 490 | 3.15 | 1543.5 | 1543.5
PSW34 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1200mm Type A | No | 48 | 3.15 | 151.2 | 151.2
PSW35 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1500mm Type A | No | 21 | 4.2 | 88.2 | 88.2
PSW36 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 2000mm Type A | No | 9 | 4.2 | 37.8 | 37.8
PSW37 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1500mm Type B | No | 8 | 4.2 | 33.6 | 33.6
PSW38 | Drainage | Manholes Inlets and Chambers | Gully Grating and Frame DI HEavy Duty | No | 145 | 4.305 | 624.225 | 624.225
PSW39 | Drainage | Manholes Inlets and Chambers | UPVC Drainage pipe to drain gully to manhole 200mm Diamter | No | 2010 | 4.305 | 8653.05 | 8653.05
TOTAL OMISSION BILL NO 6 | [7 empty] | 70280.7
BILL NO 7 ( 3 NEW HOUSING UNITS)
Item Code | Item Name | Item Details | Additional Information | UOM | BOQ-Quantity | Unit Price In Figure | BOQ Total Amount-OMR | REVISED QTY | REVISED AMOUNT (CLAIMABLE) | QUANTITIES | ADDITION AMOUNT | Amount
C1 | General Works | Demolishing and Clearing the Construction Area. | Demolishing the complete buildings up to foundations and removing the debris from the Construction Site as per Engineer/Employer Instruction (including cart-away from the Project Site) | LS | 1 | 2000 | 2000 | 1 | 2000 | 0 |  | 0
C2 | Substructure Works | Site Clearance | This shall include removing vegetation, undergrowth, bushes, hedges, trees, other temporary buildings, structures,... or the like all complete to clean the full plot. | LS | 1 | 1000 | 1000 | 1 | 1000 | 0 |  | 0
C3 | Substructure Works | Earth work and Excavation | Bulk Excavation to receive foundations in any kind of soil including hard soil and rock, earth sport, underground, surface or running water from whatever source if any, for the new foundation building area including removal of old buildings' foundations, cleaning the site, and removing all debris (not suitable for backfilling) from the project area to the damp yard, contractor to prepare all areas to receive new foundation safely as per drawings and soil report | M3 | 350 | 0.8 | 280 | 280 | 224 | 70 |  | 56
C4 | Substructure Works | Filling | Approved imported granular fill material compacted in layers in making up levels in the excavation area of the demolished buildings from foundation level up to levels on site plan. | M3 | 400 | 0.5 | 200 | 0 | 0 | 400 |  | 200
C5 | Substructure Works | Filling | Approved imported fill material compacted in layers to raise the levels | M3 | 200 | 0.5 | 100 | 0 | 0 | 200 |  | 100
C6 | Substructure Works | Filling | Approved, selected excavated material backfilled into excavations | M3 | 350 | 0.5 | 175 | 219.852 | 109.926 | 130.148 |  | 65.074
C7 | Substructure Works | Filling | 200 mm thick well compacted hardcore filling under floors | M3 | 35 | 0.5 | 17.5 | 0 | 0 | 35 |  | 17.5
C8 | Substructure Works | Anti-termite treatment | Anti-termite treatment to surfaces of ground or filling applied strictly in accordance with the manufacturers printed instructions including digging trenches, backfilling, etc. as required by the manufacturer and the provision of guarantee valid for 10 years | M2 | 150 | 1.5 | 225 | 97.76 | 146.64 | 52.24 |  | 78.36
C9 | Substructure Works | Poured Concrete - Plain insitu concrete, poured ordinary Portland Cement (OPC), concrete grade (C15), all in accordance with Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Blinding upto 100 mm thickness for the full area under the boundary of foundation. | M3 | 17.5 | 45 | 787.5 | 12.184 | 548.28 | 5.316 |  | 239.22
C10 | Substructure Works | Reinforced insitu concrete, poured vibrated Sulphate Resistent Cement (OPC), concrete grade (C30), all in accordance with Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Footings | M3 | 45 | 50 | 2250 | 41.254 | 2062.7 | 3.746 |  | 187.3
C11 | Substructure Works | Plinth Beam | Plinth Beam | M3 | 14 | 50 | 700 | 10.829 | 541.45 | 3.171 |  | 158.55
C12 | Substructure Works | Reinforced insitu concrete, poured vibrated Sulphate Resistent Cement (OPC), concrete grade (C30), all in accordance with Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Steel fabric reinforcement, A-393 BRC mesh in two layers. All complete in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Beds (Slabs, Grade slabs) upto 200 mm thickness | M3 | 30 | 50 | 1500 | 20.112 | 1005.6 | 9.888 |  | 494.4
C13 | Substructure Works | Reinforced insitu concrete, poured vibrated ordinary Portland Cement (OPC), concrete grade (C40), all in accordance with Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Substructure columns | M3 | 4 | 50 | 200 | 3.463 | 173.15 | 0.537 |  | 26.85
C14 | Substructure Works | Concrete / Block work Protection | Polythene sheet, gauge 1200, all in accordance with Drawings and Specifications - to surfaces of structural members in contact with soil | M2 | 115 | 0.5 | 57.5 | 85.34 | 42.67 | 29.66 |  | 14.83
C15 | Substructure Works | Bitumenous Sheet | Bitumenous Paint base coat and 4mm membrane to the surfaces of concrete and block work( foundation + solid block work + short columns ) | M2 | 300 | 5 | 1500 | 0 | 0 | 300 |  | 1500
C16 | Substructure Works | Bitumenous Paint | Bitumenous paint 3 coats to the surfaces of concrete ( plinth beams ) | M2 | 145 | 0.5 | 72.5 | 0 | 0 | 145 |  | 72.5
C17 | Substructure Works | Concrete solid block work, 10.5N/mm2 compressive strength, cement and sand mortar (1:3), with and including stiffener columns and stiffener beams, as required, all in accordance with Drawings and Specifications | 200mm thick walls | M2 | 120 | 6 | 720 | 70.922 | 425.532 | 49.078 |  | 294.468
C18 | Substructure Works | Block work Protection including Bitumenous Paint and Bitumenous Sheet | Protection to concrete and excavated area, masonry/block work in contact with soil, Bitumenous Paint base coat of approved bituminous paint, 4mm bituminous sheet, and including flexible board all in accordance with Drawings and Specifications - to surfaces of block work in contact with soil.up to bottom of plinth beams | M2 | 250 | 1 | 250 | 250 | 250 | 0 |  | 0
| BILL NO 7. (3 NEW HOUSING UNIT) - SUBSTRUCTURE WORKS |  |  |  |  | 1 UNIT | 12035 |  | 8529.948 |  | 0 | 3505.052
[6 empty] | 3 UNITS | 36105 |  | 25589.844 |  | 0 | 10515.156

## MAS (hidden)
PROVISIONAL SUM
Item Code | Item Name | Item Details | Additional Information | UOM | Quantity | Unit Price | Total Price In Figure | STATUS
BILL NO. 4 (20 - NEW HOUSING UNITS)
Item Code | Item Name | Item Details | Additional Information | UOM | Quantity | Unit Price | Total Price In Figure
C91 | Superstructure Works Finishes | Allow for supply fabricate and installation of water point protection as per the specifications drawings and to approval of the Engineer. | Water point protection | No | 20 | 47.25 | 945 | Pending | Reason
C92 | Superstructure Works Finishes | Allow for supply fabricate and installation of Meter Panel protection as per the specifications drawings and to approval of the Engineer. | Meter Panel protection | No | 20 | 47.25 | 945 | Pending | Design Issue
F1 | Fire Fighting Installation | Fire Fighting Installation | Supply and install a complete fire fighting system to the approval of the Civil Defence Authorities and complete with association and fitting as shown in drawings or specified in accordance with BS 530 Part 1 1976 and Part 3 1985 and to approval of the Engineer. | Item | 1 | 0 | 0 | Cancelled
F2 | Fire Fighting Installation | Fire hose reel | 1.5 mm thick Electro static powder coated painted stainless steel recessed type fire hose reel cabinet with 25 mm diameter hose reel and 45 meter long including 1 No. 9 litter foam type fire extinguisher and 1 No 5Kg carbon dioxide type fire extinguisher with civil defence final approval certificate. | No | 3 | 0 | 0
F3 | Fire Fighting Installation | outlet | Wet riser outlet with valve assembly | NO | 3 | 80 | 240 | Pending | Reason
F4 | Fire Fighting Installation | valve | Zonal control valve assembly | NO | 1 | 120 | 120 | Pending | Reason
F5 | Fire Fighting Installation | inlet | Breaching inlet | NO | 1 | 200 | 200 | Cancelled | Not possible
GN4 | Telephone System | Cable | Cable and conduits to telephone outlet points in concealed installation from telephone junction box to IP phone expansion module for reception | No | 120 | 2.45 | 294 | Cancelled
GN5 | Telephone System | Outlet | Cat 6E telephone outlet | No | 120 | 2.45 | 294 | Cancelled
GN6 | Telephone System | Junction box | Telephone junction box | No | 20 | 2.1 | 42 | Cancelled
GN16 | Structured Cabling system | patch panel | 16 Port Cat 6A Patch panel | No | 20 | 8.4 | 168 | Cancelled
GN17 | Structured Cabling system | Structured Cabling system | 500mm single mode fiber LC SC Patch cords | No | 20 | 9.45 | 189 | Pending
GN18 | Structured Cabling system | Accessories | Accessories and stacking kits and cable management and cable organizer and cable channels and supports all types of cords and pig tail connectors including termination etc complete | Item | 1 | 1050 | 1050 | Under Review
GN19 | CCTV System | PTZ Camera | PTZ Vandal proof with weather proof Bullet type Day and Night vision CCTV IP camera Outdoor as specified. | No | 40 | 26.25 | 1050 | Under Review
GN20 | CCTV System | pulling box | Allow for cable pulling boxes | Item | 1 | 1575 | 1575 | Under Review | Basic Structure not available
E25 | MAIN DISTRIBUTION BOARD Electrical Engineering Installation | Main Distribution Board | Main Distribution panel board in weather proof Stainless steel enclosure IP 65 including 2 nos 600A and 4 nos 400A and 1NOS spare100 A and 1 NOS spare 200A Incoming MCCB Breaker and 4nos 200A and 2nos spare 100 A Outgoing MCCB Breakers and supports and Busbar and earthing and cable glands and Ammeters and Voltmeters and internal wiring interconnection 1PH 3PH KWH series meters and labels as per approved MHEW drawings | NO | 6 | 14 | 84 | Under Review
7196
20 NEW HOUSING UNITS - EXTERNAL WORKS
EW11 | External Works General Site Works | Design and Build Shaded Car Parking of 20 numbers with Solar Panel Canopy | Allow for the Contractor to design and build the Shaded Car Park for houses with Solar Panel Canopy as per Engineer Employer Instruction. | no | 105 | 20 | 2100 | Under Review
EW3 | External Works General Site Works | Wicket Gate | Allow for the Contractor to supply fabricate and installation of single leaf Wicket Gate as per the Architectural Drawing and follow as per Engineer Employer Instructions including anti corrotion epoxy paint. | no | 105 | 20 | 2100 | Pending
EW4 | External Works General Site Works | Car Entrance Gate | Allow for the Contractor to supply fabricate and installation of single leaf Car Entrance Gate as per the Architectural Drawing and follow as per Engineer Employer Instructions including anti corrotion epoxy paint | no | 141.75 | 20 | 2835 | Pending
7035
BILL NO. 5 - (29 MAINTENANCE HOUSING UNITS)
C11 | Superstructure Works Metal Works | galvanized steel cat Ladder | Supply and install galvanized steel cat Ladder as specified and detailed on the drawingas per exixting desin hand rail in new houses drawings. | Item | 29 | 262.5 | 7612.5 | Pending
E25 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commission of the following lighting fixtures Emergency light | Item | 29 | 17.379 | 503.991 | Under Review
8116.491
BILL NO. 6 (STORM WATER PROTECTION)
PSW9 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 0 to 2m | m3 | 9180 | 0.7 | 6426 | Cancelled
PSW10 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 2m to 2m | m3 | 12615 | 1.575 | 19868.625 | Cancelled
PSW11 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 3m to 4m | m3 | 3090 | 2.1 | 6489 | Cancelled
PSW12 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth more than 4m | m3 | 4080 | 4.2 | 17136 | Cancelled
PSW13 | 3 Granular Subbase Aggregate Base Course and Stabilized Base Courses. | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Aggregate Base Course Class B | m3 | 1500 | 2.1 | 3150 | Cancelled
PSW14 | 4 Bituminous Pavement | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Bituminous Prime Coat Application rate 1.5 KgSq.m | m3 | 4050 | 2.1 | 8505 | Cancelled
PSW15 | Asphalt Road | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Bituminous Wearing Course Class B | m3 | 280 | 12.6 | 3528 | Cancelled
PSW17 | Concrete and Concrete Structures | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Concrete Class 15 in foundations. | m3 | 130 | 13.65 | 1774.5 | Cancelled
PSW18 | Concrete and Concrete Structures | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Concrete Class 35 in box culverts wing walls apron slab retaining walls and debris foundations. | m3 | 375 | 12.6 | 4725 | Cancelled
PSW20 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | High tensile steel bar factory epoxy coated reinforcement of any diameter | Ton | 55 | 94.5 | 5197.5 | Cancelled
PSW22 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Tar or bituminous paint Type II 2 coats for surfaces in contact with earth in all structures | m2 | 1420 | 1.05 | 1491 | Cancelled
PSW23 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Membrane Waterproofing Geotextile 4mm thickness | m2 | 15500 | 1.05 | 16275 | Cancelled
PSW25 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 300mm | m | 315 | 3.15 | 992.25 | Cancelled
PSW26 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 400mm | m | 1270 | 2.1 | 2667 | Cancelled
PSW27 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 500mm | m | 345 | 1.575 | 543.375 | Cancelled
PSW28 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 600mm | m | 865 | 1.575 | 1362.375 | Cancelled
PSW29 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 700mm | m | 1090 | 2.1 | 2289 | Cancelled
PSW30 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 800mm | m | 460 | 2.1 | 966 | Cancelled
PSW31 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 900mm | m | 130 | 3.15 | 409.5 | Cancelled
PSW32 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 1200mm | m | 490 | 3.15 | 1543.5 | Cancelled
PSW34 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1200mm Type A | No | 48 | 3.15 | 151.2 | Cancelled
PSW35 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1500mm Type A | No | 21 | 4.2 | 88.2 | Cancelled
PSW36 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 2000mm Type A | No | 9 | 4.2 | 37.8 | Cancelled
PSW37 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1500mm Type B | No | 8 | 4.2 | 33.6 | Cancelled
PSW38 | Drainage | Manholes Inlets and Chambers | Gully Grating and Frame DI HEavy Duty | No | 145 | 4.305 | 624.225 | Cancelled
PSW39 | Drainage | Manholes Inlets and Chambers | UPVC Drainage pipe to drain gully to manhole 200mm Diamter | No | 2010 | 4.305 | 8653.05 | Cancelled
PSW41 | Slope protection and Stablization | Existing Dyke Improvement | Remove the existing dyke use the suitable backfilling and compact in the new place in layers as per Oman specifications shift not suitable existing backfilling materials to damp yard etc. | Item | 1 | 52.5 | 52.5 | Cancelled
114979.2
BILL NO. 7 (3 NEW HOUSING UNITS )
C37 | Superstructure Works Metal Works | CAT Ladder | Supply and install a 3800mm high CAT steel Ladder as specified and detailed on the drawing, with anti-correlation epoxy pain. | No | 1 | 100 | 100 | Pending
C82 | Superstructure Works Finishes | Allow for supply, fabricate and installation of Meter Panel protection as per the specifications, drawings and to approval of the Engineer. | Meter Panel protection | Item | 1 | 100 | 100 | Pending
G1 | Gas supply line | Gas line | Supply and fix 18 mm diameter MS schedule 40 gas pipeline including pickup points and connection to Gas Stove | M | 10 | 50 | 500 | Under Review
GN4 | Telephone System | TV System Installation | Cable and conduits to telephone outlet points in concealed installation from telephone junction box to IP phone expansion module for reception | No | 4 | 50 | 200 | Under Review
GN5 | Telephone System | Outlet | Cat 6E telephone outlet | No | 4 | 10 | 40 | Under Review
GN6 | Telephone System | Junction box | Telephone junction box | No | 1 | 50 | 50 | Under Review
EW10 | External Works - General Site Works | Design and Build Shaded Car Parking of 20 numbers with Solar Panel Canopy | Allow for the Contractor to design and build the Shaded Car Park for houses with Solar Panel Canopy, as per Engineer / Employer Instruction. | Item | 1 | 1300 | 1300 | Cancelled
P42 | Water Supply installation | Booster pump | Cold water pressurised booster pump set 1No Working pump and 1No standby pump for domestic water supply delivering 2 l per sec at 2.5 bar with Gate valve and Non return valve and float switch and pressue guage and pressure vessel 30 to 50 lit PN10 and water low level cut off relay etc with pump room all complete as detailed in the drawing to approval. | No | 1 | 1500 | 1500 | Pending
EW5 | External Works - General Site Works | Wicket Gate | Single leaf Wicket Gate solid WPC | Item | 1 | 900 | 900 | Pending
EW6 | External Works - General Site Works | Car Entrance Gate | Single leaf Car Entrance Gate soild WPC | Item | 1 | 1200 | 1200 | Pending
[6 empty] | 1 UNIT | 5890
[6 empty] | 3 UNIT | 17670

## Copy of GRANT SUMMARY
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
GRAND SUMMARY
Priced Bill Of Quantities
Transfer the Contract Summary of Contract Value to the Form of Tender
S/N | BILL NO | DESCRIPTION | BOQ AMOUNT | BOQ AMOUNT | REVISED VALUE AFTER V.O 1 | Addition | Omission | Savings Excluding V.O 1 | EXPECTED REVISED BOQ VALUE AFTER A/O |  | ADDITION AMOUNT/VARIATION | SAVING AMOUNT | % |  |  | CLAUSES | Appendix
1 | BILL NO 1 | PRELIMINARIES | 227580 | 227580 | 227580 | 0 | 124800 | 124800 | 102780 | -124800 |  | 124800 | 54.8379 | 2.901% | 2.901% |  | Bill No 1. (PRELIMINARIES)
2 | BILL NO 2 | DAY WORKS | 88252.5 | 88252.5 | 88252.5 | 0 | 88252.5 | 88252.5 | 0 | 88252.5 |  | 88262.5 | 100 | 0% | 0% |  | Bill No 2. (DAY WORK)
3 | BILL NO 3 | PROVISIONAL SUM | 200000 | 200000 | 0 | 0 |  |  | 0 | 0 |  | 200000 | 0 | 0% |  |  | Bill No 3. (PROVISIONAL SUM)
4 | BILL NO 4 | NEW HOUSING UNIT (20 UNITS) | 1965370.94 | [11 empty] | 44.41%
|  | SUBSTRUCTURE WORKS |  | 947257 | 947257 | 0 | 291914.7084 | 291914.7084 | 655342.2915 | -363427.5831 |  | 291914.7084 | 30.8168 | 18.5% |  | 12.1 | 20 NEW ADD QTY
|  | SUPERSTRUCTURE WORKS |  | 1018113.94 | 1018113.94 | 23100 | 123401.5 | 100301.5 | 917812.44 | 817510.94 | 23100 | 123401.5 | 9.8517 | 25.91% |  | 12.2 | GRAND SUM. ADD. (Bill No. 4 & 7)
5 | BILL NO 4 | EXTERNAL WORKS AND EXTERNAL SERVICES | 28455 | 28455 | 28455 | 0 | 2100 | 2100 | 26355 | 26355 |  | 2100 | 7.3801 | 0.744% | 0.744% |  | BIll No 4 (20 NHI EXXTERNAL WORK)
6 | BILL NO 5 | MAINTENANCE WORKS FOR THE EXISTING HOUSING UNITS (29 NO) | 1436308.607 | 1436308.607 | 1436308.607 | 11890 | 9991.805 | -1898.195 | 1438206.802 | 1440104.997 | 11890 | 9991.805 | -0.13216 | 40.6% | 40.6% | 12.2 | ADD. WORK (29 - MHU)
7 | BILL NO 6 | PROTECTION AND STORM WATER DRAINAGE | 265674.675 | 265674.675 | 265674.675 | 0 | 70280.7 | 70280.7 | 195393.975 | -125113.275 |  | 70280.7 | 26.4537 | 5.516% | 5.516% |  | ADD. WORK ON CHANNEL
8 | BILL NO 7 | 3 NUMBER HOUSING UNITS | 239991.025 | [11 empty] | 5.834%
|  | SUBSTRUCTURE WORKS |  | 36105 | 36105 | 0 | 10515.096 | 10515.096 | 25589.904 | 15074.808 |  | 10515.156 | 29.1237 | 0.7224% |  | 12.1 | 20 NHU ADD. QTY/ Bill No 7. (3 NHU)
|  | SUPERSTRUCTURE WORK |  | 203886.025 | 203886.025 | 2295 | 25110 | 22815 | 181071.025 | 158256.025 | 1111.44 | 25110 | 11.1901 | 5.111% |  | 12.2 | SUM. OF ADD. WORKS (Bill No 4 & 7)
[14 empty] | #REF! | #REF!
[9 empty] | 0 |  |  |  | 982477.8095
0
Total Contract Value |  |  | 4451632.747 | 4451632.747 | 4251632.747 | 37285 | 746366.3095 | 709081.3095 | 3542551.4375 | 909081.3095 | 36101.44 | 946376.3695
[6 empty] | 709081.3095 |  |  | 909081.3095 |  |  | 946376.3695
1455447.6189
|  |  |  | CONTRACT PRICE |  |  |  |  | CLAIMABLE |  |  | ADD/OMISSION IMPACT |  | 336267.29 |  | 19525
[14 empty] | 115915.29 |  | 624800 | 4167351.4375
|  | PERCENTAGE |  | AMOUNT |  |  |  |  | PERCENTAGE | 1618162.6189 |  | 982477.8095
| Addition/Omission and Change Order Impact | CONTRACT TOTAL VALUE |  | 4451632.747 |  |  |  |  | 100% | 0 | [6 empty] | 284281.3095
|  | CLAIMABLE TOTAL AMOUNT |  | 3542551.4375 |  |  |  |  | 79.58%
|  | ADDITION OMMISSION IMPACT |  | 946376.3695 |  |  |  |  | 21.26%
|  | ADDITIONAL WORK BILL NO. 5 |  | 1111.44 |  |  |  |  | 4.975% |  |  | 221463.44
|  | CHANGE ORDER -2 |  | 220352
|  | NET FINANCIAL IMPACT |  | 3764014.8775 |  |  |  |  | 84.55%
| Progress Impact | OVERALL FINANCIAL IMPACT | [6 empty] | 15.45%
|  | CLAIMED TO DATE AGAINST CONTRACT |  | 2193954.35 |  |  |  |  | 49.28% |  |  | 55.61%
|  | CLAIMED AGAINST CLAIMABLE VALUE |  | 2193954.35 |  |  |  |  | 61.93%
|  | CLAIMABLE AMOUNT - BILL 11 (13-04-26) |  | 110000 |  |  |  |  | 2.471%
[9 empty] | 15.12% |  |  | 13.89%
|  | Progres Against Contract Vs Revised Value | [6 empty] | Planned VS Actual Cost |  |  | Planned Vs Actual Progress

## BILL NO 1. (PRELIMINARIES)
BILL NO 1. (PRELIMINARIES)
Item Code | Item Name | Item Details | Additional Information | UOM | BOQ-Quantity | Unit Price | BOQ Total Amount | Claimable Amount | Addition & Omission Quantity | Omission | Addition | Overall Prelim. Excluding P111 |  | 102780
Fixed Preliminaries
P1 | Preliminary and General Requirements Tender Drawings | Notes | All items will be priced individually. Any item not priced hereunder will be deemed to be included in the Contractors Tender. | Item | 0 | 0 | 0 | 0 |  |  |  |  | P8 | 10500
P2 | Preliminary and General Requirements Tender Drawings | Tender Drawings | The Tender Drawings are listed in Volume 4 Tender Drawings. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P9 | 10500
P3 | Preliminary and General Requirements Conditions of Contract | Conditions of Contract | The Conditions of Contract shall be those contained within the Sultanate of Oman Standard Documents for Building and Civil Engineering Works prepared and issued by the Ministry of Finance Muscat. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P32 | 1575
P4 | Preliminary and General Requirements Conditions of Contract | Conditions of Contract | The Contractor shall allow for complying in all respect with the Conditions of Contract. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P33 | 1575
P5 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | The Contractor shall be responsible for checking all drawings and schedule etc. supplied by the Engineer. In the event of any discrepancy being found between such drawings and schedules etc. or if the Contractor considers that additional detail drawings are required then in either case the Contractor shall report such discrepancy to the Engineer for instruction or apply in writing for such detail drawings at least 28 days before the materials and components necessary for the works are to be placed on order by the Contractor. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P70 | 1575
P6 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | The Contractor shall ascertain from the drawings or otherwise any holes recesses plugs etc. which may be required in time to form these as the work proceeds. No extra payments will be allowed for cuttings or forming such holes subsequently. | Item | 1 | 0 | 0 | 0 | [5 empty] | 25725
P7 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | The Contractor will prepare at his own cost detailed working and shop drawings that may require supplementary to the construction drawings furnished by the Engineer. | Item | 1 | 0 | 0 | 0 |  |  |  | Time based Preliminaries
P8 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | The detail and working drawing for civil and building works shall be prepared by the contractor supplement the construction drawings furnished by the Engineer will include Reinforcement details and Other drawings. | Item | 1 | 10500 | 10500 | 10500 |  |  |  |  | P54 | 1050
P9 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | The detail and working drawing for civil and building works shall be prepared by the contractor supplement the construction drawings furnished by the Engineer will include the Drawings and details of foundation for equipment machinery and technical installation. | Item | 1 | 10500 | 10500 | 10500 |  |  |  |  | P56 | 1575
P10 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | Such drawing and detail will depend on the type and make of the equipment offered and will include in particular foundations etc. for the standby power generators chiller and radiators transformers ventilation and airconditioning equipment etc. Construction details as required. | Item | 1 | 0 | 0 | [5 empty] | P66 | 15750
A |  |  | SUM FOR PAGE1/13 |  |  |  | 21000 | 21000 |  |  |  |  | P67 | 7560
[13 empty] | P68 | 15120
P11 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | No drawing etc. prepared by the Contractor shall be used in the works before the Engineer has approved it. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P72 | 525
P12 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | The Contractor shall submit to the Engineer for his approval two copies of all his detail working or shop drawings and related documents produced by him for use in construction work. Any changes or modifications considered necessary by the Engineer shall be made at no extra cost to the Employer. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P73 | 525
P13 | Preliminary and General Requirements Contractors Administration Arrangements | Drawings | Drawings and other documentation submitted to the Engineer for approval during the construction period should in no case be submitted later than two weeks before the date when the drawings or documents will be required on site for construction purpose. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P98 | 1050
P14 | Preliminary and General Requirements General Instruction | DESCRIPTION OF THE WORKS | The work under this Contract comprises the provision of all materials plant and labour of whatever kind necessary and the proper performance of every operation required for the complete and proper construction completion commissioning and maintenance of Proposed 20 Nos Housing Units at Halaniyat Island including civil structural mechanical and electrical services and external works. The exact scope of work is indicated in the Tender Drawings. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P114 | 25200
P15 | Preliminary and General Requirements General Instruction | GENERAL INSTRUCTIONS | The Tenderer shall insert a lumpsum or rate to each individual item Clause or SubClause in this Bill which he considers has a financial implication or is of financial value. Where the Contractor considers that an item Clause or SubClause has no financial value he shall insert the word Nil. Lump Sums shall not be inserted covering more than one item Clause or SubClause. | Item | 1 | 0 | 0 | 0 |  |  |  |  | P115 | 8700
P16 | Preliminary and General Requirements General Instruction | GENERAL INSTRUCTIONS | The value of services and obligations involved in all the items Clauses and SubClauses in this Bill shall not be included in rates or prices in other Bills of Quantities but shall be priced in their totality in this Bill. | Item | 1 | 0 | 0 | 0 | [5 empty] | 77055
P17 | Preliminary and General Requirements Contractors Administration Arrangements | Contractors Administrative Arrangements | No examination or approval by the Engineer of any drawing or order documents submitted by the Contractor shall relieve the Contractor of any of his responsibilities under the Contract. | Item | 1 | 0 | 0 | 0
P18 | Preliminary and General Requirements Contractors Administration Arrangements | Site Administration | The Contractor shall allow for providing all that is required for the proper administration of the Contract at site level and in particular for complying in all respects with the relevant Clauses in the Standard Conditions of Contract. | Item | 1 | 0 | 0 | 0 |  |  |  | Vessel |  | 40000
P19 | Preliminary and General Requirements Contractors Administration Arrangements | Site Inspection | The Contractor is advised to visit and inspect the site during tendering at his own cost and hire own boat and to satisfy himself as to the accessibility and full extent and character of the site and of all local conditions and restrictions including the provision of and any matter referred to in Clause 11 of the Conditions of Contract.. | Item | 1 | 0 | 0 | 0 |  |  |  | Head Office Exp |  | 13232
B |  |  | SUM FOR PAGE2/13 |  |  |  | 0 | 0 |  |  |  | OPC/SRC self life |  | 5935
[12 empty] | Warehouse Taqa |  | 2200
P20 | Preliminary and General Requirements Contractors Administration Arrangements | Access to the site | Access to the site will be from existing roads adjacent to the site.Access to the site may be obtained by prior arrangement with Engineer. During the construction and maintenance stages the Contractor will be responsible for complying with all of the Employers security and safety requirements. | Item | 1 | 0 | 0 | 0 |  |  |  | Logistics |  | 2700
P21 | Preliminary and General Requirements Contractors Administration Arrangements | Access to the site | During construction the Contractor will afford access to the site to any persons or Company employed directly by the Employer for the purpose of carrying out work at the site and will liaise with that person or company to agree a work procedure to ensure a mutually beneficial programme of work and to provide such services as are required in accordance with Clause 31 of the Conditions of Contract. | Item | 1 | 0 | 0 | 0 |  |  |  | Eng. Accomodations |  | 1260
P22 | Preliminary and General Requirements Contractors Administration Arrangements | Access for Plant | The Contractor should allow for all costs involved in making access arrangements for any items of plant etc. without risk of damage to roads leading to the site and such like and for reinstatement thereto. | Item | 1 | 0 | 0 | 0 |  |  |  | Prolongation Overhead Cost |  | 65327
P23 | Preliminary and General Requirements Contractors Administration Arrangements | Limitations of Working Space | The Contractor shall confine his apparatus the storage of materials and the operations of the workman to the site and shall not be unreasonably encumber the area with his materials. | Item | 1 | 0 | 0 | 0
P24 | Preliminary and General Requirements Contractors Administration Arrangements | Limitations of Working Space | The Contractor shall be entirely responsible for complying with municipality regulations regarding fencing the site storage of materials and spoil heaps unloading of materials temporary building sanitary arrangements etc. No claims for delay or costs will be entertained in the event of work being stopped for breach of regulations. | Item | 1 | 0 | 0 | 0
P25 | Preliminary and General Requirements Contractors Administration Arrangements | Limitation of Working Hours | Any work which in accordance with Clause 45 of the Conditions of Contract or by agreement with the Engineer executed outside of normal working hours or on Fridays or Public Holidays shall be carried out in such a way as to cause the absolute minimum of disturbance or inconvenience to the Residents or users of the buildings near or adjacent to the works. | Item | 1 | 0 | 0 | 0
P26 | Preliminary and General Requirements Contractors Administration Arrangements | Limitation of Working Hours | The Contractors specific attention is drawn to the clauses in the specification relating to restriction of placement of certain items of work in certain weatherstemperature conditions and he is to allow for complying with these requirements. | Item | 1 | 0 | 0 | 0 |  |  |  | Time Based Claim/Day |  | 105.5548
P27 | Preliminary and General Requirements Contractors Administration Arrangements | Restrictions | The site shall not be used for any purpose other than the execution of the Contract. | Item | 1 | 0 | 0 | 0 |  |  |  | Claim for 128 Days |  | 13511.0137
P28 | Preliminary and General Requirements Contractors Administration Arrangements | Restrictions | The Contractor will be required to make good any damage to the surrounding properties caused during the execution of the work and to restore to their original condition after the completion of the works. | Item | 1 | 0 | 0 | 0 |  |  |  | Prolongation Cost Indirect |  | 65327
P29 | Preliminary and General Requirements Contractors Administration Arrangements | Restrictions | Vegetation and trees are not to be cut down or in any way interfered with even if shown on the drawings to be removed or breached until the Engineers permission has been obtained. | Item | 1 | 0 | 0 | 0 |  |  |  | Total Times Based Prelim. Claim |  | 78838.0137
C |  |  | SUM FOR PAGE3/13 |  |  |  | 0 | 0
[12 empty] | Overall Prelim Excluding P111/Day |  | 140.7945
P30 | Preliminary and General Requirements Contractors Administration Arrangements | Vegetation and Trees | Prevent damage to vegetation and trees and provide protection for them in accordance with the Specification. Pay all costs and charges incurred in complying with statutes and regulations regarding trees | Item | 1 | 0 | 0 | 0 |  |  |  | Claim for 128 Days |  | 18021.6986
P31 | Preliminary and General Requirements Contractors Administration Arrangements | Vegetation and Trees | The Contractor shall ascertain for himself the location of existing services on under or over the site. He shall take precautions to protect all such services within the confines of the site temporarily divert as required reinstate on completion and immediately make good any damage at his own expense all to the satisfaction of the Engineer. | Item | 1 | 0 | 0 | 0 |  |  |  | Prolongation Cost Indirect |  | 65327
P32 | Preliminary and General Requirements Contractors Administration Arrangements | Existing Services | The Contractor shall ascertain for himself the location of existing services on under or over the site. He shall take precautions to protect all such services within the confines of the site temporarily divert as required reinstate on completion and immediately make good any damage at his own expense all to the satisfaction of the Engineer. | Item | 1 | 1575 | 1575 | 1575 |  |  |  | Total Overall Prelim Based Claim |  | 83348.6986
P33 | Preliminary and General Requirements Contractors Administration Arrangements | Existing Services | Allow for locate protect uphold temporarily divert if necessary and maintain all pipes ducts drains sewers service mains overhead or underground electrical telephone cables etc. during execution of the Works. The Contractor shall make good any damage to existing services andor property however caused at his own expense or pay any costs or charges in connection. Approval shall be obtained a minimum of two weeks in advance of any planned interruption of services. | Item | 1 | 1575 | 1575 | 1575
P34 | Preliminary and General Requirements Contractors Administration Arrangements | Existing Services | Existing services and their locations may not be fully shown on the drawings and the Contractor shall liaise with the relevant authorities to determine the exact nature and full extent of such services which require protection and maintenance. | Item | 1 | 0 | 0 | 0
P35 | Preliminary and General Requirements Contractors Administration Arrangements | Supervision | Detailed Curriculum Vitae of the Contractors Supervisory staff together with those of his SubContractors Supervisors must be submitted for the Engineers approval prior to commencement of the Works. | Item | 1 | 0 | 0 | 0
P36 | Preliminary and General Requirements Contractors Administration Arrangements | Supervision | The Project Manager Project Engineer shall not be changed without one months written notice to the Engineer. | Item | 1 | 0 | 0 | 0
P37 | Preliminary and General Requirements Contractors Administration Arrangements | Security | Allow for providing security to the site. Only those staff and workpeople directly employed on this project will be allowed on site. | Item | 1 | 0 | 0 | 0
P38 | Preliminary and General Requirements Contractors Administration Arrangements | Safety Health and Welfare of Workpeople | Provide for all costs and charges incurred by complying with all safety health and welfare regulations appertaining to staff and workpeople employed on the site including those employed by all SubContractors. | Item | 1 | 0 | 0 | 0
D |  |  | SUM FOR PAGE4/13 |  |  |  | 3150 | 3150
P39 | Preliminary and General Requirements Contractors Administration Arrangements | Safety Health and Welfare of Workpeople | The Contractor shall be responsible for and shall allow for providing medical facilities including emergency medical facilities for his staff and shall make these available to the Engineers staff. | Item | 1 | 0 | 0 | 0
P40 | Preliminary and General Requirements Contractors Administration Arrangements | Safety Health and Welfare of Workpeople | Allow for all costs for providing protective clothing and accessories for all workmen and supervisory staff on site. | Item | 1 | 0 | 0 | 0
P41 | Preliminary and General Requirements Contractors Administration Arrangements | Safety Health and Welfare of Workpeople | Contractors and Subcontractors operatives will not be allowed to eat and sleep on site at any time. Proper shaded areas are to be provided within the site establishment for Contractors and Subcontractors operatives to ensure they do not move outside the site premises. | Item | 1 | 0 | 0 | 0
P42 | Preliminary and General Requirements Contractors Administration Arrangements | Transport of Workpeople | Allow for the cost of all transport to and from site of the workpeople engaged on the site in approved vehicles. | Item | 1 | 0 | 0 | 0
P43 | Preliminary and General Requirements Contractors Administration Arrangements | Constructional PlantSmall Plant and Tools | Provide for all necessary small plant and tools for the proper execution and completion of the Contract. | Item | 1 | 0 | 0 | 0
P44 | Preliminary and General Requirements Contractors Administration Arrangements | Constructional PlantScaffoldingworking platforms | Provide all necessary temporary scaffolding and working platforms for the proper execution and completion of the Contract. Alter relocate and adapt from time to time as necessary. The Contractor is to ascertain whether any scaffolding or platform is required by any SubContractor before striking. If the Contractor should strike any of his scaffolding or working platform and it is so required it shall be reerected at his own expenses. | Item | 1 | 0 | 0 | 0
P45 | Preliminary and General Requirements Contractors Administration Arrangements | Constructional PlantPlant required for Specific Trades | Provide all necessary plant required for specific trades for the proper execution and completion of the Contract. | Item | 1 | 0 | 0 | 0
P46 | Preliminary and General Requirements Contractors Administration Arrangements | Constructional PlantCranes and Lifting Plant | Allow for all cranes and lifting plant necessary for the safe and efficient execution of the works to the satisfaction of the Engineer. | Item | 1 | 0 | 0 | 0
P47 | Preliminary and General Requirements Contractors Administration Arrangements | Constructional PlantPlant generally | Allow for all other plant necessary for the safe and efficient execution of the Works. | Item | 1 | 0 | 0 | 0
P48 | Preliminary and General Requirements Contractors Administration Arrangements | Transport for Work People | The Contractor is to allow for obtaining an adequate labour force for the Works and is to include for transport men to and from the Site as is necessary. | Item | 1 | 0 | 0 | 0
P49 | Preliminary and General Requirements Contractors Administration Arrangements | Site Transportation | Provide all necessary vehicles and other site transport etc. with all consumables store etc. as described for small plant and tools etc. | Item | 1 | 0 | 0 | 0
E |  |  | SUM FOR PAGE5/13 |  |  |  | 0 | 0
P50 | Preliminary and General Requirements Employer Facilities | Temporary Office | Provide erect furnish equip maintain and remove three month after completion of the Contract fully serviced furnished and equipped airconditioned offices and a conference room for the exclusive use of the Engineer all as described in General Requirement of the Architectural Specification. | Item | 1 | 0 | 0 | 0
P51 | Preliminary and General Requirements Employer Facilities | Temporary Office | The offices shall be provided and maintained throughout the period of the Contract. | Item | 1 | 0 | 0 | 0
P52 | Preliminary and General Requirements Employer Facilities | Temporary Office | The Contractor shall be responsible for providing security power water drainage safety helmets safety boots daily cleaning car parking and other facilities to the Engineers offices. | Item | 1 | 0 | 0 | 0
P53 | Preliminary and General Requirements Employer Facilities | Temporary Office | The Contractor shall be responsible during the continuance of the Contract for satisfactorily maintain and security of the offices and for all plans documents and paper and other articles contained there in. | Item | 1 | 0 | 0 | 0
P54 | Preliminary and General Requirements Employer Facilities | Telephone for the Engineer and Employer | Allow for providing the Engineers site office with an independent telephone service until removal of office and for paying all charges incurred by the Engineers staff for business calls concerning the project within the Sultanate of Oman. | Item | 1 | 1050 | 1050 | 1050
P55 | Preliminary and General Requirements Employer Facilities | Attendance on the Engineer | Provide attendance and assistance to the Engineer all as described in the Specification. | Item | 1 | 0 | 0 | 0
P56 | Preliminary and General Requirements Employer Facilities | Surveying and other equipment | The Contractor shall provide to the Engineer for his exclusive use all survey equipment and electrical test equipment as described in the Specification. | Item | 1 | 1575 | 1575 | 1575
P57 | Preliminary and General Requirements Employer Facilities | Mobilisation | The Engineer may issue the notice to proceed at any time within the period of validity of the tender. After the date of the notice to proceed the Contractor shall have a period of 120 days to complete mobilisation and to be completely prepared for the work. After the mobilisation is complete the work shall be carried out in accordance with the requirements of this Contract. | Item | 1 | 0 | 0 | 0
P58 | Preliminary and General Requirements Employer Facilities | Programme and Order of Works | Within 14 days of receipt of an order to commence the Works the Contractor shall submit to the Engineer a detailed programme in respect of all works contained in the scope of works including temporary works and services. | Item | 1 | 0 | 0 | 0
P59 | Preliminary and General Requirements Employer Facilities | Programme and Order of Works | Within 21 days of receipt of an order to commence the Works the Contractor shall submit to the Engineer a detailed programme in respect of all trades separately for each building section and external works and services together with the target dates for receipt of information required to enable the Contractor to comply with this programme. | Item | 1 | 0 | 0 | 0
F |  |  | SUM FOR PAGE6/13 |  |  |  | 2625 | 2625
P60 | Preliminary and General Requirements Employer Facilities | Programme and Order of Works | In addition the Contractor shall at the same time submit to the Engineer a detailed schedule of items and information that he requires instruction upon for early ordering schedules. | Item | 1 | 0 | 0 | 0
P61 | Preliminary and General Requirements Employer Facilities | Coordination | The Contractors attention is drawn to the fact that he shall be entirely responsible for the coordination of all works carried out by both his own workmen and the workmen of SubContractors and shall be responsible for ensuring that all SubContractors shop andor working drawings are submitted to the Engineer for approval in such time as not to prejudice the expeditious execution of the Works in accordance with the Contractors programme. | Item | 1 | 0 | 0 | 0
P62 | Preliminary and General Requirements Employer Facilities | Reports | Provide and maintain daily reports and delivery records for inspection by the Engineer. Such reports must give details of number and category of labour force list of plant list of material deliveries work planned and work carried out climatic conditions high and low temperature and any other information required by the Engineer. | Item | 1 | 0 | 0 | 0
P63 | Preliminary and General Requirements Employer Facilities | Progress Reports | Provide progress reports at intervals and in a format as required by the Engineer. | Item | 1 | 0 | 0 | 0
P64 | Preliminary and General Requirements Employer Facilities | Progress Reports | Provide a camera on site for use by the Engineer and arrange each month to print in duplicate colour progress photographs of the works taken by the Engineer. All photographs shall be subject to the Employers security precautions and shall not be used for promotional commercial purposes without written permission of the Employer. The Contractor shall provide suitable albums for the correct storage of the above photographs. The copy rights of all photographs rests with the Employer. | Item | 1 | 0 | 0 | 0
P65 | Preliminary and General Requirements Employer Facilities | Site Sign Boards | The Contractor shall allow for the provision erection and maintenance of two site sign board to display the project name the names of all Consultants associated with the Works and the Contractors name all as specified and to the approval of the Engineer.The sign board shall be complete with all necessary foundations supports framing painting and sign writing in Arabic and English denoting the title of the Project name of the Employer and names of Consultants and Contractor with their respective addresses and logos. The Contractor shall provide all details of the sign board to the Engineer for his approval before any work is put in hand and to enable erection to commence in the early stages of the Contract.The Contractor shall at the completion of the Contract remove the sign board supports and foundations. | Item | 1 | 0 | 0 | 0
G |  |  | SUM FOR PAGE7/13 |  |  |  | 0 | 0
P66 | Preliminary and General Requirements Employer Facilities | Site Offices Stores and Other Facilities | The Contractor shall provide erect maintain and remove on completion all necessary site offices stores messrooms sanitary accommodation and other facilities as may be required by the Contractor for his own and his SubContractors use together with all associated water drainage electrical lighting and power airconditioning telephoneradio facilities furniture equipment and attendance. | Item | 1 | 15750 | 15750 | 15750
P67 | Preliminary and General Requirements Employer Facilities | Site Offices Stores and Other Facilities | The position of all site offices stores etc. shall be to the approval of the Engineer and the Contractor must allow for all other facilities he may require to fulfil his contractual obligations additional to the area allocated to him. | Item | 1 | 7560 | 7560 | 7560
P68 | Preliminary and General Requirements Contractor Facilities | Accommodation for Workmen | The Contractor will not be allowed to accommodate workpeople on the site and arrangements must be made for such accommodation elsewhere at the Contractors expense and for transporting the workforce to the site. | Item | 1 | 15120 | 15120 | 15120
P69 | Preliminary and General Requirements Contractor Facilities | Communications | Provide a telephone for both his own and his SubContractors use including paying all charges in connection therewith. Radio telephone will only be permitted at the discretion of the Engineer if in his opinion it is not feasible to obtain a conventional telephone connection. | Item | 1 | 0 | 0 | 0
P70 | Preliminary and General Requirements | Temporary worksTemporary Fencing | Allow for all temporary fencing hoardings screens gantries etc. necessary for the execution of the Works. The Contractors particular attention is drawn to the neatness and approval of the hoardings by the Authorities and the Engineer. | Item | 1 | 1575 | 1575 | 1575
P71 | Preliminary and General Requirements | Temporary worksTemporary Roads | Provide maintain and alter as necessary temporary roads paths hardstandings pavement crossings and the like to and within the site. Remove and reinstate all ground and work disturbed when required. | Item | 1 | 0 | 0 | 0
P72 | Preliminary and General Requirements | Temporary worksWater for the Works | Provide all water required for the Works and provide and remove on completion all requisite temporary pipework pumps storage tanks etc. The Contractor must include for obtaining water from an independent source. | Item | 1 | 525 | 525 | 525
P73 | Preliminary and General Requirements | Temporary worksElectricity for the Works | Provide all electric light and power required for the Works including all temporary installations maintaining altering and adapting as necessary and remove all temporary installations on completion. | Item | 1 | 525 | 525 | 525
P74 | Preliminary and General Requirements | Temporary worksTraffic Diversions | The Contractor is to maintain at all times the flow of traffic on the existing roads and is to provide suitable signs lights and flag men at all times during the currency of the Contract all to the approval of the Authorities and the Engineer. | Item | 1 | 0 | 0 | 0
P75 | Preliminary and General Requirements | Temporary worksPumping and Dewatering | Provide here for all equipment and labour necessary to comply with the requirements for keeping the excavations and area of site free from surface underground running or standing water to the complete satisfaction of the Engineer to cover all such work wherever such work is not specifically measured in the relevant sections of the Bills of Quantities. | Item | 1 | 0 | 0 | 0
H |  |  | SUM FOR PAGE8/13 |  |  |  | 41055 | 41055
P76 | Preliminary and General Requirements | Temporary worksTemporary Lighting | Allow for installation maintenance and operation during hours of darkness a system of sufficient artificial lighting of roads paths access routes working platforms and areas where the works are in operation on site and that may be used or approached by any persons authorised to be on site and final removal from site on completion of the works. | Item | 1 | 0 | 0 | 0
P77 | Preliminary and General Requirements | Sundry ItemsTesting of Materials and the Works | Allow for all tests required by the Specification to be carried out including providing all necessary equipment materials and samples | Item | 1 | 0 | 0 | 0
P78 | Preliminary and General Requirements | Sundry ItemsSingle Sources of Supply | Where a choice of manufacturer or source of supply is allowed for any particular product of material the whole quantity required to complete the work must be of the same type manufacturer andor source. Changes will not be allowed without prior approval of the Engineer and at no cost to the Client. Written evidence of sources of supply must be produced when requested by Engineer. | Item | 1 | 0 | 0 | 0
P79 | Preliminary and General Requirements | Sundry ItemsSamples; generally | Allow for providing and submitting to the Engineer as he may require samples of all materials and goods which the Contractor proposes to incorporate in the Works. | Item | 1 | 0 | 0 | 0
P80 | Preliminary and General Requirements | Sundry ItemsSamples; generally | Allow for providing sample panels of materials workmanship and mockups as required by the Specification. | Item | 1 | 0 | 0 | 0
P81 | Preliminary and General Requirements | Sundry ItemsSamples Marble | The contractor shall submit three samples 300 x 300 mm of each marble specified layout of slabs and detailed shop drawings showing dimensions to the Engineer and obtain his approval prior to placing order. One of the samples should be the type of marble proposed to be incorporated in the works. | Item | 1 | 0 | 0 | 0
P82 | Preliminary and General Requirements | Sundry ItemsSamples Marble | The other two shall indicate the closest natural variation in colour and grain of the proposed marble. All marble slabs shall be delivered on site polished and ready for installation. | Item | 1 | 0 | 0 | 0
P83 | Preliminary and General Requirements | Sundry ItemsSource of Marble | Tenderers are required to name the proposed suppliers of marble to be incorporated in the works this information is to be submitted with the Tender. | Item | 1 | 0 | 0 | 0
P84 | Preliminary and General Requirements | Sundry ItemsProtection of the Works | Allow for protecting the Works from damage from any source including inclement weather. | Item | 1 | 0 | 0 | 0
P85 | Preliminary and General Requirements | Sundry ItemsDisposal of refuse | Keep the site free from debris arising from the Works during the construction period and leave the site free from debris and large loose stones on completion to the satisfaction of the Engineer. | Item | 1 | 0 | 0 | 0
P86 | Preliminary and General Requirements | Sundry ItemsSite Clearance | Clear the site of all scrub debris rubbish etc. in accordance with the Specification. | Item | 1 | 0 | 0 | 0
I |  |  | SUM FOR PAGE9/13 |  |  |  | 0 | 0
P87 | Preliminary and General Requirements | Sundry ItemsReports | Provide and maintain all Records Site Books and Daily Reports for inspection by the Engineer. | Item | 1 | 0 | 0 | 0
P88 | Preliminary and General Requirements | Sundry ItemsProgress Report | Provide Progress Reports at monthly intervals in a format as required by the Engineer. | Item | 1 | 0 | 0 | 0
P89 | Preliminary and General Requirements | Sundry ItemsCleaning the Works | Remove protective casings and coverings and thoroughly clean the Works at completion to the entire satisfaction of the Engineer. | Item | 1 | 0 | 0 | 0
P90 | Preliminary and General Requirements | Sundry ItemsTraffic Regulations | Allow for complying with all traffic regulations. | Item | 1 | 0 | 0 | 0
P91 | Preliminary and General Requirements | Sundry ItemsMaintenance of Public and Private Roads | Allow for making good any damage to public or private roads paths paved or landscaped areas. Contractors SubContractors and Suppliers vehicles must be kept in a clean condition and must not be allowed to soil public or private areas. | Item | 1 | 0 | 0 | 0
P92 | Preliminary and General Requirements | Sundry ItemsFire Fighting Facilities | Provide fire fighting facilities on site to the approval of the Authorities and the Engineer. | Item | 1 | 0 | 0 | 0
P93 | Preliminary and General Requirements | Sundry ItemsMaintenance of existing property access. | The Contractor is to maintain access to existing properties at all times with the use of steel plates ramps ducts etc. all to the approval of the Engineer. | Item | 1 | 0 | 0 | 0
P94 | Preliminary and General Requirements | Sundry ItemsDrying the Works | Allow for drying the works in accordance with the Specification and to the satisfaction of the Engineer. | Item | 1 | 0 | 0 | 0
P95 | Preliminary and General Requirements | Sundry ItemsControl of noise and pollution | Allow for keeping noise and pollution to an absolute minimum.Take all necessary precautions to reduce noise from plant by means of mufflers silencers screens and the like.Work entailing excessive noise is to be carried out during suitable hours as directed by the Engineer. | Item | 1 | 0 | 0 | 0
P96 | Preliminary and General Requirements | Sundry ItemsAntipollution Measures | The Contractor shall take precautions to minimize the pollution of and disturbance to lands roads and other places on and around the site. | Item | 1 | 0 | 0 | 0
J |  |  | SUM FOR PAGE10/13 |  |  |  | 0 | 0
P97 | Preliminary and General Requirements | Sundry ItemsStatutory Obligations | Allow for complying with all Statutory Obligations and for obtaining all permissions licences etc. and paying all fees as required by Statutory Authorities in connection with the carrying out of the Works.Allow for arranging inspection and the obtaining of all no objection certificates.The Contractor shall allow for complying with all building regulations. | Item | 1 | 0 | 0 | 0
P98 | Preliminary and General Requirements | Sundry ItemsPublic Authority for Electricity and Water PAEW and Oman Telecommunications Company OMANTEL Regulations and Requirements | Public Authority for Electricity and Water PAEW and OMANTEL regulations require certain works to be carried out by specialist Contractors approved by them and it is the responsibility of Tenderers to establish the extent of such work. Tenderers will be deemed to have allowed in their rates against the various items of work for complying with Public Authority for Electricity and Water and OMANTEL regulations and where necessary for employing Public Authority for Electricity and Water and OMANTEL approved Contractors for such specialist works. | Item | 1 | 1050 | 1050 | 1050
P99 | Preliminary and General Requirements | Sundry ItemsSite Survey and Grid of Levels | Before commencing excavation or site levelling operations the Contractor shall conduct a coordinated site survey witnessed by the Engineer related to a bench mark referred to in the Contract document and shall prepare a site plan showing a grid of levels at 5 m centres to the proposed site the Contractor shall provide the Engineer with one transparency and two copies of the site survey plan. | Item | 1 | 0 | 0 | 0
P100 | Preliminary and General Requirements | Sundry ItemsSite Survey and Grid of Levels | The Contractor shall conduct similar site survey after site levelling operations and external works have been completed and provide drawings as above. | Item | 1 | 0 | 0 | 0
P101 | Preliminary and General Requirements | Sundry ItemsCopies of Orders | Provide the Engineers Representative with a copy of all orders for the supply of such materials or goods required in connection with the Works as the Engineers Representative may specify. | Item | 1 | 0 | 0 | 0
P102 | Preliminary and General Requirements | Sundry ItemsWorking Drawings | Allow for preparing and submission to the Engineer of all working drawings and operation and maintenance instructions as detailed in the specification if these costs are not specifically measured elsewhere in the relevant sections of this document. | Item | 1 | 0 | 0 | 0
P103 | Preliminary and General Requirements | Sundry ItemsWorking Drawings | Upon completion of the works submit two sets of diskettes Autocad R12 later two transparencies and four copies of all drawings duly marked AsBuilt clearly defining all locations depths shapes and dimensions of all permanent works executed. | Item | 1 | 0 | 0 | 0
K |  |  | SUM FOR PAGE11/13 |  |  |  | 1050 | 1050
P104 | Preliminary and General Requirements | Sundry ItemsTraining of Employers Personnel | During the execution of the Works the Contractor shall provide such assistance as may be necessary for the instruction and training of personnel appointed by the Employer. | Item | 1 | 0 | 0 | 0
P105 | Preliminary and General Requirements | Sundry ItemsTraining of Employers Personnel | The Contractor shall provide all necessary instruction material for this purpose such as manuals booklets pamphlets drawings sketches models pictures photoscolour slides films etc. This instruction material shall become the property of the Employer. | Item | 1 | 0 | 0 | 0
P106 | Preliminary and General Requirements | Sundry ItemsDirect Contractors | The Tenderers attention is drawn to the fact that the Employer may appoint other Contractors to carry out certain items of Specialist Works in accordance with Clause 31 of the Conditions of Contract. | Item | 1 | 0 | 0 | 0
P107 | Preliminary and General Requirements Performance Bond Advance Payment Bond and Insurance Certificate | Performance Bond | The Contractor will be required to provide Performance Bond all in accordance with Clause 4.2 of the Conditions of Contract. | Item | 1 | 0 | 0 | 0
P108 | Preliminary and General Requirements Performance Bond Advance Payment Bond and Insurance Certificate | Insurance | The Contractor will be required to provide all Insurances in accordance with the Conditions of Contract. | Item | 1 | 0 | 0 | 0
P109 | Preliminary and General Requirements Performance Bond Advance Payment Bond and Insurance Certificate | Insurance Declaration | On signing the Contract the Contractor shall obtain from his Insurance Company and lodge with the Engineer a declaration that the insurance provided is strictly in accordance with all relevant Clause in the Conditions of Contract. This shall also include insurance against damage of any kind to existing buildings which may arise as a result of the building operations. | Item | 1 | 0 | 0 | 0
P110 | Preliminary and General Requirements Performance Bond Advance Payment Bond and Insurance Certificate | Advance Payment Bond | The Contractor will be required to provide an Advance Payment Bond all in accordance with Clause 14.2 of Conditions of Contract. | Item | 1 | 0 | 0 | 0
L |  |  | SUM FOR PAGE12/13 |  |  |  | 0 | 0
P111 |  | Refer Provisional SumTemporary Houses | The Contractor will be required to provide temporary houses Caravan for the resident while working in the Construction and also during Maintenance Works and refix inside houses after work finish as outside extra rooms for them. Every caravan will be around 65m2 and will include and not be limited to 2 rooms a hall a kitchen and two toilets The structure to use steel structure painted with anticorrosion paint with isolated walls and roof aluminum sandwich panels 50 mm thickness from 2 sheets 0.7 mm thickness and foam of 45 kgm3 density internal ceramic floor and walls for toiles and kitchen to be ceramic all sanitary fixture for toilet and kitchen sink and cabinet sewage electrical and water connection to be done in the temporary place and will be finally done again after move to internal new and maintained houses foundation for caravan and 3 steps omani marble in final place fixing also 4 AC are included design of caravan to be done by the contractor approved by clientconsultant beforedelivery the caravans will be under project defects notification period for one year. | item | 1 | 124800 | 124800 |  | 1 | 124800
P112 | Preliminary and General Requirements CCTV Control. | CCTV | The Contractor will be required to provide CCTV to monitor and maintain the work activity at site while working in the Construction Works also during Maintenance Works. | Item | 1 | 0 | 0 | 0
P113 | Preliminary and General Requirements Temporary Facilities. | External Temporary Building | The Contractor should follow maintenance works for the External Building for the Existing 32 Housing while working in the Construction Works also during Maintenance Works. | Item | 1 | 0 | 0 | 0
P114 | Preliminary and General Requirements EngineerEmployer Facilities | Facilities for Engineers Employers | The Contractor shall provide erect maintain and remove on completion all necessary Engineers accommodation Employers accommodation common kitchen with dining hall including food for all time to the EngineersEmployers sanitary accommodation and other facilities all by the Contractor expenses and link together with all associated water drainage electrical lighting and power airconditioning telephone mobile phones 4nos with recharge cards 30rial new furniture washing equipment and maintenance the same until the Completion of Project as per details in prim documents. | Item | 1 | 25200 | 25200 | 25200
P115 | Preliminary and General Requirements Contractors Administration Arrangements | Site Transportation for Engineers Employers | Provide necessary 4x4 vehicles 2nos in excellent condition for consultantclient staff transportation and pickup vehicle 2nos for site transport etc. with all consumables fuel etc. as described for small plant and tools for regular maintenance etc as per details in prim documents. | Item | 1 | 8700 | 8700 | 8700
M |  |  | SUM FOR PAGE13/13 |  |  |  | 158700 | 33900
TOTAL PRELIMINARIES | [6 empty] | 227580 | 102780 |  | 124800 | 0

## BILL NO 2. (DAY WORK)
BILL NO 2. (DAY WORK)
Item Code | Item Name | Item Details | Additional Information | UOM | Quantity | Unit Price | Total Price In Figure | CLAIMABLE AMOUNT | Omission | Addition
D1 | Daywork Schedule | Day Work | The Contractor may be required to execute certain works on the basis of day works. | Item | 1 | 0 | 0
D2 | Daywork Schedule | Day Work | The Contractor shall keep an accurate record of time spent and materials and plant and used on each separate instruction given. Day work sheets are to be numbered and are to describe fully the instructions to which they refer and they are to be fully summarized fully priced and submitted to the Engineer for signature. The submission of such day work sheets does not necessarily mean that the work will be valued under Clause 13.5 of the Conditions of Contract or that any payment is in fact due. | Item | 1 | 0 | 0
D3 | Daywork Schedule | Labour 1. The Tenderer shall give the rates herein required for labourers and craftsmen against each item stated. 2.The rates are to be comprehensive and include | Wages and all costs payments and charges including pensions annual and public holidays traveling time expenses fares and transport guaranteed time nonproductive time and other expenses in connection with overtime incentive and bonus payments dirty money and danger money and other disbursements arising from employment of labour including redundancy payment reduced working hours during Ramadhan all associated costs if labourers imported form other countries and workmens compensation insurance gratuity and all terminal benefits as per Oman labour Laws. | Item | 1 | 0 | 0
D4 | Daywork Schedule | Labour 1. The Tenderer shall give the rates herein required for labourers and craftsmen against each item stated. 2.The rates are to be comprehensive and include | Charges incurred in respect of site and office supervision including foreman�s time and extra emoluments paid to foreman and leading craftsmen and gangers. | Item | 1 | 0 | 0
D5 | Daywork Schedule | Labour 1. The Tenderer shall give the rates herein required for labourers and craftsmen against each item stated. 2.The rates are to be comprehensive and include | Site and Head Office overhead charges such as rent rates insurances electricity fuel water printing stationery postage telephone charges motor car expenses renewals maintenance and depreciation of premises machinery plant and the like. | Item | 1 | 0 | 0
D6 | Daywork Schedule | Labour 1. The Tenderer shall give the rates herein required for labourers and craftsmen against each item stated. 2.The rates are to be comprehensive and include | Profit | Item | 1 | 0 | 0
D7 | Daywork Schedule | Materials | Materials used in day works to be charged at invoice cost. All discounts are to be allowed to the Ministry of Health. Invoices are to be made available to the Engineer at the time the relevant day work sheets are submitted. | Item | 1 | 0 | 0
D8 | Daywork Schedule | Materials | The Contractor is to allow for additional percentage he requires to be added to the invoice cost of materials to cover for ordering taking delivery paying all insurances in transit landing charges dues custom duties Municipality tax and all other charges loading and transporting to the site taking into store storing as may be required and all other charges and profit. | Item | 1 | 0 | 0
D9 | Daywork Schedule | Plant 1. The Contractor shall give here the rates he requires for plant and machinery 2. The rates are to be comprehensive and include | Mobilization and demobilization costs | Item | 1 | 0 | 0
D10 | Daywork Schedule | Plant 1. The Contractor shall give here the rates he requires for plant and machinery 2. The rates are to be comprehensive and include | Fuel oil lubricants and all other consumable stores. | Item | 1 | 0 | 0
D11 | Daywork Schedule | Plant 1. The Contractor shall give here the rates he requires for plant and machinery 2. The rates are to be comprehensive and include | Servicing repairs and replacements. | Item | 1 | 0 | 0
D12 | Daywork Schedule | Plant 1. The Contractor shall give here the rates he requires for plant and machinery 2. The rates are to be comprehensive and include | Site and Head Office overhead charges as previously defined. | Item | 1 | 0 | 0
D13 | Daywork Schedule | Plant 1. The Contractor shall give here the rates he requires for plant and machinery 2. The rates are to be comprehensive and include | Profit | Item | 1 | 0 | 0
D14 | Daywork Schedule | Plant | The rates are to include for haulage to and from site and all other charges relating to plant and shall be exclusive of attendants and drivers who shall be charged at labour rates as set out above. | Item | 1 | 0 | 0
D15 | Daywork Schedule | Plant | If the Contractor is unable to price the particular type of plant listed he should price for the nearest equivalent item available to him and state what has been included in his tender. | Item | 1 | 0 | 0
D16 | Daywork Schedule | Labour | Labourers | Hr | 200 | 0 | 0
D17 | Daywork Schedule | Labour | Gangers | Hr | 25 | 0 | 0
D18 | Daywork Schedule | Labour | Steelfixers | Hr | 50 | 0 | 0
D19 | Daywork Schedule | Labour | Carpenters and Joiners | Hr | 50 | 0 | 0
D20 | Daywork Schedule | Labour | Tile Layers | Hr | 50 | 0 | 0
D21 | Daywork Schedule | Labour | Masons | Hr | 50 | 10.6 | 530 |  | 530
D22 | Daywork Schedule | Labour | Painters | Hr | 50 | 10.5 | 525 |  | 525
D23 | Daywork Schedule | Labour | Scaffolders | Hr | 50 | 10.5 | 525 |  | 525
D24 | Daywork Schedule | Labour | Drainlayers | Hr | 50 | 10.6 | 530 |  | 530
D25 | Daywork Schedule | Labour | Plumbers | Hr | 50 | 10.5 | 525 |  | 525
D26 | Daywork Schedule | Labour | ElectriciansA.C. Mechanics | Hr | 50 | 10.5 | 525 |  | 525
D27 | Daywork Schedule | Labour | Welders | Hr | 50 | 10.5 | 525 |  | 525
D28 | Daywork Schedule | Labour | FabricatorsFitters | Hr | 50 | 10.5 | 525 |  | 525
D29 | Daywork Schedule | Labour | Plant and Machinery Operators and Drivers | Hr | 80 | 10.5 | 840 |  | 840
D30 | Daywork Schedule | Materials | Include the Provisional Sum of Rials Omani Ten Thousand RO. 10000.000 for the cost of Local Materials expended on Dayworks. These costs shall be charged at the nett price paid by the Contractor for the materials exsupplier as substantiated by the suppliers invoices. | Item | 1 | 0 | 0
D31 | Daywork Schedule | Materials | Include the Provisional Sum of Rials Omani Ten Thousand R.O. 10000.000 for the cost of Imported Materials expended on daywork. These costs shall be charged at the nett price paid by the Contractor for the materials delivered C.I.F. Oman as substantiated by the suppliers invoices. | Item | 1 | 0 | 0
D32 | Daywork Schedule | Materials | Contractors percentage on net cost of material 5 percent | Item | 1 | 0 | 0
D33 | Daywork Schedule | Plant | Portable compressors Complete with hoses Delivery of free air Up to 4.6 Cumper minute | Hr | 50 | 52.5 | 2625 |  | 2625
D34 | Daywork Schedule | Plant | Pneumatic hammer including steels | Hr | 20 | 31.5 | 630 |  | 630
D35 | Daywork Schedule | Plant | Concrete Mixers | Hr | 50 | 21 | 1050 |  | 1050
D36 | Daywork Schedule | Plant | Dumper up to 0.5 Cum bucket capacity | Hr | 30 | 21 | 630 |  | 630
D37 | Daywork Schedule | Plant | Concrete vibrator poker 50mm diameter | Hr | 30 | 10.5 | 315 |  | 315
D38 | Daywork Schedule | Plant | Excavators up to 0.5 Cum bucket capacity | Hr | 30 | 10.5 | 315 |  | 315
D39 | Daywork Schedule | Plant | Generator sets 50 KVA | Hr | 50 | 31.5 | 1575 |  | 1575
D40 | Daywork Schedule | Plant | Tipper truck 10 tonne | Hr | 40 | 52.5 | 2100 |  | 2100
D41 | Daywork Schedule | Plant | Van or utility vehicle | Hr | 40 | 21 | 840 |  | 840
D42 | Daywork Schedule | Plant | Three tonne pickup | Hr | 40 | 31.5 | 1260 |  | 1260
D43 | Daywork Schedule | Plant | Water tanker 2000 gallon | Hr | 20 | 31.5 | 630 |  | 630
D44 | Daywork Schedule | Plant | Excavator hydraulic full circle slew 1m3 | Hr | 20 | 42 | 840 |  | 840
D45 | Daywork Schedule | Plant | Mobile Crane 10 tonne | Hr | 25 | 52.5 | 1312.5 |  | 1312.5
D46 | Daywork Schedule | Plant | Bulldozer 430hp | Hr | 25 | 42 | 1050 |  | 1050
D47 | Daywork Schedule | Plant | Loader1.5m3 | Hr | 25 | 52.5 | 1312.5 |  | 1312.5
D48 | Daywork Schedule | Plant | Grader 200 hp | Hr | 25 | 52.5 | 1312.5 |  | 1312.5
D49 | Daywork Schedule | Plant | Roller 4 tonne | Hr | 25 | 42 | 1050 |  | 1050
D50 | Daywork Schedule | Plant | Welding set 300 A including electrodes | Hr | 25 | 31.5 | 787.5 |  | 787.5
D51 | Daywork Schedule | Plant | Oxy acetylene cutting set including electrodes | Hr | 25 | 31.5 | 787.5 |  | 787.5
D52 | Daywork Schedule | Plant | 2 inch Water pump 5 hp | Hr | 30 | 26.25 | 787.5 |  | 787.5
D53 | Daywork Schedule | Plant | 4 inch Water pump 10 hp | Hr | 30 | 36.75 | 1102.5 |  | 1102.5
D54 | Daywork Schedule | Employee Staff | Project Manager | Hr | 200 | 42 | 8400 |  | 8400
D55 | Daywork Schedule | Employee Staff | Resident Project Engineer | Hr | 200 | 26.25 | 5250 |  | 5250
D56 | Daywork Schedule | Employee Staff | Resident Civil Material Engineer | Hr | 200 | 26.25 | 5250 |  | 5250
D57 | Daywork Schedule | Employee Staff | Resident Electrical Engineer | Hr | 200 | 26.25 | 5250 |  | 5250
D58 | Daywork Schedule | Employee Staff | Resident Mechanical Engineer | Hr | 200 | 26.25 | 5250 |  | 5250
D59 | Daywork Schedule | Employee Staff | Resident Architecture Engineer Omani | Hr | 200 | 26.25 | 5250 |  | 5250
D60 | Daywork Schedule | Employee Staff | Resident Quantity Surveyor | Hr | 200 | 26.25 | 5250 |  | 5250
D61 | Daywork Schedule | Employee Staff | Resident Draftsman Omani | Hr | 200 | 26.25 | 5250 |  | 5250
D62 | Daywork Schedule | Employee Staff | Resident QA QC | Hr | 200 | 26.25 | 5250 |  | 5250
D63 | Daywork Schedule | Employee Staff | Resident HSE Omani | Hr | 200 | 26.25 | 5250 |  | 5250
D64 | Daywork Schedule | Employee Staff | Cook | Hr | 200 | 15.75 | 3150 |  | 3150
D65 | Daywork Schedule | Employee Staff | Assistant to Cook | Hr | 200 | 10.5 | 2100 |  | 2100
P66 | Preliminary and General Requirements Employer Facilities | Site Offices Stores and Other Facilities | The Contractor shall provide erect maintain and remove on completion all necessary site offices stores messrooms sanitary accommodation and other facilities as may be required by the Contractor for his own and his SubContractors use together with all associated water drainage electrical lighting and power airconditioning telephoneradio facilities furniture equipment and attendance. | Item | 1 | 0 | 0
P67 | Preliminary and General Requirements Employer Facilities | Site Offices Stores and Other Facilities | The position of all site offices stores etc. shall be to the approval of the Engineer and the Contractor must allow for all other facilities he may require to fulfil his contractual obligations additional to the area allocated to him. | Item | 1 | 0 | 0
P68 | Preliminary and General Requirements Contractor Facilities | Accommodation for Workmen | The Contractor will not be allowed to accommodate workpeople on the site and arrangements must be made for such accommodation elsewhere at the Contractors expense and for transporting the workforce to the site. | Item | 1 | 0 | 0
P69 | Preliminary and General Requirements Contractor Facilities | Communications | Provide a telephone for both his own and his SubContractors use including paying all charges in connection therewith. Radio telephone will only be permitted at the discretion of the Engineer if in his opinion it is not feasible to obtain a conventional telephone connection. | Item | 1 | 0 | 0
P70 | Preliminary and General Requirements | Temporary worksTemporary Fencing | Allow for all temporary fencing hoardings screens gantries etc. necessary for the execution of the Works. The Contractors particular attention is drawn to the neatness and approval of the hoardings by the Authorities and the Engineer. | Item | 1 | 0 | 0
P71 | Preliminary and General Requirements | Temporary worksTemporary Roads | Provide maintain and alter as necessary temporary roads paths hardstandings pavement crossings and the like to and within the site. Remove and reinstate all ground and work disturbed when required. | Item | 1 | 0 | 0
P72 | Preliminary and General Requirements | Temporary worksWater for the Works | Provide all water required for the Works and provide and remove on completion all requisite temporary pipework pumps storage tanks etc. The Contractor must include for obtaining water from an independent source. | Item | 1 | 0 | 0
P73 | Preliminary and General Requirements | Temporary worksElectricity for the Works | Provide all electric light and power required for the Works including all temporary installations maintaining altering and adapting as necessary and remove all temporary installations on completion. | Item | 1 | 0 | 0
P74 | Preliminary and General Requirements | Temporary worksTraffic Diversions | The Contractor is to maintain at all times the flow of traffic on the existing roads and is to provide suitable signs lights and flag men at all times during the currency of the Contract all to the approval of the Authorities and the Engineer. | Item | 1 | 0 | 0
P75 | Preliminary and General Requirements | Temporary worksPumping and Dewatering | Provide here for all equipment and labour necessary to comply with the requirements for keeping the excavations and area of site free from surface underground running or standing water to the complete satisfaction of the Engineer to cover all such work wherever such work is not specifically measured in the relevant sections of the Bills of Quantities. | Item | 1 | 0 | 0
P76 | Preliminary and General Requirements | Temporary worksTemporary Lighting | Allow for installation maintenance and operation during hours of darkness a system of sufficient artificial lighting of roads paths access routes working platforms and areas where the works are in operation on site and that may be used or approached by any persons authorised to be on site and final removal from site on completion of the works. | Item | 1 | 0 | 0
P77 | Preliminary and General Requirements | Sundry ItemsTesting of Materials and the Works | Allow for all tests required by the Specification to be carried out including providing all necessary equipment materials and samples | Item | 1 | 0 | 0
P78 | Preliminary and General Requirements | Sundry ItemsSingle Sources of Supply | Where a choice of manufacturer or source of supply is allowed for any particular product of material the whole quantity required to complete the work must be of the same type manufacturer andor source. Changes will not be allowed without prior approval of the Engineer and at no cost to the Client. Written evidence of sources of supply must be produced when requested by Engineer. | Item | 1 | 0 | 0
P79 | Preliminary and General Requirements | Sundry ItemsSamples; generally | Allow for providing and submitting to the Engineer as he may require samples of all materials and goods which the Contractor proposes to incorporate in the Works. | Item | 1 | 0 | 0
P80 | Preliminary and General Requirements | Sundry ItemsSamples; generally | Allow for providing sample panels of materials workmanship and mockups as required by the Specification. | Item | 1 | 0 | 0
P81 | Preliminary and General Requirements | Sundry ItemsSamples Marble | The contractor shall submit three samples 300 x 300 mm of each marble specified layout of slabs and detailed shop drawings showing dimensions to the Engineer and obtain his approval prior to placing order. One of the samples should be the type of marble proposed to be incorporated in the works. | Item | 1 | 0 | 0
P82 | Preliminary and General Requirements | Sundry ItemsSamples Marble | The other two shall indicate the closest natural variation in colour and grain of the proposed marble. All marble slabs shall be delivered on site polished and ready for installation. | Item | 1 | 0 | 0
P83 | Preliminary and General Requirements | Sundry ItemsSource of Marble | Tenderers are required to name the proposed suppliers of marble to be incorporated in the works this information is to be submitted with the Tender. | Item | 1 | 0 | 0
P84 | Preliminary and General Requirements | Sundry ItemsProtection of the Works | Allow for protecting the Works from damage from any source including inclement weather. | Item | 1 | 0 | 0
P85 | Preliminary and General Requirements | Sundry ItemsDisposal of refuse | Keep the site free from debris arising from the Works during the construction period and leave the site free from debris and large loose stones on completion to the satisfaction of the Engineer. | Item | 1 | 0 | 0
P86 | Preliminary and General Requirements | Sundry ItemsSite Clearance | Clear the site of all scrub debris rubbish etc. in accordance with the Specification. | Item | 1 | 0 | 0
P87 | Preliminary and General Requirements | Sundry ItemsReports | Provide and maintain all Records Site Books and Daily Reports for inspection by the Engineer. | Item | 1 | 0 | 0
P88 | Preliminary and General Requirements | Sundry ItemsProgress Report | Provide Progress Reports at monthly intervals in a format as required by the Engineer. | Item | 1 | 0 | 0
P89 | Preliminary and General Requirements | Sundry ItemsCleaning the Works | Remove protective casings and coverings and thoroughly clean the Works at completion to the entire satisfaction of the Engineer. | Item | 1 | 0 | 0
P90 | Preliminary and General Requirements | Sundry ItemsTraffic Regulations | Allow for complying with all traffic regulations. | Item | 1 | 0 | 0
P91 | Preliminary and General Requirements | Sundry ItemsMaintenance of Public and Private Roads | Allow for making good any damage to public or private roads paths paved or landscaped areas. Contractors SubContractors and Suppliers vehicles must be kept in a clean condition and must not be allowed to soil public or private areas. | Item | 1 | 0 | 0
P92 | Preliminary and General Requirements | Sundry ItemsFire Fighting Facilities | Provide fire fighting facilities on site to the approval of the Authorities and the Engineer. | Item | 1 | 0 | 0
P93 | Preliminary and General Requirements | Sundry ItemsMaintenance of existing property access. | The Contractor is to maintain access to existing properties at all times with the use of steel plates ramps ducts etc. all to the approval of the Engineer. | Item | 1 | 0 | 0
P94 | Preliminary and General Requirements | Sundry ItemsDrying the Works | Allow for drying the works in accordance with the Specification and to the satisfaction of the Engineer. | Item | 1 | 0 | 0
P95 | Preliminary and General Requirements | Sundry ItemsControl of noise and pollution | Allow for keeping noise and pollution to an absolute minimum.Take all necessary precautions to reduce noise from plant by means of mufflers silencers screens and the like.Work entailing excessive noise is to be carried out during suitable hours as directed by the Engineer. | Item | 1 | 0 | 0
P96 | Preliminary and General Requirements | Sundry ItemsAntipollution Measures | The Contractor shall take precautions to minimize the pollution of and disturbance to lands roads and other places on and around the site. | Item | 1 | 0 | 0
P97 | Preliminary and General Requirements | Sundry ItemsStatutory Obligations | Allow for complying with all Statutory Obligations and for obtaining all permissions licences etc. and paying all fees as required by Statutory Authorities in connection with the carrying out of the Works.Allow for arranging inspection and the obtaining of all no objection certificates.The Contractor shall allow for complying with all building regulations. | Item | 1 | 0 | 0
P98 | Preliminary and General Requirements | Sundry ItemsPublic Authority for Electricity and Water PAEW and Oman Telecommunications Company OMANTEL Regulations and Requirements | Public Authority for Electricity and Water PAEW and OMANTEL regulations require certain works to be carried out by specialist Contractors approved by them and it is the responsibility of Tenderers to establish the extent of such work. Tenderers will be deemed to have allowed in their rates against the various items of work for complying with Public Authority for Electricity and Water and OMANTEL regulations and where necessary for employing Public Authority for Electricity and Water and OMANTEL approved Contractors for such specialist works. | Item | 1 | 0 | 0
P99 | Preliminary and General Requirements | Sundry ItemsSite Survey and Grid of Levels | Before commencing excavation or site levelling operations the Contractor shall conduct a coordinated site survey witnessed by the Engineer related to a bench mark referred to in the Contract document and shall prepare a site plan showing a grid of levels at 5 m centres to the proposed site the Contractor shall provide the Engineer with one transparency and two copies of the site survey plan. | Item | 1 | 0 | 0
P100 | Preliminary and General Requirements | Sundry ItemsSite Survey and Grid of Levels | The Contractor shall conduct similar site survey after site levelling operations and external works have been completed and provide drawings as above. | Item | 1 | 0 | 0
P101 | Preliminary and General Requirements | Sundry ItemsCopies of Orders | Provide the Engineers Representative with a copy of all orders for the supply of such materials or goods required in connection with the Works as the Engineers Representative may specify. | Item | 1 | 0 | 0
P102 | Preliminary and General Requirements | Sundry ItemsWorking Drawings | Allow for preparing and submission to the Engineer of all working drawings and operation and maintenance instructions as detailed in the specification if these costs are not specifically measured elsewhere in the relevant sections of this document. | Item | 1 | 0 | 0
P103 | Preliminary and General Requirements | Sundry ItemsWorking Drawings | Upon completion of the works submit two sets of diskettes Autocad R12 later two transparencies and four copies of all drawings duly marked AsBuilt clearly defining all locations depths shapes and dimensions of all permanent works executed. | Item | 1 | 0 | 0
P104 | Preliminary and General Requirements | Sundry ItemsTraining of Employers Personnel | During the execution of the Works the Contractor shall provide such assistance as may be necessary for the instruction and training of personnel appointed by the Employer. | Item | 1 | 0 | 0
P105 | Preliminary and General Requirements | Sundry ItemsTraining of Employers Personnel | The Contractor shall provide all necessary instruction material for this purpose such as manuals booklets pamphlets drawings sketches models pictures photoscolour slides films etc. This instruction material shall become the property of the Employer. | Item | 1 | 0 | 0
P106 | Preliminary and General Requirements | Sundry ItemsDirect Contractors | The Tenderers attention is drawn to the fact that the Employer may appoint other Contractors to carry out certain items of Specialist Works in accordance with Clause 31 of the Conditions of Contract. | Item | 1 | 0 | 0
P107 | Preliminary and General Requirements Performance Bond Advance Payment Bond and Insurance Certificate | Performance Bond | The Contractor will be required to provide Performance Bond all in accordance with Clause 4.2 of the Conditions of Contract. | Item | 1 | 0 | 0
P108 | Preliminary and General Requirements Performance Bond Advance Payment Bond and Insurance Certificate | Insurance | The Contractor will be required to provide all Insurances in accordance with the Conditions of Contract. | Item | 1 | 0 | 0
P109 | Preliminary and General Requirements Performance Bond Advance Payment Bond and Insurance Certificate | Insurance Declaration | On signing the Contract the Contractor shall obtain from his Insurance Company and lodge with the Engineer a declaration that the insurance provided is strictly in accordance with all relevant Clause in the Conditions of Contract. This shall also include insurance against damage of any kind to existing buildings which may arise as a result of the building operations. | Item | 1 | 0 | 0
P110 | Preliminary and General Requirements Performance Bond Advance Payment Bond and Insurance Certificate | Advance Payment Bond | The Contractor will be required to provide an Advance Payment Bond all in accordance with Clause 14.2 of Conditions of Contract. | Item | 1 | 0 | 0
P111 | Preliminary and General Requirements Temporary Facilities. | Refer Provisional SumTemporary Houses | The Contractor will be required to provide temporary houses Caravan for the resident while working in the Construction and also during Maintenance Works and refix inside houses after work finish as outside extra rooms for them. Every caravan will be around 65m2 and will include and not be limited to 2 rooms a hall a kitchen and two toilets The structure to use steel structure painted with anticorrosion paint with isolated walls and roof aluminum sandwich panels 50 mm thickness from 2 sheets 0.7 mm thickness and foam of 45 kgm3 density internal ceramic floor and walls for toiles and kitchen to be ceramic all sanitary fixture for toilet and kitchen sink and cabinet sewage electrical and water connection to be done in the temporary place and will be finally done again after move to internal new and maintained houses foundation for caravan and 3 steps omani marble in final place fixing also 4 AC are included design of caravan to be done by the contractor approved by clientconsultant beforedelivery the caravans will be under project defects notification period for one year. | item | 0 | 0 | 0
P112 | Preliminary and General Requirements CCTV Control. | CCTV | The Contractor will be required to provide CCTV to monitor and maintain the work activity at site while working in the Construction Works also during Maintenance Works. | Item | 1 | 0 | 0
P113 | Preliminary and General Requirements Temporary Facilities. | External Temporary Building | The Contractor should follow maintenance works for the External Building for the Existing 32 Housing while working in the Construction Works also during Maintenance Works. | Item | 1 | 0 | 0
P114 | Preliminary and General Requirements EngineerEmployer Facilities | Facilities for EngineersEmployers | The Contractor shall provide erect maintain and remove on completion all necessary Engineers accommodation Employers accommodation common kitchen with dining hall including food for all time to the EngineersEmployers sanitary accommodation and other facilities all by the Contractor expenses and link together with all associated water drainage electrical lighting and power airconditioning telephone mobile phones 4nos with recharge cards 30rial new furniture washing equipment and maintenance the same until the Completion of Project as per details in prim documents. | Item | 1 | 0 | 0
P115 | Preliminary and General Requirements Contractors Administration Arrangements | Site Transportation for EngineersEmployers | Provide necessary 4x4 vehicles 2nos in excellent condition for consultantclient staff transportation and pickup vehicle 2nos for site transport etc. with all consumables fuel etc. as described for small plant and tools for regular maintenance etc as per details in prim documents. | Item | 1 | 0 | 0
TOTAL DAYWORKS | [5 empty] | 88252.5 |  | 0 | 88262.5 | 0

## BILL NO 3. (PROVISIONAL SUM)
BILL NO. 3 (PROVISIONAL SUM)
Item Code | Item Name | Item Details | Additional Information | UOM | Quantity | Unit Price | Total Price In Figure | REVISED BOQ AMOUNT | Omission | Addition
PV1 | Allow for the provisional sums to be expended as directed by the Engineer or deducted in whole or in part if not required - Soft landscaping and Irrigation System | 1 | Item | Item | 1 | 20000 | 20000 |  | 20000
PV2 | Allow for the provisional sums to be expended as directed by the Engineer or deducted in whole or in part if not - 2000 KVA Sub Station | 1 | Item | Item | 1 | 40000 | 40000 |  | 40000
PV3 | Allow for the provisional sums to be expended as directed by the Engineer or deducted in whole or in part if not - 11 KV extension & tapping | 1 | Item | Item | 1 | 60000 | 60000 |  | 60000
PV4 | Allow for the provisional sums to be expended as directed by the Engineer or deducted in whole or in part if not - Water and Power Main Connection from the Authority for Electricity line and Water line. | 1 | Item | Item | 1 | 40000 | 40000 |  | 40000
PV5 | Allow for the provisional sums to be expended as directed by the Engineer or deducted in whole or in part if not - Relocation of Halaniyat Resident to the Temporary Houses in Salalah, Two Bed Room, Two Toilet, One Kitchen for 28 months. | 1 | Item | Item | 1 | --------------- | Covered in Preliminaries P111 |  | -------------------
PV6 | Allow for the provisional sums to be expended as directed by the Engineer or deducted in whole or in part if not - Add for overhead and profit (7.5 percent) | 1 | Item | Item | 1 | 40000 | 40000 |  | 40000
TOTAL PROVISIONAL SUM | [6 empty] | 200000 | ---------------- | 200000 | 0

## BILL NO4. (20 NHU)
BILL NO 4. (20 NEW HOUSING UNITS) | [7 empty] | REVISED AMOUNT |  | OMISSION |  | ADDITION
Item Code | Item Name | Item Details | Additional Information | UOM | BOQ-Quantity | Unit Price | Total Price In Figure | Actual-Quantity | Actual Amount | QUANTITIES | AMOUNT | QUANTITIES | AMOUNT | APPENDIX
C1 | General Works | Demolishing and Clearing the Construction Area | Demolishing the complete building and removing the debris from the Construction Site as per EngineerEmployer Instruction including cart away from the Project Site up to OGL | NO | 20 | 2520 | 50400 | 20 | 50400
C2 | Substructure Works | Site Clearance | This shall include removing vegetation undergrowth bushes hedges trees other temporary buildings structures or the like all complete to clean the full plot. | NO | 20 | 52.5 | 1050 | 20 | 1050
C3 | Substructure Works | Earth work and Excavation | Bulk Excavation to receive foundations in any kind of soil including hard soil and rock earth sport underground surface or running water from whatever source if any for the new foundation building area including removal of old buildings foundations cleaning the site and removing all debris not suitable for backfilling from the project area to the damp yard contractor to prepare all areas to receive new foundation safely as per drawings and soil report. | M3 | 15000 | 0.77 | 11550 | 12726.72 | 9799.5744 | 2273.28 | 1750.4256
C4 | Substructure Works | Filling | Approved imported granular fill material compacted in layers in making up levels under floors | M3 | 4000 | 0.525 | 2100 |  |  | 4000 | 2100
C5 | Substructure Works | Filling | Approved imported fill material compacted in layers to raise the levels | M3 | 15000 | 0.525 | 7875 | 5561.35 | 2919.7088 | 9438.65 | 4955.2913
C6 | Substructure Works | Filling | Approved selected excavated material backfilled into excavations | M3 | 6000 | 0.525 | 3150 | 6000 | 3150 | 0 | 0
C7 | Substructure Works | Filling | 200 mm thick well compacted hardcore filling under floors | M3 | 1040 | 0.455 | 473.2 |  | 0 | 1040 | 473.2
C8 | Substructure Works | Anti termite treatment | Anti termite treatment to surfaces of ground or filling applied strictly in accordance with the manufacturers printed instructions including digging trenches backfilling etc. as required by the manufacturer and the provision of guarantee valid for 10 years | M2 | 6200 | 1.524 | 9448.8 | 5934.35 | 9043.9494 | 265.65 | 404.8506
A | SUM FOR PAGE-1/68 | [5 empty] | 86047 |  | 76363.2326 | 0 | 9683.7675
C9 | Substructure Works | Poured Concrete Plain insitu concrete poured Ordinary Portland Cement OPC Concrete Grade C15 all in accordance with Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Blinding upto 100 mm thickness | M3 | 300 | 63 | 18900 | 284.36 | 17914.68 | 15.64 | 985.32
B | SUM FOR PAGE-2/68 | [5 empty] | 18900 |  | 17914.68 | 0 | 985.32
C10 | Substructure Works | Reinforced insitu concrete poured vibrated Sulphate Resistent Cement OPC Concrete Grade C30 all in accordance with Drawings and Specifications and including Reinforcement High yield strength deformed bars conforming to BS 4449 Grade 460 including cutting bending binding binding wire cover blocks tests and all necessary fixing accessories all in accordance with the Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Footings | M3 | 800 | 94.5 | 75600 | 734.32 | 69393.24 | 65.68 | 6206.76
C | SUM FOR PAGE-3/68 | [5 empty] | 75600 |  | 69393.24 | 0 | 6206.76
C11 | Substructure Works | Reinforced insitu concrete poured vibrated Sulphate Resistent Cement OPC Concrete Grade C30 all in accordance with Drawings and Specifications and including Reinforcement High yield strength deformed bars conforming to BS 4449 Grade 460 including cutting bending binding binding wire cover blocks tests and all necessary fixing accessories all in accordance with the Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Plinth beams | M3 | 600 | 94.5 | 56700 | 444.6 | 42014.7 | 155.4 | 14685.3
D | SUM FOR PAGE-4/68 | [5 empty] | 56700 |  | 42014.7 | 0 | 14685.3
C12 | Substructure Works | Reinforced insitu concrete poured vibrated Sulphate Resistent Cement OPC Concrete Grade C30 all in accordance with Drawings and Specifications and including Reinforcement High yield strength deformed bars conforming to BS 4449 Grade 460 including cutting bending binding binding wire cover blocks tests and all necessary fixing accessories all in accordance with the Drawings and Specifications and including Steel fabric reinforcement A 393 BRC mesh in two layers. All complete in accordance with the Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Beds Slabs Grade slabs upto 120 mm thickness | M3 | 800 | 94.5 | 75600 | 693.042 | 65492.469 | 106.958 | 10107.531
E | SUM FOR PAGE-5/68 | [5 empty] | 75600 |  | 65492.469 | 0 | 10107.531
C13 | Substructure Works | Reinforced insitu concrete poured vibrated ordinary Portland Cement OPC Concrete Grade C40 all in accordance with Drawings and Specifications and including Reinforcement High yield strength deformed bars conforming to BS 4449 Grade 460 including cutting bending binding binding wire cover blocks tests and all necessary fixing accessories all in accordance with the Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Substructure columns | M3 | 200 | 94.5 | 18900 | 113.54 | 10729.53 | 86.46 | 8170.47
C14 | Substructure Works | Sundries Concrete and Block work Protection | Polythene sheet gauge 1200 all in accordance with Drawings and Specifications to surfaces of structural members in contact with soil | M2 | 8400 | 2 | 16800 | 8618.95 | 17961.65 | -218.95 | -437.9
C15 | Substructure Works | Sundries Bitumenous Paint | Bitumenous Paint 3 coat to the surfaces of concrete | M2 | 10000 | 0.546 | 5460 |  | 0 | 10000 | 5460
C16 | Substructure Works | Sundries Bitumenous Sheet | Bitumenous Sheet to the surfaces of concrete | M2 | 5200 | 5.25 | 27300 |  | 0 | 5200 | 27300
F | SUM FOR PAGE-6/68 | [5 empty] | 68460 |  | 28691.18 | 0 | 40492.57
C17 | Substructure Works | Sundries Block work Protection including Bitumenous Paint and Bitumenous Sheet | Protection to concrete masonryblock work in contact with soil 3 coats of approved bituminous paint bituminous sheet and including flexible board all in accordance with Drawings and Specifications to surfaces of block work in contact with soil. | M2 | 22000 | 21 | 462000 | 15282.25 | 320927.25 | 6717.75 | 141072.75
C18 | Substructure Works | Concrete solid block work 10.5N per mm2 compressive strength cement and sand mortar 1to3 with and including stiffener columns and stiffener beams as required all in accordance with Drawings and Specifications | 200mm thick walls | M2 | 11000 | 9.45 | 103950 | 3732.2 | 35269.29 | 7267.8 | 68680.71
C19 | Substructure Works | The Contractor should read and quote as per the supply laying and all works are included and required approval and commissioning as per contract standards should be under the Contractor scope of work including required charges also including DNP scope and guarantees for material. | Important Note | Item | 0 | 0 | 0 | - | -
G | SUM FOR PAGE-7/68 | [5 empty] | 565950 |  | 356196.54 |  | 209753.46
C20 | Substructure Works | The Contractor is adviced to complete the project as per the drawing boq and specification also need to complete if anything missing in the drawing but mentioned in the boq and specification and viceversa. Should the Tenderer fail to insert any item here it will be deemed that this lump sum price for the tender includes all items and no subsequent claim for any additional items will be entertained | Important Note | Item | 0 | 0 | 0 | - | -
H | SUM FOR PAGE-8/68 | [5 empty] | 0 |  | -
C21 | Substructure Works | The Contractor is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum tender price for this section of the works. Should the Tenderer fail to insert any item here it will be deemed that this lump sum price for the tender includes all items and no subsequent claim for any additional items will be entertained | Important Note | Item | 0 | 0 | 0 | - | -
I | SUM FOR PAGE-9/68 | [5 empty] | 947257 |  | 656066.0415 |  | 291914.7084
C22 | Superstructure Works Concrete Works | Poured Concrete Reinforced insitu concrete poured vibrated Ordinary Portland Cement OPC concrete grade C30 all in accordance with the Drawings and Specifications and including Reinforcement High yield strength deformed bars conforming to BS 4449 Grade 460 including cutting bending binding binding wire cover blocks tests and all necessary fixing accessories all in accordance with the Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Suspended slabs waist slabs landingsstair etc. not exceeding 200 mm thickness | M3 | 1400 | 10.08 | 14112 | 1400 | 14112
J | SUM FOR PAGE-10/68 | [5 empty] | 14112 |  | 14112
C23 | Superstructure Works Concrete Works | Poured Concrete Reinforced insitu concrete poured vibrated Ordinary Portland Cement OPC Concrete Grade C30 all in accordance with the Drawings and Specifications and including Reinforcement High yield strength deformed bars conforming to BS 4449 Grade 460 including cutting bending binding binding wire cover blocks tests and all necessary fixing accessories all in accordance with the Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Columns | M3 | 380 | 13.153 | 4998.14 | 380 | 4998.14
K | SUM FOR PAGE-11/68 | [5 empty] | 4998.14 |  | 4998.14
C24 | Superstructure Works Concrete Works | Poured Concrete Reinforced insitu concrete poured vibrated Ordinary Portland Cement OPC Concrete Grade C30 all in accordance with the Drawings and Specifications and including Reinforcement High yield strength deformed bars conforming to BS 4449 Grade 460 including cutting bending binding binding wire cover blocks tests and all necessary fixing accessories all in accordance with the Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Beams | M3 | 650 | 8.53 | 5544.5 | 650 | 5544.5
L | SUM FOR PAGE-12/68 | [5 empty] | 5544.5 |  | 5544.5
C25 | Superstructure Works Concrete Works | Poured Concrete Reinforced insitu concrete poured vibrated Ordinary Portland Cement OPC Concrete Grade C30 all in accordance with the Drawings and Specifications and including Reinforcement High yield strength deformed bars conforming to BS 4449 Grade 460 including cutting bending binding binding wire cover blocks tests and all necessary fixing accessories all in accordance with the Drawings and Specifications and including Formwork to give as struck finish. Providing and erecting formwork including all necessary staging centering shuttering supports cross bracing deshuttering carefully making good the damaged surfaces wherever necessary all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Ramp | M3 | 200 | 1.26 | 252 | 200 | 252
C26 | Superstructure Works Concrete Works | Sundries | GRC Mesh in the Duct 300 X 400 refer to the Architectural Drawing. | NO | 20 | 21 | 420 | 20 | 420
M | SUM FOR PAGE-13/68 | [5 empty] | 672 |  | 672
C27 | Superstructure Works Concrete Works | Sundries | GRC Mesh in the Duct 300 X 500 refer to the Architectural Drawing. | NO | 20 | 21 | 420 | 20 | 420
C28 | Superstructure Works Concrete Works | Sundries | GRC Mesh in the Duct 300 X 1000 refer to the Architectural Drawing. | NO | 20 | 21 | 420 | 20 | 420
C29 | Superstructure Works Concrete Works | Sundries | Planter box including excavation backfilling disposals blinding solid blockwork waterproofing plaster all complete of various size | No | 100 | 47.25 | 4725 | 100 | 4725
C30 | Superstructure Works Masonry | Internal Walls Ordinary Portland cement concrete blocks 7.5N per mm2 compressive strength cement and sand mortar 1to3 with and including stiffener columns and stiffener beams as required all in accordance with the Drawings and Specifications | 200mm thick walls | M2 | 17400 | 15 | 261000 | 17400 | 261000
C31 | Superstructure Works Masonry | Sunken Slab Waterproofing | Providing and applying Sunken Slab Waterproof course with bituminous paint and bituminous membrane conforming to BSto6398 in horizontal joints laid strictly in compliance with approved manufacturers printed instructions and as directed by Engineer. | M2 | 700 | 3.6 | 2520 | 700 | 2520
N | SUM FOR PAGE-14/68 | [5 empty] | 269085 |  | 269085
| Superstructure Works Masonry | Roof Slab Waterproofing THERMAL AND MOISTURE PROTECTION COVERINGS AND LININGS | Combo roof treatment for thermal and moisture protection for open terraces by an approved expert agency complete with thermal and moisture resistant layers UV protection layer leveling course separation layers top finishes skirting with 250mm high etc. ensuring smooth runoff and with minimum 25 years of warranty. | Item | 1 | 15750 | 15750 | 1 | 15750
C33 | Superstructure Works Thermal and Moisture Protection | Backgrounds and Finishes Roof screed light weight concrete screed 1000 kg per m3 minimum 50 mm thick to a maximum of 125 mm thick | 50 mm minimum bed laid on concrete to falls and cross falls | M2 | 5600 | 1.05 | 5880 | 5600 | 5880
C34 | Superstructure Works Thermal and Moisture Protection | 4 mm thick torch applied acrylic polypropylene modified bitumen membrane with non woven polyester reinforcement and polyethylene film waterproof membrane including primer to roofs as per the manufacturer printed instructions complete as specified. Contractor to allow for 10 years guarantee and 24 hours flood test. | To roof decks 4mm thick on flat surface laid to falls and cross falls | M2 | 5600 | 1.05 | 5880 | 5600 | 5880
O | SUM FOR PAGE-15/68 | [5 empty] | 27510 |  | 27510
C35 | Superstructure Works Thermal and Moisture Protection | Skirting 300 mm girth including turning into groove | In up standsdrops and around plinths minimum 300 mm high including dressing over fillet grooves sealant tantalized batten etc. complete to roof deck | M | 1900 | 1.05 | 1995 | 1900 | 1995
C36 | Superstructure Works Thermal and Moisture Protection | Insulation Extruded high density polystyrene foam board insulation with rigid closed cell structure all in accordance with the specifications and drawings in external | to roof decks 50 mm thick laid on concrete spot bonded to waterproofing | M2 | 5600 | 1.05 | 5880 | 5600 | 5880
C37 | Superstructure Works Thermal and Moisture Protection | Roof Finishes | 300 x 300 x 30 mm white cement tiles bedded on and including cement mortar screed to falls and cross falls jointed in cement mortar movements joints etc. complete to roof | M2 | 5600 | 4.2 | 23520 | 5600 | 23520
C38 | Superstructure Works Thermal and Moisture Protection | Roof Finishes | 100 x 30 mm white cement skirting to upstands | M | 1900 | 3.15 | 5985 | 1900 | 5985
C39 | Superstructure Works Thermal and Moisture Protection | Roof Sundries | Allow for Providing dressing around 110mm 83mm UPVC rainwater outlets roof duct gargoyle extract fan soil and vent pipe | NO | 20 | 78.75 | 1575 | 20 | 1575
P | SUM FOR PAGE-16/68 | [5 empty] | 38955 |  | 38955
C40 | Superstructure Works Thermal and Moisture Protection | Roof Sundries | Allow for gun applied sealant to seal the joints and groove as applicable and as specified. | NO | 20 | 26.25 | 525 | 20 | 525
C41 | Superstructure Works Metal Works | WPC Pergola | Supply fabricate and install of WPC Pergola as per the approved Construction Drawing and refer to the Architectural Drawing for a highquality WPC Pergola waterproof and antimoisture. The Contractor should submit a detailed drawing of pergola approval 10 years guarantee.. | NO | 19 | 210 | 3990 | 19 | 3990
C42 | Superstructure Works Metal Works | Staircase hand rail | Stainless steel handrail as shown in the Architectural drawing shop drawings with full sections details to be approved before supply. Note to all stainless steel material shall be of 316 grade. | M | 200 | 26.25 | 5250 | 200 | 5250
C43 | Superstructure Works Metal Works | CAT Ladder | Supply and install a 3800mm high CAT steel Ladder as specified and detailed on the drawing with anticorrelation epoxy pain. | No | 20 | 152.25 | 3045 | 20 | 3045
C44 | Superstructure Works Doors and Windows | Wood Doors Note | 1 All timber and veneers shall be well conditioned seasoned dried vacuum treated and preservative treated all as specified | Item | 1 | 0 | 0 | 1 | 0
C45 | Superstructure Works Doors and Windows | Wood Doors Note | 2 Prepare the surface prime and apply two under coats and two finishing coats of high gloss enamel paint of approved quality make and shade for shutter and frame | Item | 1 | 0 | 0 | 1 | 0
C46 | Superstructure Works Doors and Windows | Wood Doors Note | 3 All hardwood timber shall be best quality Meranti | Item | 0 | 0 | 0 | 1 | 0
Q | SUM FOR PAGE-17/68 | [5 empty] | 12810 | 1 | 12810
C47 | Superstructure Works Doors and Windows | Wood Doors Note | 4 Sizes stated are structural opening sizes | Item | 0 | 0 | 0 | 0 | 0
C48 | Superstructure Works Doors and Windows | Wood Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade | Type D1 double leaf overall size 1800x2400mm high | No | 20 | 892.5 | 17850 |  |  | 20 | 17850 | 20 | 17850 | Replaced with Aluminium Door - Check Appendix A
R | SUM FOR PAGE-18/68 | [5 empty] | 17850 |  |  | 0 | 0 | 0 | 0 | Replaced with Aluminium Door - Check Appendix A
C49 | Superstructure Works Doors and Windows | Wood Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade | Type D2 single leaf overall size 1000x2400mm high | No | 20 | 262.5 | 5250 |  |  | 20 | 5250 | 20 | 5250 | Replaced with Aluminium Door - Check Appendix A
S | SUM FOR PAGE-19/68 | [5 empty] | 5250 |  | 0
C50 | Superstructure Works Doors and Windows | Wood Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade | Type D3 single leaf overall size 1000x2100mm high | No | 160 | 229.7 | 36752 |  | 0 | 160 | 36752
T | SUM FOR PAGE-20/68 | [5 empty] | 36752 |  | 0
C51 | Superstructure Works Doors and Windows | Wood Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade | Type D4 single leaf overall size 800x2100mm high | No | 100 | 220.5 | 22050 |  | 0 | 100 | 22050
U | SUM FOR PAGE-21/68 | [5 empty] | 22050 |  | 0
C52 | Superstructure Works Doors and Windows | Wood Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade | Type D5 single leaf overall size 1000x2100mm high | No | 40 | 262.5 | 10500 | 40 | 10500
V | SUM FOR PAGE-22/68 | [5 empty] | 10500 |  | 10500
C53 | Superstructure Works Doors and Windows | Wood Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade | Type D6 single leaf overall size 1000x2400mm high | No | 40 | 131.25 | 5250 | 40 | 5250
W | SUM FOR PAGE-23/68 | [5 empty] | 5250 |  | 5250
C54 | Superstructure Works Doors and Windows | WPC Solid Core Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade. | Type D1 double leaf overall size 1800x2400mm high | Item | 1 | 9135 | 9135 |  | 0 | 1 | 9135
X | SUM FOR PAGE-24/68 | [5 empty] | 9135 |  | 0 | 0 | 0
C55 | Superstructure Works Doors and Windows | WPC Solid Core Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade. | Type D2 single leaf overall size 1000x2400mm high | Item | 1 | 4410 | 4410 |  | 0 | 1 | 4410
Y | SUM FOR PAGE-25/68 | [5 empty] | 4410 |  | 0
C56 | Superstructure Works Doors and Windows | WPC Solid Core Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade. | Type D3 single leaf overall size 1000x2100mm high | Item | 1 | 26460 | 26460 | 1 | 26460
Z | SUM FOR PAGE-26/68 | [5 empty] | 26460 |  | 26460
C57 | Superstructure Works Doors and Windows | WPC Solid Core Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade. | Type D4 single leaf overall size 800x2100mm high | Item | 1 | 15750 | 15750 | 1 | 15750
AA | SUM FOR PAGE-27/68 | [5 empty] | 15750 |  | 15750
C58 | Superstructure Works Doors and Windows | WPC Solid Core Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade. | Type D5 single leaf overall size 1000x2100mm high | Item | 1 | 8400 | 8400 |  | 0 | 1 | 8400
AB | SUM FOR PAGE-28/68 | [5 empty] | 8400 |  | 0 | 0 | 0
C59 | Superstructure Works Doors and Windows | WPC Solid Core Doors Door comprising profiled heads jambs frames subframes architraves beadings mouldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved fixed to hardwood including paint All locks shall be under master key system as detailed on drawing Note All stainless steel fittings shall be of 316 grade. | Type D6 single leaf overall size 1000x2400mm high | Item | 1 | 4410 | 4410 |  | 0 | 1 | 4410
AC | SUM FOR PAGE-29/68 | [5 empty] | 4410 |  | 0
C60 | Superstructure Works Doors and Windows | Ironmongery Supply and fix of ironmongery with and including all necessary fixing accessories and screws to match all in accordance with the specifications and drawings to wood doors | Allow for grand master key and master key system | No | 20 | 31.5 | 630 | 20 | 630
C61 | Superstructure Works Doors and Windows | UPVC windows window sets complete with all necessary ironmongery as specified including fixing to blockwork or concrete and mastic pointing all around all as specified and detailed on drawing and including required reinforcement cement concrete lintels | Type W1 overall size 2000 x 1300mm high | No | 160 | 68.906 | 11024.96 | 160 | 11024.96
AD | SUM FOR PAGE-30/68 | [5 empty] | 11654.96 |  | 11654.96
C62 | Superstructure Works Doors and Windows | UPVC windows window sets complete with all necessary ironmongery as specified including fixing to blockwork or concrete and mastic pointing all around all as specified and detailed on drawing and including required reinforcement cement concrete lintels | Type W2 overall size 1200 x 900mm high | No | 20 | 47.25 | 945 | 20 | 945
C63 | Superstructure Works Doors and Windows | UPVC windows window sets complete with all necessary ironmongery as specified including fixing to blockwork or concrete and mastic pointing all around all as specified and detailed on drawing and including required reinforcement cement concrete lintels | Type W3 overall size 600 x 1300mm high | No | 60 | 78.75 | 4725 | 60 | 4725
AE | SUM FOR PAGE-31/68 | [5 empty] | 5670 |  | 5670
C64 | Superstructure Works Doors and Windows | UPVC windows window sets complete with all necessary ironmongery as specified including fixing to blockwork or concrete and mastic pointing all around all as specified and detailed on drawing and including required reinforcement cement concrete lintels | Type W4 overall size 1000 x 3700mm high | No | 20 | 94.5 | 1890 | 20 | 1890
C65 | Superstructure Works Doors and Windows | UPVC ventilator ventilator sets complete with all necessary ironmongery as specified including fixing to blockwork or concrete and mastic pointing all around all as specified and detailed on drawing and including required reinforcement cement concrete lintels | Type V overall size 600 x 600mm high | No | 100 | 94.5 | 9450 | 100 | 9450
AF | SUM FOR PAGE-32/68 | [5 empty] | 11340 |  | 11340
C66 | Superstructure Works Finishes | Backgrounds Plaster cement and sand 1to3 internal To walls and columns on concrete block base internal including stainsteel mesh butterfly angle between the concrete column and block work. | to receive internal painting | M2 | 16200 | 2.385 | 38637 | 16200 | 38637
C67 | Superstructure Works Finishes | Backgrounds Plaster cement and sand 1to4 external To walls and columns on concrete block base external including stainsteel mesh butterfly angle between the concrete column and block work. | to receive external painting | M2 | 14000 | 2.07 | 28980 | 14000 | 28980
C68 | Superstructure Works Finishes | Allow for laying of Marble Threshold as per the specifications drawings and to approval of the Engineer. | Internal Floor Tile | No | 20 | 945 | 18900 | 20 | 18900
AG | SUM FOR PAGE-33/68 | [5 empty] | 86517 |  | 86517
C69 | Superstructure Works Finishes | Floor Tilesto FF1 Ceramic floor tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | 600 x 600 x 8 mm AntiSlip tiling to floor | M2 | 3700 | 4.086 | 15118.2 | 3700 | 15118.2
C70 | Superstructure Works Finishes | Floor Tilesto FF2 Ceramic floor tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | 600 x 600 x 8 mm AntiSlip tiling to floor | M2 | 550 | 4.582 | 2520.1 | 550 | 2520.1
C71 | Superstructure Works Finishes | Floor Tilesto FF3 Ceramic floor tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | 600 x 600 x 8 mm AntiSlip tiling to floor | M2 | 600 | 6.3 | 3780 | 600 | 3780
C72 | Superstructure Works Finishes | Floor Tilesto FF4 30mm tk. Granite laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | 30mm thick Granite for Staircase and Steps | M2 | 600 | 5.6 | 3360 | 600 | 3360
AH | SUM FOR PAGE-34/68 | [5 empty] | 24778.3 |  | 24778.3
C73 | Superstructure Works Finishes | Floor Tilesto FF5 20mm tk. Granite laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | 20mm tk. Granite Tiles alternative bands of rough smooth coping both sides | M2 | 500 | 2.52 | 1260 | 500 | 1260
C74 | Superstructure Works Finishes | Floor Tilesto FF6 80mm tk. Interlock tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | 80mm tk. Heavy Duty Interlock Tile | M2 | 4000 | 1.47 | 5880 | 4000 | 5880
C75 | Superstructure Works Finishes | Floor Tilesto FF7 Porcelain tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | Porcelain Tiles 600 X 600 X 20 | M2 | 800 | 16.275 | 13020 | 800 | 13020
C76 | Superstructure Works Finishes | Floor Tilesto FF9 Granite tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | 30mm thick Granite for Entrance floor and Staircase and Steps | M2 | 200 | 14 | 2800 | 200 | 2800
AI | SUM FOR PAGE-35/68 | [5 empty] | 22960 |  | 22960
C77 | Superstructure Works Finishes | Skirting Tilesto FF1 Ceramic tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | Ceramic Tiles 600 X 150 X 8 Anti Slip | M | 3800 | 1.658 | 6300.4 | 3800 | 6300.4
C78 | Superstructure Works Finishes | Skirting Tilesto FF4 30mm tk. Granite laid on screed grouted with waterproof coloured compatible mortar to manufacturers specificationinstruction; internally | 30mm thick Granite for Staircase and Steps | M | 200 | 4.725 | 945 | 200 | 945
C79 | Superstructure Works Finishes | Allow for construction of Decorative projection weather coat stoneshield with 10 years garantee as per the specifications drawings and to approval of the Engineer | External Elevation | No | 20 | 47.25 | 945 | 20 | 945
AJ | SUM FOR PAGE-36/68 | [5 empty] | 8190.4 |  | 8190.4
C80 | Superstructure Works Finishes | Allow for construction of Decorative projection weather coat stoneshield with 10 years garantee as per the specifications drawings and to approval of the Engineer | F1F2 External Elevation | M2 | 11600 | 1.72 | 19952 | 11600 | 19952
C81 | Superstructure Works Finishes | Allow for construction of Decorative projection as per the specifications drawings and to approval of the Engineer | F3 External Elevation | Item | 2400 | 0.525 | 1260 | 2400 | 1260
C82 | Superstructure Works Finishes | Wall Finishes FF1 Painting and decorating Eligance marble paint finish internal | Smooth Plaster Painting Anti Fungal and Water Resistance | M2 | 12200 | 2.479 | 30243.8 | 12200 | 30243.8
C83 | Superstructure Works Finishes | Wall Finishes FF2 Ceramic Tiles 600 X 200 X 8 Anti Slip | Ceramic Tiles 600 X 200 X 20 Anti Slip | M2 | 1700 | 4.941 | 8399.7 | 1700 | 8399.7
C84 | Superstructure Works Finishes | Wall Finishes FF3 Ceramic Tiles 600 X 200 X 8 Anti Slip | Ceramic Tiles 600 X 200 X 20 Anti Slip | M2 | 3600 | 7 | 25200 | 3600 | 25200
AK | SUM FOR PAGE-37/68 | [5 empty] | 85055.5 |  | 85055.5
C85 | Superstructure Works Finishes | Ceilings Finishes FF1 Painting and decoratingEligance marble paint finish internal | Smooth Plaster Painting Anti Fungal and Water Resistance | M2 | 3700 | 7.15 | 26455 | 3700 | 26455
C86 | Superstructure Works Finishes | Ceilings Finishes FF2 Smooth Plaster PaintingEligance marble paint finish Anti Fungal and Water Resistance | Smooth Plaster Painting Anti Fungal and Water Resistance | M2 | 550 | 7.636 | 4199.8 | 550 | 4199.8
C87 | Superstructure Works Finishes | Ceilings Finishes FF3 Smooth Plaster Painting Eligance marble paint finish Anti Fungal and Water Resistance | Smooth Plaster Painting Anti Fungal and Water Resistance | M2 | 600 | 8.4 | 5040 | 600 | 5040
C88 | Superstructure Works Finishes | Ceilings Finishes FF4 Smooth Plaster Painting Eligance marble paint finish Anti Fungal and Water Resistance | Smooth Plaster Painting Anti Fungal and Water Resistance | M2 | 600 | 7.88 | 4728 | 600 | 4728
C89 | Superstructure Works Finishes | Allow for supply fabricate and installation of Gas Cyclinder Stage as per the specifications drawings and to approval of the Engineer. | Gas Cylinder Stage | No | 20 | 36.75 | 735 | 20 | 735
AL | SUM FOR PAGE-38/68 | [5 empty] | 41157.8 |  | 41157.8
C90 | Superstructure Works Finishes | Allow for corecut remove and smooth finish as per the specifications drawings and to approval of the Engineer. | Drain Open to connect Sewage Tanker to the Holding Tank size 550 X 400mm | No | 20 | 42 | 840 | 20 | 840
C91 | Superstructure Works Finishes | Allow for supply fabricate and installation of water point protection as per the specifications drawings and to approval of the Engineer. | Water point protection | No | 20 | 47.25 | 945 | 20 | 945
C92 | Superstructure Works Finishes | Allow for supply fabricate and installation of Meter Panel protection as per the specifications drawings and to approval of the Engineer. | Meter Panel protection | No | 20 | 47.25 | 945 | 20 | 945
AM | SUM FOR PAGE-39/68 | [5 empty] | 2730 |  | 2730
C93 | Superstructure Works Finishes | Allow for supply fabricate and installation of Kitchen Stage including Stage Concrete Stage Korean Top and Stage Area Ceramic Wall Tile as per the specifications drawings and to approval of the Engineer. | Kitchen Stage Concrete Korean Top Ceramic Wall Tiles | No | 20 | 178.5 | 3570 | 20 | 3570
C94 | Superstructure Works Finishes | Allow for supply fabricate and installation of Kitchen Hood Range including Aluminum Kitchen Cabinet above and Aluminum Kitchen Cabinet below all as per the specifications drawings and to approval of the Engineer. | Kitchen Hood Range Cabinet above and below Cabinet. | No | 20 | 189 | 3780 | 20 | 3780
AN | SUM FOR PAGE-40/68 | [5 empty] | 7350 |  | 7350
C95 | Superstructure Works Finishes | The Contractor should read and quote as per the supply laying and all works are included and required approval commissioning as per contract standards should be under the Contractor scope of work including required charges also including DNP scope and guarantees for material. | Important Note | Item | 0 | 0 | 0 | 0 | 0
C96 | Superstructure Works Finishes | The Contractor is adviced to complete the project as per the drawing boq and specification also need to complete if anything missing in the drawing but mentioned in the boqspecification and viceversa. Should the Tenderer fail to insert any item here it will be deemed that this lump sum price for the tender includes all items and no subsequent claim for any additional items will be entertained | Important Note | Item | 0 | 0 | 0 | 0 | 0
AO | SUM FOR PAGE-41/68 | [5 empty] | 0 |  | -
C97 | Superstructure Works Finishes | The Contractor is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum tender price for this section of the works. Should the Tenderer fail to insert any item here it will be deemed that this lump sum price for the tender includes all items and no subsequent claim for any additional items will be entertained | Important Note | Item | 0 | 0 | 0 | 0 | 0
P1 | Sanitary Installation | UPVC pipes to BS 4514 1983 and BS 4660 1973 including all joints and accessories and brackets | UPVC drain pipes to BS 4514 1983 and BS 4660 1973 including all joints with ring seals fittings and accessories in the running length. | Item | 0 | 0 | 0 | 0 | 0
P2 | Sanitary Installation | UPVC pipes to BS 4514 1983 and BS 4660 1973 including all joints and accessories and brackets | 160mm diamater | M | 1120 | 6.975 | 7812 | 1120 | 7812
AP | SUM FOR PAGE-42/68 | [5 empty] | 7812 |  | 7812
P3 | Sanitary Installation | UPVC pipes to BS 4514 1983 and BS 4660 1973 including all joints and accessories and brackets | 110mm diamater | M | 320 | 4.725 | 1512 | 320 | 1512
P4 | Sanitary Installation | UPVC pipes to BS 4514 1983 and BS 4660 1973 including all joints and accessories and brackets | 82mm diameter | M | 600 | 4.41 | 2646 | 600 | 2646
P5 | Sanitary Installation | UPVC pipes to BS 4514 1983 and BS 4660 1973 including all joints and accessories and brackets | 50mm diameter | M | 580 | 4.78 | 2772.4 | 580 | 2772.4
P6 | Sanitary Installation | UPVC pipes to BS 4514 1983 and BS 4660 1973 including all joints and accessories and brackets | 42mm diameter | M | 200 | 10.5 | 2100 | 200 | 2100
P7 | Sanitary Installation | vent cowl | Vent cowl with weathering apron 50mm diameter | No | 80 | 2.1 | 168 | 80 | 168
P8 | Sanitary Installation | Floor Drain trap | Floor Trap with 150 X 150 mm SS grating Cover | No | 160 | 2.625 | 420 | 160 | 420
P9 | Sanitary Installation | Gully Trap | 300 mm and 300 mm gully trap of approximate 300 mm depth set in concrete Grade 30 Nmm� joints to drain pipes complete with 300 mm and 300 mm medium duty cast iron cover and frame. | No | 100 | 58.8 | 5880 | 100 | 5880
P10 | Sanitary Installation | Inspection Chambers | Manhole size 600 and 600 mm internally upto 1.30m deep to invert | No | 185 | 45.4 | 8399 | 185 | 8399
AQ | SUM FOR PAGE-43/68 | [5 empty] | 23897.4 |  | 23897.4
P11 | Sanitary Installation | Manhole Cover | 600 and 600 mm medium duty double seal cast iron manhole cover and frame. | No | 185 | 55.62 | 10289.7 | 185 | 10289.7
P12 | Sanitary Installation | Holding tank with soak pit | Reinforced concrete grade 30 N mm2 holding tank size 4000 and 2000 and 2500 mm deep internally with concrete grade 15 N mm2 and 100mm thick blinding and 250mm thick concrete base slab and 200mm thick concrete wall and roof slab and including reinforcement and formwork and rendering and step irons and 3 coats of bitumen paint and 2 layer of 1000 gauge polythene sheet and excavation and dewatering backfilling and disposal of surplus excavated materials and 600 and 600 mm heavy duty double seal ductile iron cover and frame and Precast concrete soak pit size 2000 mm diameter and 2500 mm deep internally including reinforcement and excavation and dewatering and backfilling and disposal of surplus excavated materials 600 and 600 mm heavy duty ductile iron cover and frame et as detailed on drawing. | No | 20 | 945 | 18900 | 20 | 18900
|  |  | RCC Holding Tank | No |  | 827.06 |  | 20
|  |  | Sak Pit | No |  | 117.94 |  | 20
P13 | Sanitary Wares and Fittings | Semi pedestal wash basin | 650 mm and 475 mm vitreous china white wash basin with semi pedestal and center tap hole and overflow and bottle trap including required complete Civil Works. | No | 100 | 15.75 | 1575 | 100 | 1575
P14 | Sanitary Wares and Fittings | Counter top wash basin | 630 mm and 510 mm vitreous china white counter top wash basin and center tap hole and overflow and bottle trap including required complete Civil Works. | No | 80 | 15.75 | 1260 | 80 | 1260
AR | SUM FOR PAGE-44/68 | [5 empty] | 32024.7 |  | 32024.7
P15 | Sanitary Wares and Fittings | Stainless Steel Sink | 1000 mm and 550 mm stainless steel sink single bowl single drainer with drainboard to BS 1244 complete with 2 piece tubular P trap chain and plug and waste and brackets including required complete Civil Works. | No | 20 | 2.1 | 42 | 20 | 42
P16 | Sanitary Wares and Fittings | European Water Closet | 400 mm and 685 mm vitreous china white concealed tank wall hung mounted EWC squatting pan built in wall toilet dual flush 3L or 6L concealed cistern and heavy duty auto closed seat and cover including required complete Civil Works. | No | 100 | 1.05 | 105 | 100 | 105
P17 | Sanitary Wares and Fittings | Faucet spray | Chromium plated approved ablution faucet with angle valve and hose and spray unit. | No | 100 | 1.05 | 105 | 100 | 105
P18 | Sanitary Wares and Fittings | Wash Basin Mixer | Single lever chrome plated wash basin mixer including pop up waste. | No | 180 | 1.05 | 189 | 180 | 189
P19 | Sanitary Wares and Fittings | Sink Mixer | Single lever chrome plated Sink mixer. | No | 20 | 2.1 | 42 | 20 | 42
P20 | Sanitary Wares and Fittings | Toilet tissue holder | Recessed type stainless steel Toilet tissue dispenser or holder with stainless steel hood. | No | 100 | 1.05 | 105 | 100 | 105
P21 | Sanitary Wares and Fittings | Towel rail | 610 and 75 and 75 mm towel rail | No | 140 | 1.05 | 147 | 140 | 147
P22 | Sanitary Wares and Fittings | Mirror | 450 and 600 mm mirror 6 mm thick and bevel edged and plywood backing fixed with chromium plated dome headed screws | No | 180 | 1.05 | 189 | 180 | 189
P23 | Sanitary Wares and Fittings | Bath shower | Single lever dual control bath shower mixer | No | 100 | 1.05 | 105 | 100 | 105
P24 | Sanitary Wares and Fittings | Bip tap | For internal and external. | No | 140 | 0.6 | 84 | 140 | 84
AS | SUM FOR PAGE-45/68 | [5 empty] | 1113 |  | 1113
P25 | Sanitary Installation AC DRAIN SYSTEM | NOTE | HPUPVC pipes and fittings to BS 3505 Class E including all joints and connections and fittings. | Item | 0 | 0 | 0 | 0 | 0
P26 | Sanitary Installation AC DRAIN SYSTEM | Hpupvc pipe | 25 mm diameter pipe for air conditioner drainage pipe to ac drain pit. | M | 1230 | 0.512 | 629.76 | 1230 | 629.76
P27 | Water Supply installation | Polypropylene random copolymer pipe NOTE | Polypropylene random copolymer pipes and fittings and cold and hot water connections to international standard ISO EN ISO 15874 2003 and DIN 80777 8078 including up stand and brackets exposed insulation as per Specification in running length and 25mm thick rigid performed sectional fiber glass insulation with aluminum foil and fiber glass reinforced adhesive and canvas Cora cloth with 2 coats of foster paint one coat of water proof emulsion glossy white paint and vapour barrier coating as described. | Item | 0 | 0 | 0 | 0 | 0
P28 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 15 mm diameter | M | 1400 | 0.9 | 1260 | 1400 | 1260
P29 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 20 mm diameter | M | 2200 | 0.46 | 1012 | 2200 | 1012
P30 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 25 mm diameter | M | 550 | 2.52 | 1386 | 550 | 1386
P31 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 32 mm diameter | M | 1600 | 1.05 | 1680 | 1600 | 1680
P32 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 40 mm diameter | M | 1000 | 0.84 | 840 | 1000 | 840
AT | SUM FOR PAGE-46/68 | [5 empty] | 6807.76 |  | 6807.76
P33 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 50 mm diameter | M | 50 | 2.1 | 105 | 50 | 105
P34 | Water Supply installation | Cold and Hot water Valves | Supply and install the following Isolating valves to BS 5154 series B bronze and wedge gate pattern and screwed joints with adaptor to pipes etc wherever shown in drawings and or specified and as approved by the Engineer. | Item | 0 | 0 | 0 | 0 | 0
P35 | Water Supply installation | Cold and Hot water Valves | 15 mm diameter | No | 700 | 0.81 | 567 | 700 | 567
P36 | Water Supply installation | Cold and Hot water Valves | 20 mm diameter | No | 400 | 0.945 | 378 | 400 | 378
P37 | Water Supply installation | Cold and Hot water Valves | 25 mm diameter | No | 40 | 2.1 | 84 | 40 | 84
P38 | Water Supply installation | Cold and Hot water Valves | 32 mm diameter isolating value | No | 120 | 1.925 | 231 | 120 | 231
P39 | Water Supply installation | Cold and Hot water Valves | 40 mm diameter | No | 40 | 1.575 | 63 | 40 | 63
P40 | Water Supply installation | Cold and Hot water Valves | 50 mm diameter | No | 20 | 5.25 | 105 | 20 | 105
P41 | Water Supply installation | Equipment and Accessories Note | Equipment and accessories as specified including all connections and fittings | Item | 0 | 0 | 0 | 0 | 0
P42 | Water Supply installation | Water Tank | 600 US gallon capacity GRP type water storage tank with foundation epoxy coated frame ball valve overflows etc to approval | No | 20 | 21 | 420 | 20 | 420
AU | SUM FOR PAGE-47/68 | [5 empty] | 1953 |  | 1953
P43 | Water Supply installation | Water Heater | 50 liter capacity horizontal type copper tank high level wall mounted electrical water heater including all connections and fixing. | No | 120 | 68.25 | 8190 | 120 | 8190
P44 | Water Supply installation | Booster pump | Cold water pressurised booster pump set 1No Working pump and 1No standby pump for domestic water supply delivering 2 l per sec at 2.5 bar with Gate valve and Non return valve and float switch and pressue guage and pressure vessel 30 to 50 lit PN10 and water low level cut off relay etc with pump room all complete as detailed in the drawing to approval. | No | 20 | 99.75 | 1995 |  | 0 | 20 | 1995
P45 | RAIN WATER SYSTEM Rain Water Installation | Rain Water UPVC Pipes | UPVC pipes to BS 4514 or 1983 including all joints and fittings and accessories and connections and brackets | Item | 0 | 0 | 0 | 0 | 0
P46 | RAIN WATER SYSTEM Rain Water Installation | Rain Water UPVC Pipes | 110mm diamater | m | 700 | 1.8 | 1260 | 700 | 1260
P47 | RAIN WATER SYSTEM Rain Water Installation | Rain water Outlet | 110 mm diameter root terminal socket tail rain water outlet. | No | 80 | 3.675 | 294 | 80 | 294
P48 | Plumbing and Drainage System | Sundries | Allow for working drawings and asbuilt drawings. | Item | 1 | 0 | 0 | 1 | 0
P49 | Plumbing and Drainage System | Sundries | Allow for all supports plinths and dog houses and necessary builder s work after obtaining approval through shop drawings including setting out and marking holes and chases cut outs etc and making good. | Item | 1 | 10.5 | 10.5 | 1 | 10.5
AV | SUM FOR PAGE-48/68 | [5 empty] | 11749.5 |  | 9754.5
P50 | Plumbing and Drainage System | Sundries | Allow for all protective and decorative painting. | Item | 1 | 315 | 315 | 1 | 315
P51 | Plumbing and Drainage System | Sundries | Allow for providing Test Certificates | Item | 1 | 315 | 315 | 1 | 315
P52 | Plumbing and Drainage System | Sundries | Allow for co ordination with other Engineering Installations. | Item | 1 | 840 | 840 | 1 | 840
P53 | Plumbing and Drainage System | Sundries | Allow for testing and commissioning of underground cable prior to and after backfilling. | Item | 1 | 945 | 945 | 1 | 945
P54 | Plumbing and Drainage System | Sundries | Allow for OandM Manual | Item | 1 | 945 | 945 | 1 | 945
P55 | Plumbing and Drainage System | Sundries | Allow for sterilization of all pipes and over head tanks etc. | Item | 1 | 945 | 945 | 1 | 945
P56 | Plumbing and Drainage System | Sundries | Allow for spare parts for three years as per manufacturers recommendation. | Item | 1 | 1785 | 1785 | 1 | 1785
P57 | Plumbing and Drainage System | Sundries | Allow for training OandM staff. | Item | 1 | 1680 | 1680 | 1 | 1680
P58 | Plumbing and Drainage System | Sundries | Allow for any other activity not listed above. | Item | 1 | 63 | 63 | 1 | 63
AW | SUM FOR PAGE-49/68 | [5 empty] | 7833 |  | 7833
F1 | Fire Fighting Installation | Fire Fighting Installation | Supply and install a complete fire fighting system to the approval of the Civil Defence Authorities and complete with association and fitting as shown in drawings or specified in accordance with BS 530 Part 1 1976 and Part 3 1985 and to approval of the Engineer. | Item | 1 | 0 | 0 |  | 0 | 0 | 0
F2 | Fire Fighting Installation | Fire hose reel | 1.5 mm thick Electro static powder coated painted stainless steel recessed type fire hose reel cabinet with 25 mm diameter hose reel and 45 meter long including 1 No. 9 litter foam type fire extinguisher and 1 No 5Kg carbon dioxide type fire extinguisher with civil defence final approval certificate. | No | 3 | 0 | 0 | 3 | 0 | 0 | 0
F3 | Fire Fighting Installation | outlet | Wet riser outlet with valve assembly | NO | 3 | 80 | 240 | 3 |  | 3 | 240
F4 | Fire Fighting Installation | valve | Zonal control valve assembly | NO | 1 | 120 | 120 | 1 |  | 1 | 120
F5 | Fire Fighting Installation | inlet | Breaching inlet | NO | 1 | 200 | 200 | 1 |  | 1 | 200
F6 | Fire Fighting Installation | Fire Extinguisher | 2 Kg carbon dioxide fire extinguisher | No | 20 | 2.1 | 42 | 20 | 42
F7 | Fire Fighting Installation | Fire Extinguisher | 180 and 180 mm fire blanket | No | 20 | 1.05 | 21 | 20 | 21
F8 | Fire Fighting Installation | Fire alarm cable and conduits and panel and accessories installation | Automatic Multi detector point | No | 20 | 130 | 2600 | 20 | 2600
G1 | Gas supply line | Gas line | Supply and fix 18 mm diameter MS schedule 40 gas pipeline including pickup points and connection to Gas Stove | M | 100 | 10.5 | 1050 | 100 | 1050
AX | SUM FOR PAGE-50/68 | [5 empty] | 4273 |  | 3713
M1 | Air Conditioning and Ventilation Installation | High level Wall mounted Split AC with DX unit | 18000 BTU HR capacity high level wall mounted split type air conditioner including connection to electrical outlet and concrete base foundation. | No | 120 | 240 | 28800 | 120 | 28800
M2 | Air Conditioning and Ventilation Installation | High level Wall mounted Split AC with DX unit | 30000 BTU HR capacity high level wall mounted split type air conditioner including connection to electrical outlet and concrete base foundation. | No | 20 | 320 | 6400 | 20 | 6400
M3 | Air Conditioning and Ventilation Installation | High level Wall mounted Split AC with DX unit | 36000 BTU HR capacity high level wall mounted split type air conditioner including connection to electrical outlet and concrete base foundation. | No | 20 | 420 | 8400 | 20 | 8400
M4 | Mechanical installation | Sundries | Allow for builders works in connection with sanitary and water services including holes and chases and sleeves and pipe brackets painted casing to exposed pipes and access panels and weather proof flashing to vent pipes passing through roof etc. | Item | 1 | 0 | 0 | 1 | 0
M5 | Mechanical installation | Sundries | Allow for incidental works such as co ordination with other engineering installations | Item | 1 | 0 | 0 | 1 | 0
M6 | Mechanical installation | Sundries | Allow for protective covering and painting to all exposed water supply and ventilation pipe work. | Item | 1 | 0 | 0 | 1 | 0
M7 | Mechanical installation | Sundries | Allow for identification labels and color coding etc. | Item | 1 | 0 | 0 | 1 | 0
M8 | Mechanical installation | Sundries | Allow for testing and commissioning. | Item | 1 | 0 | 0 | 1 | 0
M9 | Mechanical installation | Sundries | Allow for chlorination of water storage tanks and pipe work | Item | 1 | 0 | 0 | 1 | 0
AY | SUM FOR PAGE-51/68 | [5 empty] | 43600 |  | 43600
M10 | Mechanical installation | Sundries | Allow for document As installed drawings and Operation ad Maintenance Manuals | Item | 1 | 0 | 0 | 1 | 0
E1 | Electrical Engineering Installation | Note | Supply and install 11 KV underground line including intermediate pole tapping arrangement from existing O H linea and stays and pit excavation and cable trench and backfilling and all accessories and connections as per Public Authority for Electricity and Water rules and regulation and to approval. | Item | 1 | 0 | 0 | 1 | 0
E2 | Electrical Engineering Installation | Cable | 3C and 240 mm2 11 KV UG cable including termination | M | 100 | 0 | 0 | 100 | 0
E3 | Electrical Engineering Installation | Excavation | Excavation of HV cable trench and pit and backfilling as per Public Authority for Electricity and Water rules and regulation and to approval. | M | 100 | 0 | 0 | 100 | 0
E4 | Electrical Engineering Installation | Testing and commissioning | Testing and commissioning including liaison with Public Authority for Electricity and Water | Item | 1 | 0 | 0 | 1 | 0
E5 | Electrical Engineering Installation | Substation Equipments Note | Supply and install electrical substation equipments including foundation all as per Public Authority for Electricity and Water requirement and to approval. | Item | 1 | 0 | 0 | 1 | 0
E6 | Electrical Engineering Installation | Transformer | 1600 KVA 11KV 415V transformer including cable termination | No | 1 | 0 | 0 | 1 | 0
E7 | Electrical Engineering Installation | Feeder Pillar | 2500 A incomer feeder pillar with 2Nos 600A three Phase Strip fuse isolator 4 Nos 400A three phase Strip Fuse isolator and 1Nos spare 100A single phase Strip fuse isolator and 1 Nos spare 200A three phase strip fuse isolator in weatherproof enclosure IP 54 with seperate CT meter weatherproof encolsure including cable termination. | No | 1 | 0 | 0 | 1 | 0
AZ | SUM FOR PAGE-52/68 | [5 empty] | 0 |  | 0
E8 | Electrical Engineering Installation | RMU | Substation Ring Main Unit RMU from 2OLU and 1HFU to 2OLU and 2HFU including excavation and reaarangement of RMU and cable termination as per MEDC Public Authority for Electricity and Water requirement and to approval. | No | 1 | 0 | 0 | 1 | 0
E9 | Electrical Engineering Installation | Cable | 3C and 120 mm2 11 KV UG cable from RMU to transformers | M | 10 | 0 | 0 | 10 | 0
E10 | Electrical Engineering Installation | Cable | 7 Runs of 1C and 630 mm2 XLPE PVC SWA PVC Cu. Cable from transformer to Feeder pillar And Main Feeder Pillar to SubFeeder Pillar including all termination | M | 20 | 0 | 0 | 20 | 0
E11 | Electrical Engineering Installation | Manhole | 2500 and 1500 and 700 mm deep internal size electrical manhole RCC wall and rendering internally 75 mm PCC at bottom with 800 and 800 mm double seal heavy duty cast iron cover and frame | No | 1 | 0 | 0 | 1 | 0
E12 | Electrical Engineering Installation | Electrical Engineering Installation | Elecricity and water connection to be charged local Public Authority for Electricity and Water | Item | 1 | 0 | 0 | 1 | 0
E13 | Electrical Engineering Installation | caution tape | Cable caution tape marked in Arabic and English for cable. | M | 1250 | 0 | 0 | 1250 | 0
E14 | Electrical Engineering Installation | PVC tile | PVC tile | M | 1250 | 0 | 0 | 1250 | 0
E15 | Electrical Engineering Installation | Earth pit | Earthing with earth pit | Item | 1 | 0 | 0 | 1 | 0
E16 | Electrical Engineering Installation | Testing and commissioning | Testing and commissioning including liaison with Public Authority for Electricity and Water | Item | 1 | 0 | 0 | 1 | 0
BA | SUM FOR PAGE-53/68 | [5 empty] | 0 |  | 0
E17 | Electrical Engineering Installation | Cable duct note | UPVC cable duct with socket joint and laid in trench and encased in plain cement concrete with a minimum encasement thickness of 100 mm on all sides in running length with excavate trench in any materials and minimum 700 mm deep and including bedding and backfilling with excavated materials and disposal of surplus materials. | Item | 1 | 0 | 0 | 1 | 0
E18 | Electrical Engineering Installation | Cable duct | 160 mm diameter UPVC duct | M | 550 | 0 | 0 | 550 | 0
E19 | Electrical Engineering Installation | Cable duct | 110 mm diameter UPVC duct | M | 850 | 0 | 0 | 850 | 0
E20 | Electrical Engineering Installation | Sundries | Allow for builders work in connection with electrical installation including holes and chases and sleeves ducts and cable tray trucking panel backboards or formwork and supports and access panels and cover plates etc. | Item | 1 | 0 | 0 | 1 | 0
E21 | Electrical Engineering Installation | Sundries | Allow for incidental works such as co ordination with other engineering installations. | Item | 1 | 0 | 0 | 1 | 0
E22 | Electrical Engineering Installation | Sundries | Allow to identification labels and charts etc. | Item | 1 | 0 | 0 | 1 | 0
E23 | Electrical Engineering Installation | Sundries | Allow for testing and commissioning of complete electrical installation. | Item | 1 | 0 | 0 | 1 | 0
E24 | Electrical Engineering Installation | Sundries | Allow for documents As Installed drawings and Operation and Maintenance manuals. | Item | 1 | 0 | 0 | 1 | 0
BB | SUM FOR PAGE-54/68 | [5 empty] | 0 |  | 0
E25 | MAIN DISTRIBUTION BOARD Electrical Engineering Installation | Main Distribution Board | Main Distribution panel board in weather proof Stainless steel enclosure IP 65 including 2 nos 600A and 4 nos 400A and 1NOS spare100 A and 1 NOS spare 200A Incoming MCCB Breaker and 4nos 200A and 2nos spare 100 A Outgoing MCCB Breakers and supports and Busbar and earthing and cable glands and Ammeters and Voltmeters and internal wiring interconnection 1PH 3PH KWH series meters and labels as per approved MHEW drawings | NO | 6 | 14 | 84 |  |  | 6 | 84
E26 | MAIN DISTRIBUTION BOARD Electrical Engineering Installation | Cable | 4C and 240 mm2 UG cable from Feeder Pillar to MDB Panels | M | 500 | 0 | 0 |  | 0 | 0 | 0
E27 | MAIN DISTRIBUTION BOARD Electrical Engineering Installation | Manholes | 1000 and 1000 and 700 mm deep internal size electrical manhole RCC wall and rendering internally 75 mm PCC at bottom with 800 and 800 mm double seal heavy duty cast Ductile Iron EN 124 B400 cover and frame | No | 16 | 0 | 0 | 16 | 0
E28 | MAIN DISTRIBUTION BOARD Electrical Engineering Installation | Manholes | 600 and 600 and700 mm deep internal size electrical manhole and RCC wall and rendering internally 75 mm PCC at bottom with 600 and 600 mm double seal heavy duty cast iron cover and frame. | No | 40 | 0 | 0 | 40 | 0
BC | SUM FOR PAGE-55/68 | [5 empty] | 84 |  | 0
E29 | SUB MAIN DISTRIBUTION BOARD | Sub Main Distribution Board | Sub Main Distribution panel board in weather proof Stainless steel enclosure IP 65 including 1nos 200A MCCB and 2 NOS 100A MCCB Outgoing Breakers and supports and Busbar and earthing and cable glands and Ammeters and Voltmeters and internal wiring interconnection 1PH 3PH KWH series meters and labels as per approved MHEW drawings | No | 20 | 0 | 0 | 20 | 0
E30 | SUB MAIN DISTRIBUTION BOARD | Note | XLPE PVC SWA PVC copper cable with PVC copper earth continuity conductor including necessary conduit and trunking and cable tray and termination | Item | 1 | 0 | 0 | 1 | 0
E31 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB1 | M | 40 | 0 | 0 | 40 | 0
E32 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB2 | M | 20 | 0 | 0 | 20 | 0
E33 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB3 | M | 25 | 0 | 0 | 25 | 0
E34 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB4 | M | 35 | 0 | 0 | 35 | 0
E35 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB5 | M | 20 | 0 | 0 | 20 | 0
E36 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB6 | M | 25 | 0 | 0 | 25 | 0
E37 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB7 | M | 40 | 0 | 0 | 40 | 0
E38 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB8 | M | 20 | 0 | 0 | 20 | 0
BD | SUM FOR PAGE-56/68 | [5 empty] | 0 |  | 0
E39 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB9 | M | 20 | 0 | 0 | 20 | 0
E40 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB10 | M | 40 | 0 | 0 | 40 | 0
E41 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB11 | M | 10 | 0 | 0 | 10 | 0
E42 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB12 | M | 30 | 0 | 0 | 30 | 0
E43 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB13 | M | 40 | 0 | 0 | 40 | 0
E44 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB14 | M | 20 | 0 | 0 | 20 | 0
E45 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB15 | M | 20 | 0 | 0 | 20 | 0
E46 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB16 | M | 40 | 0 | 0 | 40 | 0
E47 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB17 | M | 40 | 0 | 0 | 40 | 0
E48 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB18 | M | 20 | 0 | 0 | 20 | 0
E49 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB19 | M | 25 | 0 | 0 | 25 | 0
BE | SUM FOR PAGE-57/68 | [5 empty] | 0 |  | 0
E50 | Electrical Engineering Installation | Cable | 4C and 70 mm� + 1C x 50 mm� ECC from MDB to SMDB20 | M | 45 | 0 | 0 | 45 | 0
E51 | Electrical Engineering Installation | Distribution Board | Distribution board including isolator and ELCB in separate enclosure and MCB RCD MCB as specified along with necessary supports earthing cable glands and internal wiring and interconnection and labels | Item | 1 | 0 | 0 | 1 | 0
E52 | Electrical Engineering Installation | Distribution Board | 100A TPN 12 way DBs | No | 20 | 3.15 | 63 | 20 | 63
E53 | Electrical Engineering Installation | Distribution Board | 100A TPN 6 way DBs | No | 20 | 4.2 | 84 | 20 | 84
E54 | Electrical Engineering Installation | Cable | XLPE PVC SWA PVC copper cable with PVC and copper earth continuity conductor including necessary conduit and trunking and cable tray and termination | Item | 1 | 0 | 0 | 1 | 0
E55 | Electrical Engineering Installation | Cable | 4C and 25 mm� + 1C and 16 mm� ECC from SMDBs to DB1 GF for 20 villas | M | 500 | 0.84 | 420 | 500 | 420
E56 | Electrical Engineering Installation | Cable | 4C and 25 mm� + 1C and 16 mm� ECC from SMDBs to DB1 GF for 21 villas | M | 500 | 0.84 | 420 | 500 | 420
E57 | Electrical Engineering Installation | Earthing Installation | Earthing system including 16 mm dia. high conductivity solid copper rod electrodes with drive head assemblies and Earthing clamps for earth pits Earthing of exposed pipe work sanitary fittings and equipment all as required including 300 and 300 and 400 mm deep internally earth pit and earth wires as per specification and drawings complete with 300 mm and 300 mm medium duty double seal cast iron cover and frame. | No | 30 | 140 | 4200 | 30 | 4200
BF | SUM FOR PAGE-58/68 | [5 empty] | 5187 |  | 5187
E58 | Electrical Engineering Installation | Sundries | Allow for builders work in connection with electrical installation including holes chases sleeves ducts cable tray trucking panel backboards or formwork supports access panels cover plates etc. | Item | 1 | 1260 | 1260 | 1 | 1260
E59 | Electrical Engineering Installation | Sundries | Allow for incidental works such as co ordination with other engineering installations. | Item | 1 | 945 | 945 | 1 | 945
E60 | Electrical Engineering Installation | Sundries | Allow to identification labels and charts etc. | Item | 1 | 1029 | 1029 | 1 | 1029
E61 | Electrical Engineering Installation | Sundries | Allow for testing and commissioning of complete electrical installation. | Item | 1 | 2100 | 2100 | 1 | 2100
E62 | Electrical Engineering Installation | Sundries | Allow for documents As installed drawings Operation and Maintenance manuals. | Item | 1 | 945 | 945 | 1 | 945
E63 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation Note | Supply and installd and connect test and commissioning of the following wiring devices including SS cover plate connect test of the conduits and cables and back box and junction box form distribution board from the following as required as shown on drawing and specification | Item | 1 | 0 | 0 | 1 | 0
E64 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 13A DP single switched socket outlet | No | 720 | 0.146 | 105.12 | 720 | 105.12
E65 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 13A DP twin switched socket outlet | No | 260 | 3 | 780 | 260 | 780
BG | SUM FOR PAGE-59/68 | [5 empty] | 7164.12 |  | 7164.12
E66 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 13A DP single gang weatherproof switch socket outlet | No | 280 | 0.975 | 273 | 280 | 273
E67 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 30A cooker socket | No | 20 | 1.05 | 21 | 20 | 21
E68 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 20A DP flux outlet for AC 1.5 ton | No | 120 | 0.875 | 105 | 120 | 105
E69 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 20A weatherproof DP flux outlet for WH | No | 120 | 1.05 | 126 | 120 | 126
E70 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 13 A unswitched fused spur unit outlet for EF | No | 120 | 1.05 | 126 | 120 | 126
E71 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 30A DP flux outlet for AC 2.5 and 3 ton | No | 40 | 1.05 | 42 | 40 | 42
E72 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 20A Dp switch for WH and AC | No | 220 | 1.05 | 231 | 220 | 231
E73 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 30A Dp switch for AC | No | 40 | 1.05 | 42 | 40 | 42
BH | SUM FOR PAGE-60/68 | [5 empty] | 966 |  | 966
E74 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 20A weatherproof TPN isolator for Booster pump | No | 20 | 0 | 0 | 20 | 0
E75 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Supply and install and connect test of the conduits and cables form distribution board from the following .Supply and install connect test and commissioning of the following wiring devices including SS cover plate connect test of the conduits and cables and back box and junction box form distribution board from the following as required as shown on drawing and specification. | Item | 1 | 0 | 0 | 1 | 0
E76 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Lighting switch 10A Double pole one way one gang | No | 220 | 0.37 | 81.4 | 220 | 81.4
E77 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Lighting switch 10A Double pole one way one gang whether proof | No | 20 | 0 | 0 | 20 | 0
E78 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Ditto one way two gang | No | 420 | 0.25 | 105 | 420 | 105
E79 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Ditto one way three gang | No | 220 | 0.115 | 25.3 | 220 | 25.3
E80 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Ditto two way one gang | No | 60 | 0.21 | 12.6 | 60 | 12.6
BI | SUM FOR PAGE-61/68 | [5 empty] | 224.3 |  | 224.3
E81 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Ditto two way two gang | No | 40 | 0 | 0 | 40 | 0
E82 | Electrical Engineering Installation | Lighting Fixture Note | Supply and install and connect test and commissioning of the following lighting fixtures and including lamps and electronic ballasts and control gear and wires and cables and all necessary accessories complete as specified and as shown on the drawings. | Item | 0 | 0 | 0 | 0 | 0
E83 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 40w led downlight | No | 720 | 1.75 | 1260 | 720 | 1260
E84 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 40w led downlight with whether proof IP 65 | No | 200 | 2.31 | 462 | 200 | 462
E85 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 40w led downlight with integral emergency conversion kit | No | 180 | 3.267 | 588.06 | 180 | 588.06
E86 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 25w led wall mounted light fixture | No | 120 | 0 | 0 | 120 | 0
E87 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 26w led wall mounted light fixture with whether proof | No | 200 | 0 | 0 | 200 | 0
E88 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 7w led mirror light | No | 180 | 0 | 0 | 180 | 0
BJ | SUM FOR PAGE-62/68 | [5 empty] | 2310.06 |  | 2310.06
E89 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 20w compound wall light with whether proof IP65 | No | 220 | 0 | 0 | 220 | 0
E90 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 40w fluorescent light fixture for car parking area | No | 20 | 0 | 0 | 20 | 0
E91 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Ceiling fan | No | 180 | 2.1 | 378 | 180 | 378
E92 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Chandelier | No | 40 | 4.2 | 168 | 40 | 168
E93 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Wall mounted exhaust fan | No | 120 | 2.1 | 252 | 120 | 252
GN1 | TV System Installation | Cable | Cable and conduit to TV point in concealed installation from satellite | No | 120 | 2.1 | 252 | 120 | 252
GN2 | TV System Installation | Outlet | Flush mounted TV Satellite outlet | No | 120 | 2.1 | 252 | 120 | 252
GN3 | TV System Installation | TV System Installation | Allow for co axial cable in concealed conduit from dish antenna to satellite switcher with all necessary accessories and trunking and conduits and trays and supports etc. | Item | 1 | 0 | 0 | 1 | 0
GN4 | Telephone System | Cable | Cable and conduits to telephone outlet points in concealed installation from telephone junction box to IP phone expansion module for reception | No | 120 | 2.45 | 294 | 120 |  | 120 | 294
GN5 | Telephone System | Outlet | Cat 6E telephone outlet | No | 120 | 2.45 | 294 | 120 |  | 120 | 294
GN6 | Telephone System | Junction box | Telephone junction box | No | 20 | 2.1 | 42 | 20 |  | 20 | 42
BK | SUM FOR PAGE-63/68 | [5 empty] | 1932 |  | 1302
GN7 | Telephone System | Excavation | Supply and laying 80 pair telephone cable including trench excavationand backfilling and ducts and bedding caution tape etc all as per site conditions | Item | 1 | 0 | 0 | 1 | 0 | 1 | 0
GN8 | Telephone System | Cables | 80 pair external grade telephone cable from mantel terminal box to main telephone junction box at main building Electrical room. | Item | 1 | 0 | 0 | 1 | 0 | 1 | 0
GN9 | Telephone System | Draw Pits | 450 and 450 and 500 mm deep internal size telephone draw pit RCC wall and rendering internally and 75 mm PCC at bottom with 450 and 450 mm medium duty ductile iron cover and frame. | Item | 1 | 0 | 0 | 1 | 0 | 1 | 0
GN10 | DATA SYSTEM | DATA SYSTEM | Supply and install and connect and test and commissioning of the following for the WiFi system including cables and trunking and accessories and as shown on specifications. | item | 1 | 0 | 0 | 1 | 0 | 1 | 0
GN11 | Structured Cabling system | Accessories | Wi Fi access units including all accessories and fittings | item | 1 | 472.5 | 472.5 |  | 0 | 1 | 472.5
GN12 | Structured Cabling system | Accessories | Any other works not specifically enumerated under the works above with implementation cost | Item | 1 | 1155 | 1155 |  | 0 | 1 | 1155
GN13 | Structured Cabling system | Cable | Cableconduits and accessories to RJ 45 Category 6A dual socket outlet | No | 120 | 11.025 | 1323 |  | 0 | 120 | 1323
GN14 | Structured Cabling system | Cable | Drop lead 3m long Category 6A | No | 160 | 8.4 | 1344 |  | 0 | 160 | 1344
GN15 | Structured Cabling system | Cable | Drop lead 6m long Category 6A | No | 160 | 8.4 | 1344 |  | 0 | 160 | 1344
GN16 | Structured Cabling system | patch panel | 16 Port Cat 6A Patch panel | No | 20 | 8.4 | 168 |  | 0 | 20 | 168
GN17 | Structured Cabling system | Structured Cabling system | 500mm single mode fiber LC SC Patch cords | No | 20 | 9.45 | 189 |  | 0 | 20 | 189
BL | SUM FOR PAGE-64/68 | [5 empty] | 5995.5
GN18 | Structured Cabling system | Accessories | Accessories and stacking kits and cable management and cable organizer and cable channels and supports all types of cords and pig tail connectors including termination etc complete | Item | 1 | 1050 | 1050 | 1 |  | 1 | 1050
GN19 | CCTV System | PTZ Camera | PTZ Vandal proof with weather proof Bullet type Day and Night vision CCTV IP camera Outdoor as specified. | No | 40 | 26.25 | 1050 | 40 |  | 40 | 1050
GN20 | CCTV System | pulling box | Allow for cable pulling boxes | Item | 1 | 1575 | 1575 | 1 |  | 1 | 1575
GN21 | CCTV System | cable | Cables and Trunking and Accessories | Item | 1 | 0 | 0 | 1
GN22 | Telephone and Structured Cabling and CCTV System | Sundries | Allow for builders work in connection with electrical installation including holes and chases and sleeves and ducts and cable tray trucking and panel backboards or formwork support and access panels and cover plates etc. | Item | 1 | 945 | 945 |  | 0 | 1 | 945
GN23 | Telephone and Structured Cabling and CCTV System | Sundries | Allow for incidental works such as co ordination with other engineering installations. | Item | 1 | 1260 | 1260 |  | 0 | 1 | 1260
GN24 | Telephone and Structured Cabling and CCTV System | Sundries | Allow to identification labels charts etc. | Item | 1 | 0 | 0 | 1 | 0 | 0 | 0
BM | SUM FOR PAGE-65/68 | [5 empty] | 5880 |  | 0 | 0
GN25 | Telephone and Structured Cabling and CCTV System | Sundries | Allow for testing and commissioning of complete electrical installation. | Item | 1 | 0 | 0 | 1 |  | 0 | 0
GN26 | Telephone and Structured Cabling and CCTV System | Sundries | Allow for documents As Installed drawings Operation and Maintenance manuals. | Item | 1 | 0 | 0 | 1 |  | 0 | 0
MEP 1 | MEP Works | The Contractor should read and quote as per the supply laying and all works are included and required approval commissioning as per contract standards should be under the Contractor scope of work including required charges also including DNP scope and guarantees for material. | Important Note | Item | 1 | 0 | 0 | 1
BN | SUM FOR PAGE-66/68 | [5 empty] | 0 |  | -
MEP 2 | MEP Works | The Contractor is adviced to complete the project as per the drawing boq and specification also need to complete if anything missing in the drawing but mentioned in the boqspecification and viceversa. Should the Tenderer fail to insert any item here it will be deemed that this lump sum price for the tender includes all items and no subsequent claim for any additional items will be entertained | Important Note | Item | 1 | 0 | 0 | 1
BO | SUM FOR PAGE-67/68 | [5 empty] | 0 |  | -
MEP 3 | MEP Works | The Contractor is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum tender price for this section of the works. Should the Tenderer fail to insert any item here it will be deemed that this lump sum price for the tender includes all items and no subsequent claim for any additional items will be entertained | Important Note | Item | 1 | 0 | 0 | 1
BP | SUM FOR PAGE-68/68 | [7 empty] | -
BP | TOTAL NEW HOUSING UNITS | [5 empty] | 1965370.94 |  | 1550778.4816 |  | 415316.2084 |  | 23100 | See Appendix A for details on Additional Works

## MSheet Of NHU (Plot 1 - 20) (hidden)
NEW HOUSING UNITS - 20 NOS
SI NO | DESCRIPTION | UOM | Nos | No.of Items | L | B | D | QTY | REMARKS
C3 | EARTH WORK
| Excavation PL | M³ | 1 | 1 | 318.17 |  | 2 | 636.34
| Total | M³ | [5 empty] | 636.34
C`9 | FOOTING PCC
Grid H-H
| F2 | M³ | 1 | 1 | 2.1 | 1.8 | 0.1 | 0.378
| F1 | M³ | 1 | 1 | 1.8 | 1.6 | 0.1 | 0.288
Grid G-G
| F1 | M³ | 1 | 1 | 1.8 | 1.6 | 0.1 | 0.288
Grid F-F
| F* | M³ | 2 | 1 | 1.2 | 1.2 | 0.1 | 0.288
| F2 | M³ | 1 | 1 | 2.1 | 1.8 | 0.1 | 0.378
| F1 | M³ | 1 | 1 | 1.8 | 1.6 | 0.1 | 0.288
Grid E-E
| F2 | M³ | 1 | 1 | 2.1 | 1.8 | 0.1 | 0.378
| F3 | M³ | 3 | 1 | 2.4 | 2.1 | 0.1 | 1.512
Grid D-D
| F2 | M³ | 1 | 1 | 2.1 | 1.8 | 0.1 | 0.378
| F3 | M³ | 2 | 1 | 2.4 | 2.1 | 0.1 | 1.008
Grid C-C
| F4 | M³ | 1 | 1 | 2.6 | 1.9 | 0.1 | 0.494
| F2 | M³ | 1 | 1 | 2.1 | 1.8 | 0.1 | 0.378
| F1 | M³ | 1 | 1 | 1.8 | 1.6 | 0.1 | 0.288
Grid B-B
| F2 | M³ | 1 | 1 | 2.1 | 1.8 | 0.1 | 0.378
| F4 | M³ | 1 | 1 | 2.6 | 1.9 | 0.1 | 0.494
| F3 | M³ | 1 | 1 | 2.4 | 2.1 | 0.1 | 0.504
Grid A-A
| F1 | M³ | 3 | 1 | 1.8 | 1.6 | 0.1 | 0.864
| F2 | M³ | 1 | 1 | 2.1 | 1.8 | 0.1 | 0.378
| Total | M³ | [5 empty] | 8.962
Block Work PCC
| Grid H-H | M³ | 1 | 1 | 6.2 | 0.4 | 0.1 | 0.248
| Grid G-G | M³ | 1 | 1 | 4.4 | 0.4 | 0.1 | 0.176
| Grid E-E | M³ | 1 | 1 | 2.25 | 0.4 | 0.1 | 0.09
| Grid D-D | M³ | 1 | 1 | 2.6 | 0.4 | 0.1 | 0.104
| Grid C-C | M³ | 1 | 1 | 1.35 | 0.4 | 0.1 | 0.054
| Grid A-A | M³ | 1 | 1 | 9.95 | 0.4 | 0.1 | 0.398
| Grid 1-1 | M³ | 1 | 1 | 1.6 | 0.4 | 0.1 | 0.064
| Grid 2-2 | M³ | 1 | 1 | 9.5 | 0.4 | 0.1 | 0.38
| Grid 3-3 | M³ | 1 | 1 | 1.35 | 0.4 | 0.1 | 0.054
| Grid 10-10 | M³ | 1 | 1 | 5.5 | 0.4 | 0.1 | 0.22
| Grid 11-11 | M³ | 1 | 1 | 3.35 | 0.4 | 0.1 | 0.134
| Grid 12-12 | M³ | 1 | 1 | 4.35 | 0.4 | 0.1 | 0.174
| Total | M³ | [5 empty] | 2.096
Plinth Beam PCC
| Grid F-F | M³ | 1 | 1 | 4.6 | 0.4 | 0.1 | 0.184
| Grid E'-F' | M³ | 1 | 1 | 5.7 | 0.4 | 0.1 | 0.228
| Grid E-E | M³ | 1 | 1 | 7.2 | 0.4 | 0.1 | 0.288
| Grid E'-D' | M³ | 1 | 1 | 4.7 | 0.4 | 0.1 | 0.188
| Grid D-D | M³ | 1 | 1 | 3.3 | 0.4 | 0.1 | 0.132
| Grid C-C | M³ | 1 | 1 | 5.4 | 0.4 | 0.1 | 0.216
| Grid B-B | M³ | 1 | 1 | 13.7 | 0.4 | 0.1 | 0.548
| Grid 2'-3' | M³ | 1 | 1 | 6.5 | 0.4 | 0.1 | 0.26
| Grid 4-4 | M³ | 1 | 1 | 8.7 | 0.4 | 0.1 | 0.348
| Grid 5-5 | M³ | 1 | 1 | 4.4 | 0.4 | 0.1 | 0.176
| Grid 6-6 | M³ | 1 | 1 | 3 | 0.4 | 0.1 | 0.12
| Grid 7-7 | M³ | 1 | 1 | 2.8 | 0.4 | 0.1 | 0.112
| Grid 8'-9' | M³ | 1 | 1 | 3.2 | 0.4 | 0.1 | 0.128
| Grid 9-9 | M³ | 1 | 1 | 4 | 0.4 | 0.1 | 0.16
| Grid 10-10 | M³ | 1 | 1 | 1.8 | 0.4 | 0.1 | 0.072
| Total | M³ | [5 empty] | 3.16
C9 | SUBTOTAL PCC
| FOOTING PCC | Nos | 20 |  | 8.96 |  |  | 179.2
| Block Work PCC | Nos | 20 |  | 2.1 |  |  | 42
| Plinth Beam PCC | Nos | 20 |  | 3.16 |  |  | 63.2
| SUBTOTAL PCC | [6 empty] | 284.4
C10 | FOOTING RCC
Grid H-H
| F2 | M³ | 1 | 1 | 1.9 | 1.6 | 0.5 | 1.52
| F1 | M³ | 1 | 1 | 1.6 | 1.4 | 0.5 | 1.12
| Grid G-G | [6 empty] | 0
| F1 | M³ | 1 | 1 | 1.6 | 1.4 | 0.5 | 1.12
| Grid F-F | [6 empty] | 0
| F* | M³ | 2 | 1 | 1 | 1 | 0.4 | 0.8
| F2 | M³ | 1 | 1 | 1.9 | 1.6 | 0.5 | 1.52
| F1 | M³ | 1 | 1 | 1.6 | 1.4 | 0.5 | 1.12
| Grid E-E | [6 empty] | 0
| F2 | M³ | 1 | 1 | 1.9 | 1.6 | 0.5 | 1.52
| F3 | M³ | 3 | 1 | 2.2 | 1.9 | 0.5 | 6.27
| Grid D-D | [6 empty] | 0
| F2 | M³ | 1 | 1 | 1.9 | 1.6 | 0.5 | 1.52
| F3 | M³ | 2 | 1 | 2.2 | 1.9 | 0.5 | 4.18
| Grid C-C | [6 empty] | 0
| F4 | M³ | 1 | 1 | 2.4 | 1.7 | 0.6 | 2.448
| F2 | M³ | 1 | 1 | 1.9 | 1.6 | 0.5 | 1.52
| F1 | M³ | 1 | 1 | 1.6 | 1.4 | 0.5 | 1.12
| Grid B-B | [6 empty] | 0
| F2 | M³ | 1 | 1 | 1.9 | 1.6 | 0.5 | 1.52
| F4 | M³ | 1 | 1 | 2.4 | 1.7 | 0.6 | 2.448
| F3 | M³ | 1 | 1 | 2.2 | 1.9 | 0.5 | 2.09
| Grid A-A | [6 empty] | 0
| F1 | M³ | 3 | 1 | 1.6 | 1.4 | 0.5 | 3.36
| F2 | M³ | 1 | 1 | 1.9 | 1.6 | 0.5 | 1.52
| Total | M³ | [5 empty] | 36.716
C13 | RCC - Short Column
Grid H-H
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 1.4 | 0.14
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 2.15 | 0.34
| Grid G-G |  | - |  |  |  |  | -
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 1.4 | 0.14
| Grid F-F |  | - |  |  |  |  | -
| c* | M³ | 2 | 1 | 0.3 | 0.2 | 1.5 | 0.18
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.15 | 0.258
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.15 | 0.215
| Grid E-E |  | - |  |  |  |  | -
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 1.4 | 0.224
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.15 | 0.258
| C3 | M³ | 2 | 1 | 0.7 | 0.2 | 2.15 | 0.602
| Grid D-D |  | - |  |  |  |  | -
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 2.15 | 0.344
| C2 | M³ | 2 | 1 | 0.6 | 0.2 | 2.15 | 0.516
| Grid C-C |  | - |  |  |  |  | -
| C2 | M³ | 2 | 1 | 0.6 | 0.2 | 2.05 | 0.492
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.15 | 0.215
| Grid B-B |  | - |  |  |  |  | -
| C2 | M³ | 2 | 1 | 0.6 | 0.2 | 2.15 | 0.516
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 2.05 | 0.287
| Grid A-A |  | - |  |  |  |  | -
| C1 | M³ | 2 | 1 | 0.5 | 0.2 | 2.15 | 0.43
| C2 | M³ | 2 | 1 | 0.6 | 0.2 | 2.15 | 0.516
| Total | M³ | [5 empty] | 5.68
C17 | SUBSTRUCTURAL BLOCK WORK
| PB4 Wall | M² | 1 | 1 | 24.1 | 2.05 |  | 49.405
| PB6 Wall | M² | 1 | 1 | 7.3 | 1.95 |  | 14.235
| PB3 Wall |  | 1 | 1 | 50.8 | 2.1 |  | 106.68
| PB2 Wall |  | 1 | 1 | 2.5 | 2.15 |  | 5.375
| Stair wall (PB3) | M² | 1 | 1 | 11.8 | 1.9 |  | 22.42
Column Deductions
Grid H-H
| C1 | M² | 1 | -1 | 0.5 |  | 1.5 | -0.75
| C4 | M² | 1 | -1 | 0.8 |  | 1.5 | -1.2
| Grid G-G | M² |  |  | - |  | - | -
| C1 | M² | 1 | -1 | 0.5 |  | 1.5 | -0.75
| Grid F-F | M² |  |  | - |  | - | -
| c* | M² | 1 | -1 | 0.3 |  | 1.6 | -0.48
| Grid E-E | M² |  |  | - |  | - | -
| C4 | M² | 1 | -1 | 0.8 |  | 1.5 | -1.2
| C2 | M² | 1 | -1 | 0.6 |  | 1.5 | -0.9
| C3 | M² | 1 | -1 | 0.7 |  | 1.5 | -1.05
| Grid D-D | M² |  |  | - |  | - | -
| C4 | M² | 1 | -1 | 0.8 |  | 1.5 | -1.2
| C2 | M² | 1 | -1 | 0.6 |  | 1.5 | -0.9
| Grid C-C | M² |  |  | - |  | - | -
| C2 | M² | 1 | -1 | 0.6 |  | 1.4 | -0.84
| C1 | M² | 1 | -1 | 0.5 |  | 1.5 | -0.75
| Grid B-B | M² |  |  | - |  | - | -
| C2 | M² | 1 | -1 | 0.6 |  | 1.5 | -0.9
| Grid A-A | M² |  |  | - |  | - | -
| C1 | M² | 2 | -1 | 0.5 |  | 1.5 | -1.5
| C2 | M² | 2 | -1 | 0.6 |  | 1.5 | -1.8
Footing Deductions
Grid H-H
| F1 | M² | 1 | -1 | 2.2 |  | 0.5 | -1.1
| F2 | M² | 1 | -1 | 1.8 |  | 0.5 | -0.9
| F1 | M² | 1 | -1 | 1.8 |  | 0.5 | -0.9
| Grid 11 | [6 empty] | -
| F1 | M² | 1 | -1 | 1.4 |  | 0.5 | -0.7
| F3 | M² | 1 | -1 | 2.5 |  | 0.5 | -1.25
| Grid 10 | [6 empty] | -
| F2 | M² | 1 | -1 | 1.55 |  | 0.5 | -0.775
| Grid 12 | [6 empty] | -
| F1 | M² | 1 | -1 | 1.7 |  | 0.5 | -0.85
| F1 | M² | 1 | -1 | 1.65 |  | 0.5 | -0.825
| Grid A-A | M² | [5 empty] | -
| F1 | M² | 1 | -1 | 1.6 |  | 0.5 | -0.8
| F2 | M² | 1 | -1 | 1.9 |  | 0.5 | -0.95
| F1 | M² | 1 | -1 | 1.65 |  | 0.5 | -0.825
| Grid 12 | [6 empty] | -
| F2 | M² | 1 | -3 | 1.6 |  | 0.5 | -2.4
| F2 | M² | 1 | -2 | 0.55 |  | 0.5 | -0.55
| F* | M² | 1 | -1 | 1.6 |  | 0.5 | -0.8
| Total | M³ | [5 empty] | 170.27
C14 | Polythene Sheet protection Work - Footing PCC
Grid H-H
| F2 | M³ | 1 | 1 | 2.1 | 1.8 |  | 3.78
| F1 | M³ | 1 | 1 | 1.8 | 1.6 |  | 2.88
Grid G-G
| F1 | M³ | 1 | 1 | 1.8 | 1.6 |  | 2.88
Grid F-F
| F* | M³ | 2 | 1 | 1.2 | 1.2 |  | 2.88
| F2 | M³ | 1 | 1 | 2.1 | 1.8 |  | 3.78
| F1 | M³ | 1 | 1 | 1.8 | 1.6 |  | 2.88
Grid E-E
| F2 | M³ | 1 | 1 | 2.1 | 1.8 |  | 3.78
| F3 | M³ | 3 | 1 | 2.4 | 2.1 |  | 15.12
Grid D-D
| F2 | M³ | 1 | 1 | 2.1 | 1.8 |  | 3.78
| F3 | M³ | 2 | 1 | 2.4 | 2.1 |  | 10.08
Grid C-C
| F4 | M³ | 1 | 1 | 2.6 | 1.9 |  | 4.94
| F2 | M³ | 1 | 1 | 2.1 | 1.8 |  | 3.78
| F1 | M³ | 1 | 1 | 1.8 | 1.6 |  | 2.88
Grid B-B
| F2 | M³ | 1 | 1 | 2.1 | 1.8 |  | 3.78
| F4 | M³ | 1 | 1 | 2.6 | 1.9 |  | 4.94
| F3 | M³ | 1 | 1 | 2.4 | 2.1 |  | 5.04
Grid A-A
| F1 | M³ | 3 | 1 | 1.8 | 1.6 |  | 8.64
| F2 | M³ | 1 | 1 | 2.1 | 1.8 |  | 3.78
| Total | M³ | [5 empty] | 89.62
Polythene Sheet protection Work - Plinth Beam PCC
| Grid F-F | M³ | 1 | 1 | 4.6 | 0.4 |  | 1.84
| Grid E'-F' | M³ | 1 | 1 | 5.7 | 0.4 |  | 2.28
| Grid E-E | M³ | 1 | 1 | 7.2 | 0.4 |  | 2.88
| Grid E'-D' | M³ | 1 | 1 | 4.7 | 0.4 |  | 1.88
| Grid D-D | M³ | 1 | 1 | 3.3 | 0.4 |  | 1.32
| Grid C-C | M³ | 1 | 1 | 5.4 | 0.4 |  | 2.16
| Grid B-B | M³ | 1 | 1 | 13.7 | 0.4 |  | 5.48
| Grid 2'-3' | M³ | 1 | 1 | 6.5 | 0.4 |  | 2.6
| Grid 4-4 | M³ | 1 | 1 | 8.7 | 0.4 |  | 3.48
| Grid 5-5 | M³ | 1 | 1 | 4.4 | 0.4 |  | 1.76
| Grid 6-6 | M³ | 1 | 1 | 3 | 0.4 |  | 1.2
| Grid 7-7 | M³ | 1 | 1 | 2.8 | 0.4 |  | 1.12
| Grid 8'-9' | M³ | 1 | 1 | 3.2 | 0.4 |  | 1.28
| Grid 9-9 | M³ | 1 | 1 | 4 | 0.4 |  | 1.6
| Grid 10-10 | M³ | 1 | 1 | 1.8 | 0.4 |  | 0.72
| Total | M³ | [5 empty] | 31.6
C14 | Polythene sheet Protection Work - Grade slab
| Entance Slab | M² | 1 | 1 | 1.7 | 2.6 |  | 4.42
| Majilis | M² | 1 | 1 | 5.7 | 4 |  | 22.8
| Salah | M² | 1 | 1 | 7.7 | 4.5 |  | 34.65
| Majilis Toilet 1 | M² | 1 | 1 | 2.2 | 1.7 |  | 3.74
| Majilis Wash 1 | M² | 1 | 1 | 1.6 | 1.7 |  | 2.72
| Lobby | M² | 1 | 1 | 3 | 3 |  | 9
| Passage from Lobby to Wash 1 | M² | 1 | 1 | 1.7 | 1.5 |  | 2.55
| Lobby Toilet | M² | 1 | 1 | 2.7 | 1.7 |  | 4.59
| Lobby Wash area | M² | 1 | 1 | 1.8 | 1.7 |  | 3.06
| Corridor | M² | 1 | 1 | 3 | 1.5 |  | 4.5
| Corridor | M² | 1 | 1 | 6.4 | 1.5 |  | 9.6
| Corridor | M² | 1 | 1 | 1.2 | 1.8 |  | 2.16
| Store | M² | 1 | 1 | 4 | 4.5 |  | 18
| Bedroom 1 Dressing | M² | 1 | 1 | 1.8 | 2.1 |  | 3.78
| Bedroom 1 Toilet | M² | 1 | 1 | 1.8 | 2.1 |  | 3.78
| Bedroom 1 | M² | 1 | 1 | 4.2 | 4.4 |  | 18.48
| Bedroom 2 | M² | 1 | 1 | 4 | 4.4 |  | 17.6
| Bedroom 3 | M² | 1 | 1 | 4.3 | 4.1 |  | 17.63
| Bedroom 3 Toilet | M² | 1 | 1 | 2.9 | 1.8 |  | 5.22
| Kitchen | M² | 1 | 1 | 4 | 4.1 |  | 16.4
| Kitchen Store | M² | 1 | 1 | 2 | 2.8 |  | 5.6
| Salalah | M² | 1 | 1 | 7.7 | 4.5 |  | 34.65
| Salalah Wash | M² | 1 | 1 | 1.8 | 1.7 |  | 3.06
| Salalah Toilet | M² | 1 | 1 | 2.7 | 1.7 |  | 4.59
| Total | M² | [5 empty] | 252.58
Polythene sheet Protection Work - Sub. Block Work PCC
| Grid H-H | M³ | 1 | 1 | 6.2 | 0.4 |  | 2.48
| Grid G-G | M³ | 1 | 1 | 4.4 | 0.4 |  | 1.76
| Grid E-E | M³ | 1 | 1 | 2.25 | 0.4 |  | 0.9
| Grid D-D | M³ | 1 | 1 | 2.6 | 0.4 |  | 1.04
| Grid C-C | M³ | 1 | 1 | 1.35 | 0.4 |  | 0.54
| Grid A-A | M³ | 1 | 1 | 9.95 | 0.4 |  | 3.98
| Grid 1-1 | M³ | 1 | 1 | 1.6 | 0.4 |  | 0.64
| Grid 2-2 | M³ | 1 | 1 | 9.5 | 0.4 |  | 3.8
| Grid 3-3 | M³ | 1 | 1 | 1.35 | 0.4 |  | 0.54
| Grid 10-10 | M³ | 1 | 1 | 5.5 | 0.4 |  | 2.2
| Grid 11-11 | M³ | 1 | 1 | 3.35 | 0.4 |  | 1.34
| Grid 12-12 | M³ | 1 | 1 | 4.35 | 0.4 |  | 1.74
| Total | M³ | [5 empty] | 20.96
C9 | SUBTOTAL - Polythene sheet Protection Work
| Polythene Sheet protection Work - Footing PCC | Nos | 20 |  |  |  | 89.62 | 1792.4
| Polythene Sheet protection Work - Plinth Beam PCC | Nos | 20 |  |  |  | 31.6 | 632
| Polythene sheet Protection Work - Grade slab | Nos | 15 |  |  |  | 252.58 | 3788.7
| Polythene sheet Protection Work - Sub. Block Work PCC | Nos | 20 |  | 20.96 |  |  | 419.2
| SUBTOTAL - Polythene sheet Protection Work | [6 empty] | 6632.3
C18 | BITUMEN WATERPROOFING WORK- Sub-Block Work
| Sub-Block Work Area | M² | 1 | 2 |  |  | 170.27 | 340.54
Footings Sides
Grid H-H
| F2 | M² | 1 | 1 | 1.9 | 1.6 | 0.5 | 3.5
| F1 | M² | 1 | 1 | 1.6 | 1.4 | 0.5 | 3
| Grid G-G | M² | [5 empty] | -
| F1 | M² | 1 | 1 | 1.6 | 1.4 | 0.5 | 3
| Grid F-F | M² | [5 empty] | -
| F* | M² | 2 | 1 | 1 | 1 | 0.4 | 3.2
| F2 | M² | 1 | 1 | 1.9 | 1.6 | 0.5 | 3.5
| F1 | M² | 1 | 1 | 1.6 | 1.4 | 0.5 | 3
| Grid E-E | M² | [5 empty] | -
| F2 | M² | 1 | 1 | 1.9 | 1.6 | 0.5 | 3.5
| F3 | M² | 3 | 1 | 2.2 | 1.9 | 0.5 | 12.3
| Grid D-D | M² | [5 empty] | -
| F2 | M² | 1 | 1 | 1.9 | 1.6 | 0.5 | 3.5
| F3 | M² | 2 | 1 | 2.2 | 1.9 | 0.5 | 8.2
| Grid C-C | M² | [5 empty] | -
| F4 | M² | 1 | 1 | 2.4 | 1.7 | 0.6 | 4.92
| F2 | M² | 1 | 1 | 1.9 | 1.6 | 0.5 | 3.5
| F1 | M² | 1 | 1 | 1.6 | 1.4 | 0.5 | 3
| Grid B-B | M² | [5 empty] | -
| F2 | M² | 1 | 1 | 1.9 | 1.6 | 0.5 | 3.5
| F4 | M² | 1 | 1 | 2.4 | 1.7 | 0.6 | 4.92
| F3 | M² | 1 | 1 | 2.2 | 1.9 | 0.5 | 4.1
| Grid A-A | M² | [5 empty] | -
| F1 | M² | 3 | 1 | 1.6 | 1.4 | 0.5 | 9
| F2 | M² | 1 | 1 | 1.9 | 1.6 | 0.5 | 3.5
Footings Top
Grid H-H
| F2 | M² | 1 | 1 | 1.9 | 1.6 |  | 3.04
| F1 | M² | 1 | 1 | 1.6 | 1.4 |  | 2.24
| Grid G-G | M² | [5 empty] | -
| F1 | M² | 1 | 1 | 1.6 | 1.4 |  | 2.24
| Grid F-F | M² | [5 empty] | -
| F* | M² | 2 | 1 | 1 | 1 |  | 2
| F2 | M² | 1 | 1 | 1.9 | 1.6 |  | 3.04
| F1 | M² | 1 | 1 | 1.6 | 1.4 |  | 2.24
| Grid E-E | M² | [5 empty] | -
| F2 | M² | 1 | 1 | 1.9 | 1.6 |  | 3.04
| F3 | M² | 3 | 1 | 2.2 | 1.9 |  | 12.54
| Grid D-D | M² | [5 empty] | -
| F2 | M² | 1 | 1 | 1.9 | 1.6 |  | 3.04
| F3 | M² | 2 | 1 | 2.2 | 1.9 |  | 8.36
| Grid C-C | M² | [5 empty] | -
| F4 | M² | 1 | 1 | 2.4 | 1.7 |  | 4.08
| F2 | M² | 1 | 1 | 1.9 | 1.6 |  | 3.04
| F1 | M² | 1 | 1 | 1.6 | 1.4 |  | 2.24
| Grid B-B | M² | [5 empty] | -
| F2 | M² | 1 | 1 | 1.9 | 1.6 |  | 3.04
| F4 | M² | 1 | 1 | 2.4 | 1.7 |  | 4.08
| F3 | M² | 1 | 1 | 2.2 | 1.9 |  | 4.18
| Grid A-A | M² | [5 empty] | -
| F1 | M² | 3 | 1 | 1.6 | 1.4 |  | 6.72
| F2 | M² | 1 | 1 | 1.9 | 1.6 |  | 3.04
Column Deduction
Grid H-H
| C1 | M² | 1 | -1 | 0.5 | 0.2 |  | -0.1
| C4 | M² | 1 | -1 | 0.8 | 0.2 |  | -0.16
| Grid G-G | M² | - | -1 |  |  |  | -
| C1 | M² | 1 | -1 | 0.5 | 0.2 |  | -0.1
| Grid F-F | M² | - | -1 |  |  |  | -
| c* | M² | 2 | -1 | 0.3 | 0.2 |  | -0.12
| C2 | M² | 1 | -1 | 0.6 | 0.2 |  | -0.12
| C1 | M² | 1 | -1 | 0.5 | 0.2 |  | -0.1
| Grid E-E | M² | - | -1 |  |  |  | -
| C4 | M² | 1 | -1 | 0.8 | 0.2 |  | -0.16
| C2 | M² | 1 | -1 | 0.6 | 0.2 |  | -0.12
| C3 | M² | 2 | -1 | 0.7 | 0.2 |  | -0.28
| Grid D-D | M² | - | -1 |  |  |  | -
| C4 | M² | 1 | -1 | 0.8 | 0.2 |  | -0.16
| C2 | M² | 2 | -1 | 0.6 | 0.2 |  | -0.24
| Grid C-C | M² | - | -1 |  |  |  | -
| C2 | M² | 2 | -1 | 0.6 | 0.2 |  | -0.24
| C1 | M² | 1 | -1 | 0.5 | 0.2 |  | -0.1
| Grid B-B | M² | - | -1 |  |  |  | -
| C2 | M² | 2 | -1 | 0.6 | 0.2 |  | -0.24
| C3 | M² | 1 | -1 | 0.7 | 0.2 |  | -0.14
| Grid A-A | M² | - | -1 |  |  |  | -
| C1 | M² | 2 | -1 | 0.5 | 0.2 |  | -0.2
| C2 | M² | 2 | -1 | 0.6 | 0.2 |  | -0.24
Footings Top - Block work area deduction
Grid H-H
| F2 | M² | 1 | -1 | 1 | 0.2 |  | -0.2
| F1 | M² | 1 | -1 | 1.15 | 0.2 |  | -0.23
| Grid G-G | M² | [5 empty] | -
| F1 | M² | 1 | -1 | 1.4 | 0.2 |  | -0.28
| Grid F-F | M² | [5 empty] | -
| F* | M² | 1 | -1 | 0.7 | 0.2 |  | -0.14
| F1 | M² | 1 | -1 | 1.4 | 0.2 |  | -0.28
| Grid E-E | M² | [5 empty] | -
| F2 | M² | 1 | -1 | 1.4 | 0.2 |  | -0.28
| F3 | M² | 1 | -1 | 1.65 | 0.2 |  | -0.33
| F3 | M² | 1 | -1 | 1.8 | 0.2 |  | -0.36
| Grid D-D | M² | [5 empty] | -
| F2 | M² | 1 | -1 | 1.25 | 0.2 |  | -0.25
| F3 | M² | 1 | -1 | 1.65 | 0.2 |  | -0.33
| Grid C-C | M² | [5 empty] | -
| F2 | M² | 1 | -1 | 1.35 | 0.2 |  | -0.27
| F1 | M² | 1 | -1 | 1.3 | 0.2 |  | -0.26
| Grid B-B | M² | [5 empty] | -
| F2 | M² | 1 | -1 | 1.4 | 0.2 |  | -0.28
| Grid A-A | M² | [5 empty] | -
| F1 | M² | 1 | -1 | 1.15 | 0.2 |  | -0.23
| F1 | M² | 1 | -1 | 1 | 0.2 |  | -0.2
| F1 | M² | 1 | -1 | 1.15 | 0.2 |  | -0.23
| F2 | M² | 1 | -1 | 1.3 | 0.2 |  | -0.26
Column Sides
Grid H-H
| C1 | M² | 1 | 1 | 0.5 | 0.2 | 1.5 | 2.1
| C4 | M² | 1 | 1 | 0.8 | 0.2 | 1.5 | 3
| Grid G-G | M² | - |  |  |  |  | -
| C1 | M² | 1 | 1 | 0.5 | 0.2 | 1.5 | 2.1
| Grid F-F | M² | - |  |  |  |  | -
| c* | M² | 2 | 1 | 0.3 | 0.2 | 1.1 | 2.2
| C2 | M² | 1 | 1 | 0.6 | 0.2 | 1.5 | 2.4
| C1 | M² | 1 | 1 | 0.5 | 0.2 | 1.5 | 2.1
| Grid E-E | M² | - |  |  |  |  | -
| C4 | M² | 1 | 1 | 0.8 | 0.2 | 1.1 | 2.2
| C2 | M² | 1 | 1 | 0.6 | 0.2 | 1.5 | 2.4
| C3 | M² | 2 | 1 | 0.7 | 0.2 | 1.5 | 5.4
| Grid D-D | M² | - |  |  |  |  | -
| C4 | M² | 1 | 1 | 0.8 | 0.2 | 1.1 | 2.2
| C2 | M² | 2 | 1 | 0.6 | 0.2 | 1.5 | 4.8
| Grid C-C | M² | - |  |  |  |  | -
| C2 | M² | 2 | 1 | 0.6 | 0.2 | 1.4 | 4.48
| C1 | M² | 1 | 1 | 0.5 | 0.2 | 1.5 | 2.1
| Grid B-B | M² | - |  |  |  |  | -
| C2 | M² | 2 | 1 | 0.6 | 0.2 | 1.5 | 4.8
| C3 | M² | 1 | 1 | 0.7 | 0.2 | 1.4 | 2.52
| Grid A-A | M² | - |  |  |  |  | -
| C1 | M² | 2 | 1 | 0.5 | 0.2 | 1.5 | 4.2
| C2 | M² | 2 | 1 | 0.6 | 0.2 | 1.5 | 4.8
Column Sides Deduction
Grid H-H
| C1 | M² | 16 | -2 |  | 0.2 | 1.5 | -19.2
| Total | M² | [5 empty] | 523.25
C18 | BITUMEN WATERPROOFING WORK- Plinth Beam
| PB1 | M³ | 2 | 1 | 19.1 |  | 0.4 | 15.28
| PB2 | M³ | 2 | 1 | 38.6 |  | 0.5 | 38.6
| PB3 | M³ | 2 | 1 | 69.6 |  | 0.55 | 76.56
| PB4 | M³ | 2 | 1 | 30.1 |  | 0.6 | 36.12
| PB5 | M³ | 2 | 1 | 17.4 |  | 0.6 | 20.88
| PB6 | M³ | 2 | 1 | 14.7 |  | 0.7 | 20.58
| PB7 | M³ | 2 | 1 | 10.2 |  | 0.7 | 14.28
Beam Out side deduction
| PB6 | M³ | -1 | 1 | 7.3 |  | 0.7 | -5.11
| PB4 | M³ | -1 | 1 | 16.8 |  | 0.6 | -10.08
| PB3 | M³ | -1 | 1 | 36.3 |  | 0.55 | -19.965
| Total | M² | [5 empty] | 187.145
C18 | SUBTOTAL BITUMEN WATERPROOFING
| BITUMEN WATERPROOFING WORK- Sub-Block Work | Nos | 20 |  |  |  | 523.25 | 10465
| BITUMEN WATERPROOFING WORK- Plinth Beam | Nos | 20 |  |  |  | 187.15 | 3743
| SUBTOTAL BITUMEN WATERPROOFING | [6 empty] | 14208
C6 | Foundation Back Filling
| Excavation PL | M³ | 1 | 1 | 318.17 |  | 2 | 636.34
| Deduction Of Footing PCC | M³ | -1 | 1 |  |  | 8.96 | -8.96
| Deduction Of Footing RCC | M³ | -1 | 1 | 36.72 |  |  | -36.72
| Deduction Of Column RCC | M³ | -1 | 1 | 5.68 |  |  | -5.68
| Deduction Of Block work | M³ | -1 | 1 | 170.27 |  | 0.2 | -34.05
| Total | M³ | [5 empty] | 550.93
C11 | Plinth Beam RCC
| PB1 | M³ | 1 | 1 | 19.1 | 0.2 | 0.4 | 1.53
| PB2 | M³ | 1 | 1 | 38.6 | 0.2 | 0.5 | 3.86
| PB3 | M³ | 1 | 1 | 69.6 | 0.2 | 0.55 | 7.66
| PB4 | M³ | 1 | 1 | 30.1 | 0.2 | 0.6 | 3.61
| PB5 | M³ | 1 | 1 | 17.4 | 0.2 | 0.6 | 2.09
| PB6 | M³ | 1 | 1 | 14.7 | 0.2 | 0.7 | 2.06
| PB7 | M³ | 1 | 1 | 10.2 | 0.2 | 0.7 | 1.43
22.23
C8 | Anti Termite Treatment
| Entance Slab | M² | 1 | 1 | 1.7 | 2.6 |  | 4.42
| Majilis Slab | M² | 1 | 1 | 5.7 | 4 |  | 22.8
| Salah Slab | M² | 1 | 1 | 7.7 | 4.5 |  | 34.65
| Majilis Toilet 1 Slab | M² | 1 | 1 | 2.2 | 1.7 |  | 3.74
| Majilis Wash 1 Slab | M² | 1 | 1 | 1.6 | 1.7 |  | 2.72
| Lobby Slab | M² | 1 | 1 | 3 | 3 |  | 9
| Passage from Lobby to Wash 1 Slab | M² | 1 | 1 | 1.7 | 1.5 |  | 2.55
| Lobby Toilet Slab | M² | 1 | 1 | 2.7 | 1.7 |  | 4.59
| Lobby Wash area Slab | M² | 1 | 1 | 1.8 | 1.7 |  | 3.06
| Corridor Slab | M² | 1 | 1 | 3 | 1.5 |  | 4.5
| Corridor Slab | M² | 1 | 1 | 6.4 | 1.5 |  | 9.6
| Corridor Slab | M² | 1 | 1 | 1.2 | 1.8 |  | 2.16
| Store Slab | M² | 1 | 1 | 4 | 4.5 |  | 18
| Bedroom 1 Dressing Slab | M² | 1 | 1 | 1.8 | 2.1 |  | 3.78
| Bedroom 1 Toilet Slab | M² | 1 | 1 | 1.8 | 2.1 |  | 3.78
| Bedroom 1 Slab | M² | 1 | 1 | 4.2 | 4.4 |  | 18.48
| Bedroom 2 Slab | M² | 1 | 1 | 4 | 4.4 |  | 17.6
| Bedroom 3 Slab | M² | 1 | 1 | 4.3 | 4.1 |  | 17.63
| Bedroom 3 Toilet Slab | M² | 1 | 1 | 2.9 | 1.8 |  | 5.22
| Kitchen Slab | M² | 1 | 1 | 4 | 4.1 |  | 16.4
| Kitchen Store Slab | M² | 1 | 1 | 2 | 2.8 |  | 5.6
| Salalah Slab | M² | 1 | 1 | 7.7 | 4.5 |  | 34.65
| Salalah Wash Slab | M² | 1 | 1 | 1.8 | 1.7 |  | 3.06
| Salalah Toilet Slab | M² | 1 | 1 | 2.7 | 1.7 |  | 4.59
| RAMP Slab | M² | 1 | 1 | 5.3 | 1.5 |  | 7.95
| Total | M² | [5 empty] | 260.53
C12 | Grade Slab RCC
| Entance Slab | M³ | 1 | 1 | 1.7 | 2.6 | 0.12 | 0.53
| Majilis | M³ | 1 | 1 | 5.7 | 4 | 0.12 | 2.74
| Salah | M³ | 1 | 1 | 7.7 | 4.5 | 0.12 | 4.16
| Majilis Toilet 1 | M³ | 1 | 1 | 2.2 | 1.7 | 0.12 | 0.45
| Majilis Wash 1 | M³ | 1 | 1 | 1.6 | 1.7 | 0.12 | 0.33
| Lobby | M³ | 1 | 1 | 3 | 3 | 0.12 | 1.08
| Passage from Lobby to Wash 1 | M³ | 1 | 1 | 1.7 | 1.5 | 0.12 | 0.31
| Lobby Toilet | M³ | 1 | 1 | 2.7 | 1.7 | 0.12 | 0.55
| Lobby Wash area | M³ | 1 | 1 | 1.8 | 1.7 | 0.12 | 0.37
| Corridor | M³ | 1 | 1 | 3 | 1.5 | 0.12 | 0.54
| Corridor | M³ | 1 | 1 | 6.4 | 1.5 | 0.12 | 1.15
| Corridor | M³ | 1 | 1 | 1.2 | 1.8 | 0.12 | 0.26
| Store | M³ | 1 | 1 | 4 | 4.5 | 0.12 | 2.16
| Bedroom 1 Dressing | M³ | 1 | 1 | 1.8 | 2.1 | 0.12 | 0.45
| Bedroom 1 Toilet | M³ | 1 | 1 | 1.8 | 2.1 | 0.12 | 0.45
| Bedroom 1 | M³ | 1 | 1 | 4.2 | 4.4 | 0.12 | 2.22
| Bedroom 2 | M³ | 1 | 1 | 4 | 4.4 | 0.12 | 2.11
| Bedroom 3 | M³ | 1 | 1 | 4.3 | 4.1 | 0.12 | 2.12
| Bedroom 3 Toilet | M³ | 1 | 1 | 2.9 | 1.8 | 0.12 | 0.63
| Kitchen | M³ | 1 | 1 | 4 | 4.1 | 0.12 | 1.97
| Kitchen Store | M³ | 1 | 1 | 2 | 2.8 | 0.12 | 0.67
| Salalah | M³ | 1 | 1 | 7.7 | 4.5 | 0.12 | 4.16
| Salalah Wash | M³ | 1 | 1 | 1.8 | 1.7 | 0.12 | 0.37
| Salalah Toilet | M³ | 1 | 1 | 2.7 | 1.7 | 0.12 | 0.55
| Total | M³ | [5 empty] | 30.31
C25 | RAMP RCC
| RAMP | M³ | 1 | 1 | 4.95 | 1.5 | 0.12 | 0.891
| Total | M³ | [5 empty] | 0.891
C23 | GF Column RCC
Grid H-H
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.6 | 0.26
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 3.3 | 0.528
| Grid G-G |  | - |  |  |  |  | -
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 1.86 | 0.186
| Grid F-F |  | - |  |  |  |  | -
| c* | M³ | 2 | 1 | 0.3 | 0.2 | 2.5 | 0.3
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.75 | 0.33
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.75 | 0.275
| Grid E-E |  | - |  |  |  |  | -
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 2.6 | 0.416
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.6 | 0.312
| C3 | M³ | 2 | 1 | 0.7 | 0.2 | 2.6 | 0.728
| Grid D-D |  | - |  |  |  |  | -
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 2.6 | 0.416
| C2 | M³ | 2 | 1 | 0.6 | 0.2 | 2.75 | 0.66
| Grid C-C |  | - |  |  |  |  | -
| C2 | M³ | 2 | 1 | 0.6 | 0.2 | 2.7 | 0.648
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.75 | 0.275
| Grid B-B |  | - |  |  |  |  | -
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.7 | 0.324
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.7 | 0.324
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 2.7 | 0.378
| Grid A-A |  | - |  |  |  |  | -
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.6 | 0.26
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.6 | 0.312
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.6 | 0.26
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.6 | 0.312
| Total | M³ | [5 empty] | 7.504
C23 | FF Column RCC
| Grid E-E |  | - |  |  |  |  | -
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 2.6 | 0.416
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.6 | 0.312
| Grid D-D |  | - |  |  |  |  | -
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 2.6 | 0.416
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.75 | 0.33
| Grid B-B |  | - |  |  |  |  | -
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.7 | 0.324
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 2.7 | 0.378
| Grid A-A |  | - |  |  |  |  | -
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.6 | 0.26
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.6 | 0.312
| Total | M³ | [5 empty] | 2.748
C23 | GF Column RCC Total | M³ | 17 |  | 7.5 |  |  | 127.5
C23 | FF Column RCC Total | M³ | 8 |  | 2.75 |  |  | 22
C23 | TOTAL | M³ |  |  | - |  |  | 149.5
C30 | GF Superstructure Block Work
| B1 |  |  |  | 10.1 |  | 2.8 | 28.28
| B2 |  |  |  | 25.6 |  | 2.75 | 70.4
| B3 |  |  |  | 39.2 |  | 2.75 | 107.8
| B4 |  |  |  | 17.4 |  | 2.7 | 46.98
| B5 |  |  |  | 24.4 |  | 2.7 | 65.88
| B6 |  |  |  | 11.5 |  | 2.6 | 29.9
| B7 |  |  |  | 12.2 |  | 2.6 | 31.72
DEDUCTIIONS
| Arch 1 | M² | -1 | 1 | 1.3 |  | 2.5 | -3.25
| Arch 2 | M² | -1 | 1 | 1.2 |  | 2.5 | -3
| Arch 3 | M² | -1 | 1 | 1 |  | 2.5 | -2.5
| Arch 4 | M² | -1 | 1 | 0.8 |  | 2.5 | -2
| D2 | M² | -1 | 1 | 1 |  | 2.4 | -2.4
| D1 | M² | -1 | 1 | 1.8 |  | 2.4 | -4.32
| D4 | M² | -1 | 1 | 0.8 |  | 2.1 | -1.68
| D3 | M² | -1 | 1 | 1 |  | 2.1 | -2.1
| D4 | M² | -1 | 1 | 0.8 |  | 2.1 | -1.68
| D5 | M² | -1 | 1 | 1 |  | 2.1 | -2.1
| D3 | M² | -1 | 1 | 1 |  | 2.1 | -2.1
| D6 | M² | -1 | 1 | 1 |  | 2.4 | -2.4
| D3 | M² | -1 | 1 | 1 |  | 2.1 | -2.1
| D3 | M² | -1 | 1 | 1 |  | 2.1 | -2.1
| D4 | M² | -1 | 1 | 0.8 |  | 2.1 | -1.68
| D6 | M² | -1 | 1 | 1 |  | 2.4 | -2.4
| D3 | M² | -1 | 3 | 1 |  | 2.1 | -6.3
| D4 | M² | -1 | 1 | 0.8 |  | 2.1 | -1.68
| W1 | M² | -1 | 2 | 2 |  | 1.3 | -5.2
| W1 | M² | -1 | 1 | 2 |  | 1.3 | -2.6
| V | M² | -1 | 2 | 0.6 |  | 0.6 | -0.72
| W1 | M² | -1 | 1 | 2 |  | 1.3 | -2.6
| W2 | M² | -1 | 1 | 1.2 |  | 0.9 | -1.08
| V | M² | -1 | 2 | 0.6 |  | 0.6 | -0.72
| W1 | M² | -1 | 3 | 2 |  | 1.3 | -7.8
| Total | M² | [5 empty] | 314.45
C30 | FF Block Work
| B2 & B3 | M² | 1 | 1 | 35.6 |  | 2.75 | 97.9
DEDUCTIIONS
| D3 | M² | -1 | 1 | 1 |  | 2.1 | -2.1
| D4 | M² | -1 | 1 | 0.8 |  | 2.1 | -1.68
| Arch | M² | -1 | 1 | 0.8 |  | 2.1 | -1.68
| D5 | M² | -1 | 1 | 1 |  | 2.4 | -2.4
| W1 | M² | -1 | 1 | 2 |  | 1.8 | -3.6
| W3 | M² | -3 | 1 | 0.6 |  | 1.8 | -3.24
| W4 | M² | -1 | 1 | 1 |  | 1.8 | -1.8
| V | M² | -1 | 1 | 0.6 |  | 0.9 | -0.54
| Total | M³ | [5 empty] | 80.86
C23 | GF Block Work | M³ | 16 |  | 314.45 |  |  | 5031.2
C23 | FF Block Work | M³ | 8 |  | 80.86 |  |  | 646.88
C23 | TOTAL | M³ |  |  | 80.86 |  |  | 5678.08
C24 | GF Roof Beams
| B1 | M³ | 1 | 1 | 10.1 | 0.2 | 0.5 | 1.01
| B2 | M³ | 1 | 1 | 25.6 | 0.2 | 0.55 | 2.816
| B3 | M³ | 1 | 1 | 39.2 | 0.2 | 0.55 | 4.312
| B4 | M³ | 1 | 1 | 17.4 | 0.2 | 0.6 | 2.088
| B5 | M³ | 1 | 1 | 24.4 | 0.2 | 0.6 | 2.928
| B6 | M³ | 1 | 1 | 11.5 | 0.2 | 0.7 | 1.61
| B7 | M³ | 1 | 1 | 12.2 | 0.2 | 0.7 | 1.708
| Total | M³ | [5 empty] | 16.472
C24 | FF Roof Beams
| B2 & B3 | M³ | 1 | 1 | 35.6 | 0.2 | 0.55 | 3.92
| CB1 | M³ | 1 | 1 | 0.85 | 0.2 | 0.5 | 0.09
| Total | M³ | [5 empty] | 4
C24 | GF ROOF BEAMS | M³ | 11 |  | 16.47 |  |  | 181.17
C24 | FF ROOF BEAMS | M³ | 7 |  | 4 |  |  | 28.01
C24 | TOTAL | M³ | [5 empty] | 209.18
C22 | GF Waist slab & Roof Slabs
| Car Parking Slab | M³ | 1 | 1 | 2.9 | 5.9 | 0.2 | 3.422
| Entance Slab | M³ | 1 | 1 | 1.5 | 8.2 | 0.2 | 2.46
| Majilis | M³ | 1 | 1 | 5.7 | 4 | 0.2 | 4.56
| Salah | M³ | 1 | 1 | 7.9 | 4.5 | 0.2 | 7.11
|  | M³ | 1 | 1 | 1.7 | 0.1 | 0.2 | 0.034
| Majilis Toilet 1 | M³ | 1 | 1 | 2.2 | 1.7 | 0.16 | 0.5984
| Majilis Wash 1 | M³ | 1 | 1 | 3.3 | 1.7 | 0.16 | 0.8976
| Lobby | M³ | 1 | 1 | 3 | 3 | 0.16 | 1.44
| Passage from Lobby to Wash 1 | M³ | 1 | 1 | 21.84 |  | 0.16 | 3.4944
| Kitchen & Store | M³ | 1 | 1 | 32.26 |  | 0.2 | 6.452
| Main Store | M³ | 1 | 1 | 4 | 4.5 | 0.16 | 2.88
| Bedroom 1 Toilet | M³ | 1 | 1 | 1.8 | 2.1 | 0.16 | 0.6048
| Bedroom 1 | M³ | 1 | 1 | 4.2 | 4.4 | 0.16 | 2.9568
| Bedroom 2 | M³ | 1 | 1 | 4 | 4.4 | 0.16 | 2.816
| Bedroom 3 | M³ | 1 | 1 | 4.3 | 4.1 | 0.16 | 2.8208
| Cantilever Slab | M³ | 1 | 1 | 1.3 | 5.9 | 0.2 | 1.534
| Staircase Waist Slab | M³ | 1 | 1 | 15.2 | 1.2 | 0.2 | 3.648
| Steps | M³ | 1 | 27 | 1.2 | 0.02 |  | 0.648
| Total | M³ | [5 empty] | 48.3768
C22 | FF Waist slab & Roof Slabs
| Headroom Slab | M³ | 1 | 1 | 3 | 4.5 | 0.2 | 2.7
| Beadroom Slab | M³ | 1 | 1 | 4 | 4.5 | 0.2 | 3.6
| Toilet Slab | M³ | 1 | 1 | 4.4 | 1.8 | 0.2 | 1.584
| Cantilever slab (Future Projection) | M³ | 1 | 1 | 20.45 | 0.85 | 0.2 | 3.4765
| Total | M³ | [5 empty] | 11.3605
C22 | GF ROOF SLAB | M³ | 11 |  | 48.38 |  |  | 532.18
C22 | FF ROOF SLAB | M³ | 7 |  | 11.36 |  |  | 79.52
C22 | TOTAL | M³ | [5 empty] | 611.7
C30 | FF Block Work
| B2 & B3 | M² | 1 | 1 | 35.6 |  | 2.75 | 97.9
DEDUCTIIONS
| D3 | M² | -1 | 1 | 1 |  | 2.1 | -2.1
| D4 | M² | -1 | 1 | 0.8 |  | 2.1 | -1.68
| D5 | M² | -1 | 1 | 1 |  | 2.4 | -2.4
| W1 | M² | -1 | 1 | 2 |  | 1.8 | -3.6
| W3 | M² | -1 | 1 | 0.6 |  | 1.8 | -1.08
| W4 | M² | -1 | 1 | 1 |  | 1.8 | -1.8
| V | M² | -1 | 1 | 0.6 |  | 0.9 | -0.54
| Total | M³ | [5 empty] | 84.7
C13 | FF RCC Column
| Grid E-E |  | - |  |  |  |  | -
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 2.75 | 0.44
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.75 | 0.33
| Grid D-D |  | - |  |  |  |  | -
| C4 | M³ | 1 | 1 | 0.8 | 0.2 | 2.75 | 0.44
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.75 | 0.33
| Grid B-B |  | - |  |  |  |  | -
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.75 | 0.33
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 2.75 | 0.385
| Grid A-A |  | - |  |  |  |  | -
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.75 | 0.275
| c* | M³ | 1 | 1 | 0.3 | 0.2 | 2.75 | 0.165
| Total | M³ | [5 empty] | 2.695
C24 | FF Roof Beams
| B2 & B3 | M³ | 1 | 1 | 35.6 | 0.2 | 0.55 | 3.916
| CB1 | M³ | 1 | 1 | 0.85 | 0.2 | 0.5 | 0.085
| Total | M³ | [5 empty] | 4.001
C22 | GF Waist slab & Roof Slabs
| Headroom Slab | M³ | 1 | 1 | 3 | 4.5 | 0.2 | 2.7
| Beadroom Slab | M³ | 1 | 1 | 4 | 4.5 | 0.2 | 3.6
| Toilet Slab | M³ | 1 | 1 | 4.4 | 1.8 | 0.2 | 1.584
| Cantilever slab (Future Projection) | M³ | 1 | 1 | 20.45 | 0.85 | 0.2 | 3.4765
| Total | M³ | [5 empty] | 11.3605

## APPENDIX - A
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
APPENDIX A - BILL NO. 4
Bill Code | Ref. No | Bill No. | Description | RATE | AMOUNT | Amount
| SEC. 1 | Bill No. 7 | 3 NEW HOUSING UNITS | Additional Blockwork (20cm height increase, 3.0m → 3.2m slab level) |  | 1111.44
| SEC. 1 | Bill No. 4 | 20 NEW HOUSING UNITS | 10cm Blockwork to All Window Openings for UPVC Fixing (Sill Treatment) |  | 713.2976
| SEC. 2 | Bill No. 4 | HOLDING TANK RCC | 4.00m(L) x 2.00m(w) x 2.5m(D) Deep RCC HOlding Tank |  | 16541.2088
| SEC. 3 | Bill No. 4 | SOAK PIT | 1m Dia. × 2.5m Deep Soak Pit - Concrete Ratio (12.48%) |  | 2358.7912
| SEC. 4A | Bill No. 4 | EPOXY STEEL REINFORCEMENT | Substructural Reinforcement Bar Footing, Short Columns & Plinth Beam - Epoxy-Coated Bars |  | 4502.836
| SEC. 4B | Bill No. 4 | NORMAL STEEL REINFOCEMENT | Substructural Reinforcement Bar Footing, Short Columns & Plinth Beam - Normal Steel Bars |  | 4002.9887
|  |  | TOTAL |  |  | 29230.5624
|  |  | ADDITIONAL WORKS SECTION |  | AMOUNT
|  | Bill No. 7 | SECTION 1 | 3 Units
|  | Bill No. 4 | SECTION 2 | 20 Units
|  | Bill No. 4 | SECTION 5A | 20 Units
0
C68 |  | Bill No 4 | Marble Threshold | 66150
0
REVISED DOORS
| D1 | ALUM. DOOR | 20 | 892.5 | 17850
| D2 | ALUM. DOOR | 20 | 262.5 | 5250
23100
|  |  |  | RCC Tank | 827.0604
|  |  |  | Soak | 117.9396
WPC DOORS
C54 | D1 | WPC DOOR | 1 | 9135 | 9135
C55 | D2 | WPC DOOR | 1 | 4410 | 4410
13545
RATE DIFFERENCES
|  | ALUMI. DOOR | WPC
| D1 | 892.5 | 456.75 |  | 435.75
| D2 | 262.5 | 220.5 |  | 42
|  | To be Deducted under Superstructure Works |  |  | 477.75
Note on G29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Amount for the threshold was removed, comment by the consultant that the item of work is included in the scope of work
Note on F35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changing of Rate from 1300 to 892.5
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changing of rate from 400 to 262.5

## SUM. OF ADD. WORKS (BILL NO. 4 (hidden)
BILL NO 7. (3 NEW HOUSING UNITS)
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
SUMMARY OF ADDITIONAL WORKS
Ref. No. | Description of Works | Unit | Qty | Rate | Amount
SECTION 1 - 3 NEW HOUSING UNITS - BILL NO. 7
Additional Blockwork (20cm height increase, 3.0m → 3.2m slab level)
C26 | 200mm Hollow Block Wall (Superstructure) - height increase 20cm | m² | 18.56 | 6 | 111.36
C58 | Internal Rendering - cement & sand 1:3 (FF1 & FF2) | m² | 19.56 | 1 | 19.56
C59 | External Rendering - cement & sand 1:4 | m² | 18.56 | 1.5 | 27.84
C69 | Internal Wall Painting (FF1 & FF2) | m² | 19.56 | 5 | 97.8
C72/C73 | Wall Tile Works - 600×200×8 Anti-Slip (Kitchen, Toilet & Wash Area) | m² | 7.04 | 3 | 21.12
C69 | External Painting | m² | 18.56 | 5 | 92.8
Sub - Total: 1 Unit |  |  |  |  | 370.48
Sub - Total: 3 Units |  |  |  |  | 1111.44
TOTAL SECTION 1: |  |  |  |  | 1111.44
Note: All Rate are Reference to Bill No. 7
SECTION 2 - 20 NEW HOUSING UNITS (Window Sill Blockwork) - BILL NO. 4
10cm Blockwork to All Window Openings for UPVC Fixing (Sill Treatment)
C18 | Block Wall - 10cm to window | m² | 1.97 | 9.45 | 18.6165
C66 | Internal Plastering/Rendering | m² | 1.97 | 2.385 | 4.6984
C67 | External Plastering/Rendering | m² | 1.97 | 2.07 | 4.0779
C82 | Internal Painting | m² | 1.97 | 2.479 | 4.8836
C80 | External Painting | m² | 1.97 | 1.72 | 3.3884
Sub - Total: 1 Unit |  |  |  |  | 35.6649
Sub - Total: 20 Units |  |  |  |  | 713.2976
TOTAL SECTION 2 |  |  |  |  | 713.2976
Note: All Rate are Reference to Bill No. 4
SECTION 3 - (RCC HOLDING TANK - 20 HOUSING UNITS) - BILL NO. 4
4.00m(L) x 2.00m(w) x 2.5m(D) Deep RCC HOlding Tank
|  |  | Contract Valve |  | 18900
1 | Earthwork Excavation | m³ | 36.48 | 87.52% | 16541.2088
2 | PCC | m³ | 1.2
3 | RCC Base Slab | m³ | 2.64
4 | RCC Wall | m³ | 6.4
5 | RCC Cover slab | m³ | 2.11
| Volume of Concrete | m³ | 11.15
Total |  |  |  |  | 16541.2088
SECTION 4 - SOAK PIT - 20 HOUSING UNITS - BILL NO. 4
1m Dia. × 2.5m Deep Soak Pit - Concrete Ratio (12.48%)
1 | Earthwork Excavation | m³ | 1.96 | 12.48% | 2358.7912
2 | Block work or concrete | m³ | 1.51
3 | Filling Material | m³ | 0.68
4 | 100mm tk RCC Cover Slab | m³ | 0.08
| Volume of Concrete | m³ | 1.59
Total |  |  |  |  | 2358.7912
SECTION A - EPOXY STEEL REINFORCEMENT - 20 HOUSING UNITS - BILL NO. 4
Substructural Reinforcement Bar Footing, Short Columns & Plinth Beam - Epoxy-Coated Bars | [5 empty] | Concrete Works |  |  | Typical reinforcement:
1 | 16mm Reinforcement Bar in Footing | Tons | 1.7311 | 557.3568 | 964.8388 | 66.8828 | 115.7807 |  | Slab: 80–120 kg/m³
2 | 16mm Bar in Short Column | Tons | 0.90137 | 557.3568 | 502.3863 | 83.6035 | 75.3579 |  | Beam: 120–180 kg/m³
3 | 12mm Diameter Bar in Short Column | Tons | 0.055467 | 585.4926 | 32.4753 | 87.8239 | 4.8713 |  | Column: 150–250 kg/m³
4 | 8mm Diameter Bar Stirrups in Short Column | Tons | 0.19063 | 585.4926 | 111.6106 | 87.8239 | 16.7416
5 | 16mm Diameter Bar in Plinth Beam | Ton | 1.3669 | 557.3568 | 761.8586 | 66.8828 | 91.423
6 | 12mm Diameter Bar in Plinth Beam | Ton | 0.060622 | 585.4926 | 35.4939 | 70.2591 | 4.2593
7 | 8mm Diameter Bar in Plinth Beam | Ton | 3.5768 | 585.4926 | 2094.1726 | 70.2591 | 251.3007
Total |  |  |  | 1 Unit | 4502.836 | 76.2193 | 7.883 | 600.8368 | 12016.7361
|  |  |  | 20 Units | 90056.7207
SECTION B - Normal STEEL REINFORCEMENT - 20 HOUSING UNITS - BILL NO. 4
Substructural Reinforcement Bar Footing, Short Columns & Plinth Beam - Normal Steel Bars
1 | 16mm Reinforcement Bar in Footing | Tons | 1.7311 | 501.0852 | 867.4272 | 60.1302 | 104.0913
2 | 16mm Bar in Short Column | Tons | 0.90137 | 501.0852 | 451.6646 | 75.1628 | 67.7497
3 | 12mm Diameter Bar in Short Column | Tons | 0.055467 | 501.0852 | 27.7935 | 75.1628 | 4.169
4 | 8mm Diameter Bar Stirrups in Short Column | Tons | 0.19063 | 515.1531 | 98.202 | 77.273 | 14.7303
5 | 16mm Diameter Bar in Plinth Beam | Ton | 1.3669 | 501.0852 | 684.9402 | 60.1302 | 82.1928
6 | 12mm Diameter Bar in Plinth Beam | Ton | 0.060622 | 501.0852 | 30.3769 | 60.1302 | 3.6452
7 | 8mm Diameter Bar in Plinth Beam | Ton | 3.5768 | 515.1531 | 1842.5843 | 61.8184 | 221.1101
Total |  |  |  | 1 Unit | 4002.9887 | 67.1154 | 7.883 | 529.0704 | 10581.4088
|  |  |  | 20 Units | 80059.7744
| Variance Between Epoxy and Normal Steel Bar |  |  | 20 Units | 499.8473 |  |  |  | 1435.3273
TWO BEDROOM ROOF EXTENSION - (MAINTENANCE HOUSING UNITS)
Ref. No. | Description of Works | Unit | Qty | Rate | Amount
1 | Two bedroom roof extension | m² | 55 | 355 | 19525
|  |  |  | 1 Unit | 19525
|  |  |  | 32 Units | 624800
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
ADDITIONAL WORKS
Ref. No | Bill No. | Description | Additional Information |  | Amount
SEC. 1 | Bill No. 7 | 3 NEW HOUSING UNITS | SEC. 1 |  | 0
SEC. 1 | Bill No. 4 | 20 NEW HOUSING UNITS | 10cm Blockwork to All Window Openings for UPVC Fixing (Sill Treatment) |  | 713.2976
|  |  | 0 |  | 0
SEC. 2 | Bill No. 4 | HOLDING TANK RCC | 4.00m(L) x 2.00m(w) x 2.5m(D) Deep RCC HOlding Tank |  | 16541.2088
|  |  | 0 |  | 0
SEC. 3 | Bill No. 4 | SOAK PIT | 1m Dia. × 2.5m Deep Soak Pit - Concrete Ratio (12.48%) |  | 2358.7912
|  |  | 0 |  | 0
SEC. 4A | Bill No. 4 | EPOXY STEEL REINFORCEMENT | Substructural Reinforcement Bar Footing, Short Columns & Plinth Beam - Epoxy-Coated Bars |  | 90056.7207
|  |  | 0 |  | 0
SEC. 4B | Bill No. 4 | NORMAL STEEL REINFOCEMENT | Substructural Reinforcement Bar Footing, Short Columns & Plinth Beam - Normal Steel Bars |  | 80059.7744
|  | TOTAL |  |  | 189729.7927
|  | ADDITIONAL WORKS SECTION |  | AMOUNT
| Bill No. 7 | SECTION 1 | 3 Units
| Bill No. 4 | BLOCK | 20 Units | 713.2976
| Bill No. 4 | STEEL | 20 Units | 9996.9462
10710.2438
| Bill No 4 | Marble Threshold |  | 66150
76860.2438
|  |  | RCC Tank | 827.0604
|  |  | Soak | 117.9396
REVISED DOORS
| D1 - ALUM. DOOR | 20 | 1349.25 | 26985
| D2 - ALUM. DOOR | 20 | 483 | 9660
114450.2438

## 20 NHU ADD. QTY (hidden)
S/N | DESCRIPTIONS | UNIT | Qty | Rate | Amount | Remark
20 New Housing Unit
RCC HOLDING TANKS
Substructural Work
A | Excavation | m³ | 45 | 0.77 | 34.65 | Ref. To Bill No. 4, Item C3
B | Leveling and Compacting | m² | 15 | 0.455 | 6.825 | Ref. To Bill No. 4, Item 7
C | Anti Termimite Treatment | m² | 63 | 1.524 | 96.012 | Ref. To Bill No. 4, Item 8
D | Blinding PCC 100mm | m³ | 1.5 | 63 | 94.5 | Ref. To Bill No. 4, Item C9
E | Reinforcced Cement Concrete RCC | m³ | 2.31 | 94.5 | 218.295 | Ref. to Bill No. 4, Item C12
F | Reinforced holding Tank Wall | m³ | 6.2 | 94.5 | 585.9 | Ref. to Bill No. 4, Item C12
G | Back Filling | m³ | 15.268 | 0.525 | 8.0157 | Ref. To Bill No. 4,, Item C6
H | Holding Tank Slab RCC | m³ | 2.04 | 94.5 | 192.78 | Ref. to Bill No. 4, Item C12
Reinforcement Bar
J | 16mm Reinforcement Bar | Tons | 2.7224 | 575.4441 | 1566.5992
Formwork
K | Base ofof Holding Tank | m² | 3.45 |  | 0
L | Wall of Holding Tank | m² | 32.25 |  | 0
M | Soffix of holding Tank | m² | 8 |  | 0
N | Edge of Holding Tank | m² | 2.72 |  | 0
| Total |  |  | 1 Unit | 2803.5769
A | TOTAL ESTIMATED AMOUNT |  |  | 20 Unis | 56071.539
| BILL NO 4 |  | BILL CODE | P12 | BOQ AMOUNT | 18900
[5 empty] | % Holding Tanks | 75%
B | BOQ AMOUNT |  |  |  | Holding Tanks | 14175
| BALANCE AMOUNT | A - B |  |  |  | 41896.539
BLOCK WORK SYSTEM
Substructural Work
A | Excavation | m³ | 45 | 0.77 | 34.65 | Ref. To Bill No. 4, Item C3
B | Leveling and Compacting | m² | 15 | 0.455 | 6.825 | Ref. To Bill No. 4, Item 7
C | Anti Termimite Treatment | m² | 63 | 1.524 | 96.012 | Ref. To Bill No. 4, Item 8
D | Blinding PCC 100mm | m³ | 1.5 | 63 | 94.5 | Ref. . Bill No. 4, Item C9
E | Block Wall | m² | 35.2 | 9.45 | 332.64 | Ref. Bill No. 4, Item C18
F | Back Filling | m³ | 14.738 | 0.525 | 7.7374 | Ref. To Bill No. 4,, Item C6
G | Holding Tank Slab RCC | m³ | 2.04 | 94.5 | 192.78 | Ref. to Bill No. 4, Item C12
Reinforcement Bar
H | 16mm Reinforcement Bar | Tons | 0.51175 | 575.4441 | 294.4819
Formwork
J | Soffix of holding Tank | m² | 8 |  | 0
K | Edge of Holding Tank | m² | 2.72 |  | 0
L | Internal Rendering |  | 33 | 2.385 | 78.705 | Ref. to Bill No. 4, Item C66
M | External Rendering |  | 37.4 | 2.07 | 77.418 | Ref. to Bill No. 4, Item C7
| Total |  |  | 1 Unit | 1215.7493
A | TOTAL ESTIMATED AMOUNT |  |  | 20 Units | 24314.9867
| BILL NO 7 |  | BILL CODE | P13 | BOQ AMOUNT | 5000
[5 empty] | % Holding Tanks | 75%
B | BOQ AMOUNT |  |  |  | Holding Tanks | 3750
11250
| 10CM BLOCK WORK TO ALL WINDOWN AS SILL |  |  |  |  | REMARK
1 | Block Wall | m² | 1.97 | 9.45 | 18.6165 | C18
2 | Plastering/Rendering
| Internal | m² | 1.97 | 2.385 | 4.6985 | C66
| External | m² | 1.97 | 2.07 | 4.0779 | C67
3 | Painting/Decoration
| Internal | m² | 1.97 | 2.479 | 4.8836 | C82
| External | m² | 1.97 | 1.72 | 3.3884 | C80
| Total | 1 Unit |  |  | 35.6649
| Total | 20 Units |  |  | 713.2976

## BILL NO 4 (20 NHU EXTERNAL WORK
BILL NO 4. (20 NHU EXTERNAL WORK)
Item Code | Item Name | Item Details | Additional Information | UOM | Unit Price In Figure | BOQ QTY | BOQ Amount | Revised QTY | Revised Amount (CLAIMABLE) | Addition/Omission Quantity | OMISSION | Additon
EW1 | External Works General Site Works | Site Preparation | Allow for setting out grading trimming including clearing loose boulders vegetation stones and the like all trees bushes shrubs and undergrowth grub up all roots and burn or remove from site as directed by the Engineer. | Item | 0 | 1 | 0 | 1 | 0
EW2 | External Works General Site Works | Boundary wall | Allow for the Contractor to prepare RCC foundation column block work plastering and painting as per the Architectural Drawing and as per Engineer Employer Instruction to complete the Boundary Wall. | M | 2.1 | 1775 | 3727.5 | 1775 | 3727.5
EW3 | External Works General Site Works | Wicket Gate | Allow for the Contractor to supply fabricate and installation of single leaf Wicket Gate as per the Architectural Drawing and follow as per Engineer Employer Instructions including anti corrotion epoxy paint. | no | 105 | 20 | 2100 | 20 | 2100
EW4 | External Works General Site Works | Car Entrance Gate | Allow for the Contractor to supply fabricate and installation of single leaf Car Entrance Gate as per the Architectural Drawing and follow as per Engineer Employer Instructions including anti corrotion epoxy paint | no | 141.75 | 20 | 2835 | 20 | 2835
EW5 | External Works General Site Works | Entrance Gate ont only | Allow for the Contractor to supply fabricate and installation of Wicket Gate solid WPC with 10 years garantee as per the Architectural Drawing and follow as per Engineer Employer Instructions including anti corrotion epoxy paint. | Item | 0 | 0 | 0 | 0 | 0
EW6 | External Works General Site Works | Wicket Gate | Single leaf Wicket Gate solid WPC | Item | 0 | 1 | 0 | 1 | 0
EW7 | External Works General Site Works | Car Entrance Gate | Single leaf Car Entrance Gate soild WPC | Item | 0 | 1 | 0 | 1 | 0
EW8 | External Works General Site Works | Entrance Concrete Paver | Allow for the Contractor to prepare Concrete Paver as per the Architectural Drawing and place at the House Main Entrance. | No | 5.25 | 100 | 525 | 100 | 525
EW9 | External Works General Site Works | Interlock Tile | Allow for connection Asphalt road to the site from the main drawing as per approval | M2 | 1.05 | 13550 | 14227.5 | 13550 | 14227.5
EW10 | External Works General Site Works | Curb Stone | Allow for connection Asphalt road to the site from the main drawing as per approval | M | 2.1 | 1400 | 2940 | 1400 | 2940
EW11 | External Works General Site Works | Design and Build Shaded Car Parking of 20 numbers with Solar Panel Canopy | Allow for the Contractor to design and build the Shaded Car Park for houses with Solar Panel Canopy as per Engineer Employer Instruction. | no | 105 | 20 | 2100 | 0 | 0 | 20 | 2100
TOTAL EXTERNAL WORKS AND EXTERNAL SERVICES | [6 empty] | 28455 |  | 26355 |  | 2100 | 0

## BILL NO 5. (MAINTENANCE HOUSING
BILL NO 5. (29 MAINTENANCE HOUSING UNIT)
Item Code | Item Name | Item Details | Additional Information | UOM | BOQ Qty | Unit Price In Figure-OMR | BOQ Total Amount-OMR | Revised QTY | Revised Amount | Saving Quantities | Omission | RATE | Addition | APPENDIX - B
EX1 | External Works Lump sum | Site Clearance | Which shall include removing vegetation undergrowth bushes hedges trees or the like all complete item also Removal and disposal of surplus excavated material including providing suitable tip to the dumping yard or as specified and directed by the Engineer or local authorities.. | Item | 29 | 304.5 | 8830.5 | 29 | 8830.5
EX2 | External Works Lump sum | Demolishing | demolishing all the structures and stores inside the boundary wall by preparing a sketch for each house and submitting to clients engineer and getting the written approval for demolishing and shifting the disposal material to damp yard including foundations of structres. | Item | 29 | 514.5 | 14920.5 | 29 | 14920.5
EX3 | External Works Lump sum | Demolishing Rebuild | demolishing and rebuilding as per the Same Specifications the gates columns damaged boundary wall damaged manholes damaged Holding Tanks damaged Sock Pits and change the cover to be GRP type Heavy duty and any other elements must be demolished to modified or rebuilt as per main scope all of this including and not limited to Excavation in any type of soil Disposal of surplus material filling by imported fill material compacted in layers waterproof concrete reinforcements joints block works polythene sheets anti termite manholes cover plastering PVC Pipes and any necessary work to finish the work in functional condition. | Item | 29 | 619.5 | 17965.5 | 29 | 17965.5
A |  | SUM FOR PAGE1/20 |  |  |  |  | 41716.5 |  | 41716.5
EX4 | External Works Lump sum | boundary wall | the contractor has to remove and demolish any damaged or unsafe parts of the wall and rebuild it with the same height after filling any cracks space between concreet and blockwork with non shirenkage filler with SS mesh between concrete and blocks and to remove all the paint or cladding and re paint again with external paint weather coat stoneshield with prime coat with 10 years garantee .all of this including and not limitted to to 200mm thick walls Polythene sheet gauge 1000 Waterproofing with two bitumen coats and membrane 4mm to surfaces of concreteProtection to concretemasonryblock work in contact with soil 3 coats approved bituminous paintExpansion joint | Item | 29 | 619.5 | 17965.5 | 29 | 17965.5 |  |  | 6 | 174 | Check Appendix - B for more Details
EX5 | External Works Lump sum | GI gates | remove the existing gates and supply and fix new gates GI and painted with marine paint as per the site conditions with warranty for the paint and gates for 10 years | Item | 29 | 724.5 | 21010.5 | 29 | 21010.5
EX6 | External Works Lump sum | Pea Gravel around the house and inside the boundary wall | the contractor has fill the full area with pea gravel with size between 20mm to 50mm max with depth 100 mm around the house detecting from it the manholes and holding tanks and sock pit only but it must be under the new caravans | Item | 29 | 829.5 | 24055.5 | 29 | 24055.5
EX7 | External Works Lump sum | Dewatering | Allow for keeping excavations free from underground surface or running water from whatever source | Item | 29 | 252 | 7308 | 29 |  | 29 | 7308
EX8 | External Works Lump sum | Gas Cylinder Room | Contractor has to built a Gas Cylinder Room with RCC base and block work with height 1.5 m with concrete top slab with suitable foundation and safety gate that powder coated and painted with marine paint with warranty 10 years. | Item | 29 | 241.5 | 7003.5 | 29 | 7003.5
B |  | SUM FOR PAGE2/20 |  |  |  |  | 77343 |  | 70035
C1 | Super Structure Works Lump sum | Demolishing the Existing staircase slab and reconstract it with Poured Concrete Reinforced insitu concrete poured vibrated Ordinary Portland Cement OPC concrete grade C35 all in accordance with the Drawings and Specifications including but not limited formwork reinforcement additives movement joints construction joints joint filler curing compounds surface finishes water stop wherever necessary concrete tests and any other accessories and ancillary work required to complete the work. | RCC slabs RCC beams RCC Columns landingsstair etc. not exceeding 200 mm thickness at staircase head rooms. | Item | 29 | 262.5 | 7612.5 | 29 | 7612.5
C2 | Superstructure Works Thermal and Moisture Protection | Removing Roof tiles and screed and waterproofing with cleaning the surfaces closing any cracks with chemical sealants and making the surface ready for receiving the new waterproofing. | Demolishing the existing roof finish with waterproof and disposal the material and make the surface ready for receiving the new waterproofing | Item | 29 | 1995 | 57855 | 29 | 57855
C |  | SUM FOR PAGE3/20 |  |  |  |  | 65467.5 |  | 65467.5
C3 | Superstructure Works Thermal and Moisture Protection | Roof screed lightweight concrete screed 1000 kgm3 minimum 50 mm thick to a maximum of 125 mm thick and Waterproofing with two bitumen coats and 4 mm thick torch applied acrylic polypropylene modified bitumen membrane with nonwoven polyester reinforcement and polyethylene film waterproof membrane including primer to roofs as per the manufacturer printed instructions complete as specified. Contractor to allow for 10 years guarantee and 24 hours flood test | To roof decksRoof screed lightweight concrete screed 1000 kgm3 minimum 50 mm thick to a maximum of 125 mm thick and Waterproofing with two bitumen coats and 4mm thick membrane on flat surface laid to falls and cross falls | Item | 29 | 3150 | 91350 | 29 | 91350
C4 | Superstructure Works Thermal and Moisture Protection | Skirting 300 mm girth including turning into groove | In up standsdrops and around parapet minimum 300 mm high including dressing over fillet grooves sealant tantalized batten etc. complete to roof deck | Item | 29 | 1890 | 54810 | 29 | 54810
C5 | Superstructure Works Thermal and Moisture Protection | Insulation Extruded high density polystyrene foam board insulation with rigid closed cell structure all in accordance with the specifications and drawings external | to roof decks 50 mm thick laid on concrete spot bonded to waterproofing | Item | 29 | 514.5 | 14920.5 | 29 | 14920.5
D |  | SUM FOR PAGE4/20 |  |  |  |  | 161080.5 |  | 161080.5
C6 | Superstructure Works Thermal and Moisture Protection | Roof Finishes | Supply and fix 300 x 300 x 25 mm terrazzo tiles bedded on and including cement mortar screed to falls and cross falls jointed in cement mortar movements joints etc. complete to roof | Item | 29 | 1995 | 57855 | 29 | 57855
C7 | Superstructure Works Thermal and Moisture Protection | Roof Finishes | Supply and fix 100x20 mm terrazzo skirting to upstands | Item | 29 | 892.5 | 25882.5 | 29 | 25882.5
C8 | Superstructure Works Thermal and Moisture Protection | Roof Sundries | Allow for Providing dressing around 110mm83mm UPVC rainwater outlets roof duct gargoyle extract fan soil and vent pipe | Item | 29 | 481.95 | 13976.55 | 29 | 13976.55
C9 | Superstructure Works Thermal and Moisture Protection | Roof Sundries | For parapet Allow for gun applied sealant to seal the joints and groove as applicable and as specified. | Item | 29 | 304.5 | 8830.5 | 29 | 8830.5
C10 | Superstructure Works Metal Works | Staircase handrail | Removing the old handrails and replacing them with 316 St.st handrails including supply and fix as per exixting desin hand rail in new houses drawings. | Item | 29 | 1575 | 45675 | 29 | 45675
C11 | Superstructure Works Metal Works | galvanized steel cat Ladder | Supply and install galvanized steel cat Ladder as specified and detailed on the drawingas per exixting desin hand rail in new houses drawings. | Item | 29 | 262.5 | 7612.5 | 29 | 7612.5
E |  | SUM FOR PAGE5/20 |  |  |  |  | 159832.05 |  | 159832.05
C12 | Superstructure Works Doors and Windows | Wood Doors All Types and Size of doors including the main entrance door comprising profiled heads jambs frames subframes architraves beadings moldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation ironmongery as specified in schedule and approved; fixed to hardwood All locks shall be 3 sets of keys Note to all stainless steel fittings shall be of 316 grade | 1remove the Old doors and maintain the frame if possible and supply and fix wooden door with the same existing size and specification and new accessories.item include and not limited to maintain the existing frame and paint. | Item | 29 | 9975 | 289275 | 29 | 289275 |  |  | 400 | 11600 | Check Appendix - B for more Details
C13 | Superstructure Works Doors | UPVC Doors | The contractor to Replace all Wooden Doors for Toilets and Roof to be UPVC and to respect the following to: 1 Door sizes stated are structural opening size 2: Tenderers shall strictly follow the door size as per site conditions prior to pricing this section. No additional payments will be entertained due to failure or and misunderstanding by the tenderer. 3: Rate shall include for supply and fixing of new all necessary ironmongery as specified 4: Roof doors shall be airtight rubbersealed and weather resistant 5: Rate shall include final finishing and final decoration as per the specification drawings and schedule and to the approval of the Engineer | Item | 29 | 3675 | 106575 | 29 | 106575
F |  | SUM FOR PAGE6/20 |  |  |  |  | 395850 |  | 395850
C14 | Superstructure Works for Windows | Aluminium windows | The contractor is to Maintain the existing Aluminum Windows for and to respect the following to: 1 Windows sizes stated are structural opening size 2 Contractor shall strictly follow the Windows size as per site conditions prior to pricing this section. No additional payments will be entertained due to failure or and misunderstanding by the contractor. 3 Rate shall include for supply and fixing of new all necessary ironmongery as specified 4 Windows shall be airtight rubbersealed and weather resistant. 5 Rate shall include final finishing and final decoration as per the specification drawings and schedule and to the approval of the Engineer 6 The exterior glass is to be replaced with new 6 mm Reflected Glass and 6 mm smokey glass for toilets complete systems including all stiffeners fasteners sealants jointing and material thickness as required to form highquality systems in accordance with specifications. 7 Contractor to replace the Insect mesh to be aluminum type not metal. 8 the contractor is to replace any Aluminum section that could be totally damaged and can not be rectified. | Item | 29 | 8400 | 243600 | 29 | 243600
C15 | Superstructure Works Finishes | Entrance Flooring | Demolishing entrance flooring preparing the surface to receive marble tiles and supplying and fixing marble tiles for landing and stairs Tread and raiser for steps also skirting included with the same material.with supplying and fixing | Item | 29 | 430.5 | 12484.5 | 29 | 12484.5
G |  | SUM FOR PAGE7/20 |  |  |  |  | 256084.5 |  | 256084.5
C16 | Superstructure Works Finishes | Salah and Majles flooring | Demolishing salah and Majles flooring preparing the surface to receive porcelain tiles and supplying and fixing porcelain tiles matching with existing floors also skirting included with the same material.with supplying and fixing | Item | 29 | 472.5 | 13702.5 | 29 | 13702.5
C17 | Superstructure Works Finishes | Kitchen and toilets flooring | Demolishing Kitchen and toilets flooring preparing the surface to receive antislip ceramic tiles and supplying and fixing antislip ceramic tiles matching with existing floors.with supplying and fixing | Item | 29 | 367.5 | 10657.5 | 29 | 10657.5
C18 | Superstructure Works Finishes | Stairs Landing and steps | Demolishing Stairs flooring preparing the surface to receive marble tiles and supplying and fixing marble tiles for landing and stairs Tread and raiser for steps also skirting included with the same material.with supplying and fixing | Item | 29 | 682.5 | 19792.5 | 29 | 19792.5
H |  | SUM FOR PAGE8/20 |  |  |  |  | 44152.5 |  | 44152.5
C19 | Superstructure Works Finishes | Internal Wall Finishes Scrap the existing paint repair the cracks fill the cracks and put SS mesh between concrete and block work and over the MEP pipes including PVC corner beads and expanded metal lath angle beads and plaster stops as specified. including decorative around the windows with internal Backgrounds Plaster cement and sand 1to3 internal To walls and columns on concrete block base internal for the damaged areas to receive INTERNAL Paint to walls of approved color over a coat of waterbased primer including preparation of surface by thorough cleaning and wetting and applying POP Gypsum powder putty as per manufacturer�s specification fully to give an even shade before painting and curing as per manufacturers specifications and as directed the paint should be antifungal growth and weather resistance. | Prepare prime and apply one coat of primer and 2 coats of approved quality and color Painting and decoratingEligance marble paint with 10 years garantee all as specifiedto internally | Item | 29 | 1260 | 36540 | 29 | 36540 |  |  | 2 | 58 | Check Appendix - B for more Details
I |  | SUM FOR PAGE9/20 |  |  |  |  | 36540 |  | 36540 |  |  | 1 | 0
C20 | Superstructure Works Finishes | External Wall Finishes Scrap the existing paint repair the cracks fill the cracks and put SS mesh between concrete and block work and over the MEP pipes including PVC corner beads and expanded metal lath angle beads and plaster stops as specified. including decorative around the windows with internal Backgrounds Plaster cement and sand 1to3 External To walls and columns on concrete block base External for the damaged areas to receive three coats of heavy texture EXTERNAL walls and columns design and windows concrete frame and all mentioned areas at tender drawings of approved color over a coat of waterbased primer including preparation of surface by thorough cleaning and wetting and applying POP Gypsum powder putty as per manufacturer�s specification fully to give an even shade before painting and curing as per manufacturers specifications and as directed the paint should be antifungal growth and weather resistance | Prepare prime and apply 3 coats of approved quality and color Decorative projection weather coat stoneshield with 10 years garantee as per the specificationsto Externally | Item | 29 | 787.5 | 22837.5 | 29 | 22837.5 |  |  | 2 | 58 | Check Appendix - B for more Details
J |  | SUM FOR PAGE10/20 |  |  |  |  | 22837.5 |  | 22837.5
C21 | Superstructure Works Finishes | Toilets and Kitchen wall Ceramic tiles | Demolishing Kitchen and toilets walls tiles preparing the surface to receive glossy ceramic tiles with supplying and fixing | Item | 29 | 735 | 21315 | 29 | 21315
C22 | Superstructure Works Finishes | Ceilings Finishes Scrap the existing paint repair the cracks fill the cracks Painting and decorating internal Paint to walls of approved color over a coat of waterbased primer including preparation of surface by thorough cleaning and wetting and applying POP Gypsum powder putty as per manufacturer�s specification fully to give an even shade before painting and curing as per manufacturers specifications and as directed the paint should be antifungal growth and weather resistance. | One coat Primertwo coats putty Three coats of Fenomastic Silk paint or equivalent on cement sand plaster. Colour as per Approval of Engineer | Item | 29 | 945 | 27405 | 29 | 27405
C23 | Superstructure Works Finishes | External Wall Finishes supply and fix Crazy Natural Stone with height 1.5 meter from external FFL | Supply and fix Crazy Natural Stone or marble with a height 1.5 meters from External FFL | Item | 29 | 1522.5 | 44152.5 | 29 | 44152.5
K |  | SUM FOR PAGE11/20 |  |  |  |  | 92872.5 |  | 92872.5
C24 | Superstructure Works Finishes | Remove the Existing and Allow for supply fabricate and installation of Kitchen Stage including Stage Concrete Stage Korean Top and Stage Area Ceramic Wall Tile as per the specifications drawings and to approval of the Engineer. | Kitchen Stage Concrete Korean Top Ceramic Wall Tiles | Item | 29 | 84 | 2436 | 29 | 2436
C25 | Superstructure Works Finishes | Remove the Existing and Allow for supply fabricate and installation of Kitchen Hood Range including Aluminum Kitchen Cabinet above and Aluminum Kitchen Cabinet below all as per the specifications drawings and to approval of the Engineer. | Kitchen Hood Range Cabinet above and below Cabinet. | Item | 29 | 84 | 2436 | 29 | 2436
P1 | Sanitary Installation | The Contractor must remove all sanitary that were fixed | The Contractor must remove all sanitary that were fixed at toilets and kitchens including but not limited to Wash basins EWC Mixers toilet accessories st st sink floor trap covers towel rails tissue holder �.. Etc and store it to handover to the client in clients storages. | Item | 29 | 95.55 | 2770.95 | 29 | 2770.95
P2 | Sanitary Installation | UPVC pipes to BS 45141983 and BS 4660 1973 including all joints accessories and brackets | Supply and install Vent cowl with weathering apron 75 mm diameter | Item | 29 | 12.6 | 365.4 | 29 | 365.4
P3 | Sanitary Installation | Floor Drain trap | Supply and install 110 mm diameter Floor Trap with 150 X 150 mm SS grating Cover including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 11.55 | 334.95 | 29 | 334.95
L |  | SUM FOR PAGE12/20 |  |  |  |  | 8343.3 |  | 8343.3
P4 | Sanitary Installation | Gully Trap | Supply and install 300 mm x 300 mm gully trap of approx. 300 mm depth set in concrete Grade 30 Nmm� joints to drain pipes complete with 300 mm x 300 mm medium duty cast iron cover and frame. including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 12.6 | 365.4 | 29 | 365.4
P5 | Sanitary Wares and Fittings | Semi pedestal wash basin | Supply and install 650 mm x 475 mm vitreous china white wash basin with semi pedestal center tap hole overflow and bottle trap. including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 12.6 | 365.4 | 29 | 365.4
P6 | Sanitary Wares and Fittings | Stainless Steel Sink | Supply and install 1000 mm x 550 mm stainless steel sink single bowl single drainer with drainboard to BS 1244 complete with 2 piece tubular P trap chain plug waste brackets. including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 23.1 | 669.9 | 29 | 669.9
P7 | Sanitary Wares and Fittings | European Water Closet | Supply and install 400 mm x 685 mm vitreous china white concealed tank wall hung mounted EWC squatting pan built in wall toilet dual flush 3L6L concealed cistern and heavy duty auto closed seat and cover including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 13.65 | 395.85 | 29 | 395.85
P8 | Sanitary Wares and Fittings | shower tray | Supply and install white glazed shower tray size 70x70 with the necessary fittings and plumbing darins including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 12.6 | 365.4 | 29 |  | 29 | 365.4
P9 | Sanitary Wares and Fittings | Ablution Faucet | Chromium plated approved ablution faucet with angle valve hose and spray unit. including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 13.65 | 395.85 | 29 | 395.85
M |  | SUM FOR PAGE13/20 |  |  |  |  | 2557.8 |  | 2192.4
P10 | Sanitary Wares and Fittings | shower Mixer | Single lever chrome plated shower mixer including Rainshower rail set with its hand shower. including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 12.6 | 365.4 | 29 | 365.4
P11 | Sanitary Wares and Fittings | Wash Basin Mixer | Single lever chrome plated wash basin mixer including pop up waste. including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 9.45 | 274.05 | 29 | 274.05
P12 | Sanitary Wares and Fittings | Sink Mixer | Single lever chrome plated Sink mixer. including all UPVC and PVC pipes for water supply and drain with fittings and flexible pipes | Item | 29 | 9.45 | 274.05 | 29 | 274.05
P13 | Sanitary Wares and Fittings | Toilet tissue holder | Recessed type stainless steel Toilet tissue dispenser holder with stainless steel hood. | Item | 29 | 9.45 | 274.05 | 29 | 274.05
P14 | Sanitary Wares and Fittings | Towel rail | 610 x 75 x 75 mm towel rail | Item | 29 | 8.4 | 243.6 | 29 | 243.6
P15 | Sanitary Wares and Fittings | Mirror | 450 x 600 mm mirror 6 mm thick bevel edged plywood backing fixed with chromium plated dome headed screws | Item | 29 | 12.6 | 365.4 | 29 | 365.4
P16 | Water Supply | Polypropylene random copolymer pipe | contractor to check the pressure of the cold and hot water at each house and to replace the damaged or leacked pipes after removing the tiles floor wall and refix the tiles again with similar or with new the Polypropylene random copolymer pipes and fittings cold and hot water connections to international standard ISOto EN ISO 15874 to 2003 and DIN 80777 8078 including up stand and brackets exposed insulation as per Specificationall the pipes as per the original sizes. | Item | 29 | 8.4 | 243.6 | 29 | 243.6
N |  | SUM FOR PAGE14/20 |  |  |  |  | 2040.15 |  | 2040.15
P17 | Water Supply | Cold and Hot water Valves | Supply and install the following Isolating valves to BS 5154 series B bronze wedge gate pattern screwed joints with adaptor to pipes etc. wherever shown in drawings and or specified and as approved by the Engineer.all the Valves as per the original sizes. | Item | 29 | 9.45 | 274.05 | 29 | 274.05
P18 | Water Supply | The Contractor must remove all Equipment and Accessories that were fixed | The Contractor must remove all Equipment and accessories that were fixed at houses including but not limited to GRP Water Tanks water Heater �.. Etc and store it to hand over to the client in the clients storage. | Item | 29 | 9.269 | 268.801 | 29 | 268.801
P19 | Water Supply | Water Tank | Supply and install 400US gallon capacity GRP type water storage tank with foundation epoxy coated frame ball valve overflows etc. to approval | Item | 29 | 52.138 | 1512.002 | 29 | 1512.002
P20 | Water Supply | Water Heater | Supply and install 50 liter capacity horizontal type copper tank high level wall mounted electrical water heater including all connections and fixing. | Item | 29 | 30.124 | 873.596 | 29 | 873.596
P21 | Rain Water Installation | Rain Water UPVC Pipeswith outlet | remove the existing and Supply and install UPVC pipes to BS 4514 1983 including all joints fittings accessories connections and brackets | Item | 29 | 32.441 | 940.789 | 29 | 940.789
P22 | Rain Water Installation | TAP AND ABLUTION FAUCET | Construct a 60x120x40 Ablution base by Solid Block with RCC base and finished from all side with anti slip ceramic including the mixer subject to the engineers and client approval | Item | 29 | 28.966 | 840.014 | 29 | 840.014
M1 | Air Conditioning and Ventilation Installation | The Contractor must remove all Equipment and Accessories that were fixed | The Contractor must remove all Equipment and accessories that were fixed at houses including but not limited to AC units indoor outdoor�.. Etc and store it to hand over to the client in the clients storage. | Item | 29 | 25.49 | 739.21 | 29 | 739.21
O |  | SUM FOR PAGE15/20 |  |  |  |  | 5448.462 |  | 5448.462
M2 | Air Conditioning and Ventilation Installation | High level Wall mounted Split AC with DX unit replacing the box type at walls | Contractor ro remove the existing AC at walls and to close the walls and make plaster with st st mesh and painting after that to fix 18000 BTUHR capacity highlevel wall mounted split type air conditioner including connection to electrical outlet and concrete base foundation and AC drain pipes to gully trap. | Item | 29 | 23.172 | 671.988 | 29 | 671.988
M3 | Air Conditioning and Ventilation Installation | High level Wall mounted Split AC with DX unit for Kitchen | 18000 BTUHR capacity highlevel wall mounted split type air conditioner including connection to electrical outlet and concrete base foundation and AC drain pipes to gully trap. | Item | 29 | 243.31 | 7055.99 | 29 | 7055.99
M4 | Air Conditioning and Ventilation Installation | High level Wall mounted Split AC with DX unit for salah and majles | 30000 BTUHR capacity highlevel wall mounted split type air conditioner including connection to electrical outlet and concrete base foundation and AC drain pipes to gully trap. | Item | 29 | 278.069 | 8064.001 | 29 | 8064.001
M5 | Air Conditioning and Ventilation Installation | Ventilating Fans | remove the existing and Supply and install test and commission ventilating fan 6 and 8 with electrically operated louvers as specified on the drawings complete with all mounting requirements flexible connections electrical connections support backdraft dampers auto changeover controller all in accordance with the specification | Item | 29 | 46.345 | 1344.005 | 29 | 1344.005
E1 | Electrical Engineering Installation | Distribution Board | the Contractor must check the Power supply distribution copper cable with earth continuity cable Rate should cover related accessories jointing glanding earthing tag termination legs PVA shrowds and cable tag for interconnecting cables cable trays cable identification cable route marker from substation to the switches and sockets and in between subboards and distribution panels and change any defected item to have the system working in functional conditions | Item | 29 | 46.345 | 1344.005 | 29 | 1344.005
P |  | SUM FOR PAGE16/20 |  |  |  |  | 18479.989 |  | 18479.989
E2 | Electrical Engineering Installation | Contractor to provide full Solar system | The contractor to Design and Provide the solar system including all materials and supply and fix it to be compatible with the MCCP and DBs at the houses and get the approvals from the ClientEngineer before executing any work | Item | 29 | 0 | - |  | 0 | 29 | 0
E3 | Electrical Engineering Installation | Sub Main Distribution Board | the Contractor to replace the existing with new weatherproof GRP IP 65 Main or Sub Main Distribution panel board including MCCBs supports earthing cable glands Ammeters Voltmeters internal wiring interconnection and labels as per drawings and specification | Item | 29 | 53.297 | 1545.613 | 29 | 1545.613
E4 | Electrical Engineering Installation | Sub Main Distribution Board | The contractor to replace the existing DBs with new weatherproof GRP IP 65 for all the DBs at the houses. | Item | 29 | 63.724 | 1847.996 | 29 | 1847.996
E5 | Electrical Engineering Installation | Sub Main Distribution Board | The contractor to add a new DB for the New Caravans to be weatherproof GRP IP 65 . | Item | 29 | 62.566 | 1814.414 | 29 |  | 29 | 1814.414
E6 | Electrical Engineering Installation | Small Power Accessories removing | the Contractor to replace the existing with new switches and sockets and the existing to be handover to client at his storage at end of the project. | Item | 29 | 6.952 | 201.608 | 29 | 201.608
E7 | Electrical Engineering Installation | Small Power Accessories Installation | the Contractor to replace the existing with new 13A DP single switched socket outlet | Item | 29 | 52.138 | 1512.002 | 29 | 1512.002
E8 | Electrical Engineering Installation | Small Power Accessories Installation | the Contractor to replace the existing with new 13A DP twin switched socket outlet | Item | 29 | 11.586 | 335.994 | 29 | 335.994
E9 | Electrical Engineering Installation | Small Power Accessories Installation | the Contractor to replace the existing with new 13A DP single gang weatherproof switch socket outlet | Item | 29 | 12.745 | 369.605 | 29 | 369.605
E10 | Electrical Engineering Installation | Small Power Accessories Installation | the Contractor to replace the existing with new 20A Dp switch outlet | Item | 29 | 637.241 | 18479.989 | 29 | 18479.989
Q |  | SUM FOR PAGE17/20 |  |  |  |  | 26107.221 |  | 24292.807
E11 | Electrical Engineering Installation | Small Power Accessories Installation | the Contractor to replace the existing with new two way two gang | Item | 29 | 27.807 | 806.403 | 29 | 806.403
E12 | Electrical Engineering Installation | Small Power Accessories Installation | the Contractor to replace the existing regulator for the ceiling fans | Item | 29 | 30.124 | 873.596 | 29 | 873.596
E13 | Electrical Engineering Installation | Small Power Lighting Fixture removing | the Contractor to replace the existing with new Lighting Fixture inside and out side and celing fans such as including lamps electronic ballasts control gearwirescables and all necessary accessories and the existing to be handover to client at his storage at end of the project. | Item | 29 | 28.966 | 840.014 | 29 | 840.014
E14 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures including lamps electronic ballasts control gearwirescables and all necessary accessories complete as specified and as shown on the drawings | Item | 29 | 173.793 | 5039.997 | 29 | 5039.997
E15 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at all Bed Rooms | Item | 29 | 24.331 | 705.599 | 29 | 705.599
E16 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at all Salah | Item | 29 | 24.331 | 705.599 | 29 | 705.599
E17 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at all Majles | Item | 29 | 28.966 | 840.014 | 29 | 840.014
E18 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at all Kitchen | Item | 29 | 28.966 | 840.014 | 29 | 840.014
E19 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at all toilets | Item | 29 | 28.966 | 840.014 | 29 | 840.014
R |  | SUM FOR PAGE18/20 |  |  |  |  | 11491.25 |  | 11491.25
E20 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at all corridors | Item | 29 | 11.586 | 335.994 | 29 | 335.994
E21 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at staircase | Item | 29 | 11.586 | 335.994 | 29 | 335.994
E22 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at entrance | Item | 29 | 11.586 | 335.994 | 29 | 335.994
E23 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commissioning of the following lighting fixtures at boundary wall | Item | 29 | 11.586 | 335.994 | 29 | 335.994
E24 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commission of the following lighting fixtures at roof 4 corners and above the stair head room 4 corners | Item | 29 | 5.793 | 167.997 | 29 | 167.997
E25 | Electrical Engineering Installation | Lighting Fixture | Supply install connect test and commission of the following lighting fixtures Emergency light | Item | 29 | 17.379 | 503.991 | 29 |  | 29 | 503.991
E26 | Electrical Engineering Installation | Ceiling Fan | Supply install connect test and commission of celing fans | Item | 29 | 23.172 | 671.988 | 29 | 671.988
E27 | Electrical Engineering Installation | Earthing Installation | Supply install NEW Earthing system including 16 mm dia. high conductivity solid copper rod electrodes with drive head assemblies and Earthing clamps for earth pits Earthing of exposed pipe work sanitary fittings and equipment all as required including 300 x 300 x 400 mm deep internally earth pit earth wires as per specification and drawings complete with 300 mm x 300 mm medium duty double seal cast iron cover and frame. | Item | 29 | 28.963 | 839.927 | 29 | 839.927
S |  | SUM FOR PAGE19/20 |  |  |  |  | 3527.879 |  | 3023.888
E28 | Electrical Engineering Installation | TV Points and Dish Installation | Supply install NEW TV Satellite system all Data Cable with the dish above the roof and the concrete base and to connect it to the existing TV points all in functional conditions. | Item | 29 | 52.138 | 1512.002 | 29 | 1512.002
G1 | Sundrie | Sundrie Items | Any other works not specifically enumerated under the works in this bill but indicated in the drawings or required to complete the work in manner of respect to handover the project in working and safe conditions to the residents specification or needed to complete the work. | Item | 29 | 52.138 | 1512.002 | 29 | 1512.002
G2 | Sundrie | Sundrie Items | if any works was miss matching with any part of this tender documents the contractor must raise his queries during tender period and by submitting the offer the contractor confirming that every points was clear for him and confirming that is included at his price and no variation will be accepted | Item | 29 | 52.138 | 1512.002 | 29 | 1512.002
T |  | SUM FOR PAGE20/20 |  |  |  |  | 4536.006 |  | 4536.006
TOTAL MAINTENANCE HOUSING UNIT (29 NO.) | [6 empty] | 1436308.607 |  | 1426316.802 |  | 9991.805 |  | 11890 | Check Appendix - B for more Details

## APPENDIX - B
ADDITIONAL WORK | [5 empty] | APPENDIX - B
BILL NO 5. (29 MAINTENANCE HOSUNIG UNITS)
Bill Code | DESCRIPTIONS | BOQ ESTIMATE |  |  |  | Remark | Rate Reference | Clause
| Maintenance Housing Unit. | Unit | Plot Unit/No | Rate | Amount
Concrete Works RCC C30
C1 | Demolising and reconstruct of the entrance column, reinfore institute concrete, steel, formwork, plastering and painting with epoxy paint. | Item | 29 | 4.8126 |  | Not Part of the BOQ, subject to Variation Of Work |  | 12.2
200mm Block Wall
C30 In Ref. to Bill No. 4 | Building wall with lintel to close Salah Entrance which included: reinforced institute concrete, steel and formwork | Item | 29 | 6 | 174 | Not Part of the BOQ, subject to Variation Of Work | In Reference to Bill No. 4, Item Code C30 | 12.2
| Plastering/Rendering of the close wall to Salah Entrance. |  |  |  |  | Not Part of the BOQ, subject to Variation Of Work
C19 | Internal | Item | 29 | 1 | 29 |  | In Reference to Bill No. 5, Item Code C19 | 12.2
C20 | External | Item | 29 | 1 | 29 |  | In Reference to Bill No. 5, Item Code C20 | 12.2
| Painting/Decoration of the close wall to Salah Entrance |  |  |  |  | Not Part of the BOQ, subject to Variation Of Work
C19 | Internal | Item | 29 | 1 | 29 |  | In Reference to Bill No. 5, Item Code C19 | 12.2
C20 | External | Item | 29 | 1 | 29 |  | In Reference to Bill No. 5, Item Code C20 | 12.2
Door
C12 | Supply and Fix of Wood Door (New door frame for Salah) 1200mm x 2100mm door comprising profiled heads jambs frames subframes architraves beadings moldings plinth block ply linings infill panels mastic and other pointing fixings neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation ironmongery as specified in schedule and approved; fixed to hardwood All locks shall be 3 sets of keys Note to all stainless steel fittings shall be of 304 grade. | Item | 29 | 400 | 11600 | Not Part of the BOQ, subject to Variation Of Work | In Reference to C12, Item of the same description | 12.2
Tiles Works
C16 | Bedroom flooring preparing the surface to receive antislip ceramic tiles and supplying and fixing antislip ceramic tiles matching with existing floors.with supplying and fixing. (600 x 600 x 8 mm AntiSlip tiling to floor) | Item | 29 | 460.3846 |  | Not Part of the BOQ, subject to Variation Of Work | Rate in Reference to C16, Item of the same Materials | 12.2 | 3 | 87
C77 in Ref. Bill No. 4 | Bedroom Skirting (Ceramic Floor Tile - Tiles 600 X 150 X 8 Anti Slip) | Item | 29 | 48.4136 |  | Not Part of the BOQ, subject to Variation Of Work | Rate in Reference to Bill No. 4, Item Code C77 (1.658) | 12.2 | 3 | 87
C16 | Lobby flooring area preparing the surface to receive antislip ceramic tiles and supplying and fixing antislip ceramic tiles matching with existing floors.with supplying and fixing. (600 x 600 x 8 mm AntiSlip tiling to floor) | Item | 29 | 236.25 |  | Not Part of the BOQ, subject to Variation Of Work | Rate in Reference to C16, Item of the same Materials | 12.2 | 3 | 87
C77 in Ref. Bill No. 4 | Bedroom Skirting (Ceramic Floor Tile - Tiles 600 X 150 X 8 Anti Slip) | Item | 29 | 22.2172 |  | Not Part of the BOQ, subject to Variation Of Work | Rate in Reference to Bill No. 4, Item Code C77 (1.658) | 12.2 | 3 | 87
| Total |  |  |  | 11890
348

## BILL NO 6 (STORM WATER)
BILL NO. 6 (STORM WATER PROTECTION)
Item Code | Item Name | Item Details | Additional Information | Unit | Qty | Unit Price in Figure | BOQ Amount | Omission | Addition
PSW4 | Earthwork | Excavation for Structures Trenches | Unclassified structural excavation Depth 0 to required depth as per drawings Excavation by mechanical means using excavators JCB Porcelains etc. in soil any type to the required level for foundation excavation. Including soft rock and hard rock and any remaining material or elements for the existing building. Dispose of excavated material offsite by mechanical means as directed to the approval of the Client and consultant. Disposal is not measured separately mass excavation must be done. | m3 | 111780 | 1.05 | 117369 | [5 empty] | 4568
PSW8 | Earthwork | Backfill for structures trenched | Backfilling | m3 | 38975 | 0.525 | 20461.875 | [5 empty] | 3500
PSW9 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 0 to 2m | m3 | 9180 | 0.7 | 6426 | 6426
PSW10 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 2m to 2m | m3 | 12615 | 1.575 | 19868.625 | 19868.625
PSW11 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 3m to 4m | m3 | 3090 | 2.1 | 6489 | 6489
PSW12 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth more than 4m | m3 | 4080 | 4.2 | 17136 | 17136 |  |  | 24480.54
PSW13 | 3 Granular Subbase Aggregate Base Course and Stabilized Base Courses. | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Aggregate Base Course Class B | m3 | 1500 | 2.1 | 3150
PSW14 | 4 Bituminous Pavement | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Bituminous Prime Coat Application rate 1.5 KgSq.m | m3 | 4050 | 2.1 | 8505
PSW15 | Asphalt Road | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Bituminous Wearing Course Class B | m3 | 280 | 12.6 | 3528
PSW17 | Concrete and Concrete Structures | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Concrete Class 15 in foundations. | m3 | 130 | 13.65 | 1774.5
PSW18 | Concrete and Concrete Structures | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Concrete Class 35 in box culverts wing walls apron slab retaining walls and debris foundations. | m3 | 375 | 12.6 | 4725
0
PSW20 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | High tensile steel bar factory epoxy coated reinforcement of any diameter | Ton | 55 | 94.5 | 5197.5 |  |  | MESH 140
PSW22 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Tar or bituminous paint Type II 2 coats for surfaces in contact with earth in all structures | m2 | 1420 | 1.05 | 1491
PSW23 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Membrane Waterproofing Geotextile 4mm thickness | m2 | 15500 | 1.05 | 16275
PSW25 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 300mm | m | 315 | 3.15 | 992.25 | 992.25
PSW26 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 400mm | m | 1270 | 2.1 | 2667 | 2667
PSW27 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 500mm | m | 345 | 1.575 | 543.375 | 543.375
PSW28 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 600mm | m | 865 | 1.575 | 1362.375 | 1362.375
PSW29 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 700mm | m | 1090 | 2.1 | 2289 | 2289
PSW30 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 800mm | m | 460 | 2.1 | 966 | 966
PSW31 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 900mm | m | 130 | 3.15 | 409.5 | 409.5
PSW32 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 1200mm | m | 490 | 3.15 | 1543.5 | 1543.5
PSW34 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1200mm Type A | No | 48 | 3.15 | 151.2 | 151.2
PSW35 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1500mm Type A | No | 21 | 4.2 | 88.2 | 88.2
PSW36 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 2000mm Type A | No | 9 | 4.2 | 37.8 | 37.8
PSW37 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1500mm Type B | No | 8 | 4.2 | 33.6 | 33.6
PSW38 | Drainage | Manholes Inlets and Chambers | Gully Grating and Frame DI HEavy Duty | No | 145 | 4.305 | 624.225 | 624.225
PSW39 | Drainage | Manholes Inlets and Chambers | UPVC Drainage pipe to drain gully to manhole 200mm Diamter | No | 2010 | 4.305 | 8653.05 | 8653.05
PSW40 | Riprap | Riprap | Mortared stone riprap Class A including fillter membrane and fillter material 150 mm thickness. | m3 | 15315 | 0.84 | 12864.6
PSW41 | Slope protection and Stablization | Existing Dyke Improvement | Remove the existing dyke use the suitable backfilling and compact in the new place in layers as per Oman specifications shift not suitable existing backfilling materials to damp yard etc. | Item | 1 | 52.5 | 52.5 | [5 empty] | 3250
| TOTAL CONTRACT VALUE OF BILL NO. 6 | [5 empty] | 265674.675 | 70280.7 | 0 |  |  | -70280.7
11318

## Copy of BILL NO 6 (STORM WATER) (hidden)
Item Code | Item Name | Item Details | Additional Information | Unit | Qty | Unit Price in Figure | Actual QTY | Estimated Amount | Omission
PSW4 | Earthwork | Excavation for Structures Trenches | Unclassified structural excavation Depth 0 to required depth as per drawings Excavation by mechanical means using excavators JCB Porcelains etc. in soil any type to the required level for foundation excavation. Including soft rock and hard rock and any remaining material or elements for the existing building. Dispose of excavated material offsite by mechanical means as directed to the approval of the Client and consultant. Disposal is not measured separately mass excavation must be done. | m3 | 111780 | 1.05 |  |  | 117369
|  | DYKE 1 |  | m3 |  | 1.05 | 1142.41 | 1199.5305
|  | DYKE 2 |  | m3 |  | 1.05 | 1088.84 | 1143.282
|  | DYKE 2/4 |  | m3 |  | 1.05 | 257.03 | 269.8815
|  | Road Cutting |  | m3 |  | 1.05 | 1269.35 | 1332.8175
|  | Channel |  | m3 |  | 1.05 | 1416.92 | 1487.766
|  | Wadi Area |  | m3 |  | 1.05 | 5828.7 | 6120.135
|  | Access Road (Dyke 1 and 2) |  | m3 |  | 1.05 | 2686.96 | 2821.308
PSW8 | Earthwork | Backfill for structures trenched | Backfilling | m3 | 38975 | 0.525 |  |  | 20461.875
|  | Channel |  | m3 |  | 0.525 | 1416 | 743.4
|  | DYKE 1 |  | m3 |  | 0.525 | 405 | 212.625
|  | DYKE 2 |  | m3 |  | 0.525 | 12656.86 | 6644.8515
|  | DYKE 2/4 |  | m3 |  | 0.525 | 257.03 | 134.9407
PSW9 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 0 to 2m | m3 | 9180 | 0.7 |  |  | 6426
PSW10 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 2m to 2m | m3 | 12615 | 1.575 |  |  | 19868.625
PSW11 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth 3m to 4m | m3 | 3090 | 2.1 |  |  | 6489
PSW12 | Earthwork | Earthwork for pipe Trenches | Trench excavation and backfilling Depth more than 4m | m3 | 4080 | 4.2 |  |  | 17136
PSW13 | 3 Granular Subbase Aggregate Base Course and Stabilized Base Courses. | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Aggregate Base Course Class B | m3 | 1500 | 2.1 |  |  | 3150
PSW14 | 4 Bituminous Pavement | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Bituminous Prime Coat Application rate 1.5 KgSq.m | m3 | 4050 | 2.1 |  |  | 8505
PSW15 | Asphalt Road | Redesign and Construction of Asphalt Road to be suitable for Erection of Culvert with all necessary drawings details… | Bituminous Wearing Course Class B | m3 | 280 | 12.6 |  |  | 3528
PSW17 | Concrete and Concrete Structures | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Concrete Class 15 in foundations. | m3 | 130 | 13.65 |  |  | 1774.5
|  | Blinding to Channel |  | m3 |  | 13.65 | 45 | 614.25
PSW18 | Concrete and Concrete Structures | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Concrete Class 35 in box culverts wing walls apron slab retaining walls and debris foundations. | m3 | 375 | 12.6 |  |  | 4725
PSW20 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | High tensile steel bar factory epoxy coated reinforcement of any diameter | Ton | 55 | 94.5 |  |  | 5197.5
|  | Channel Works Between DYKE 2 and Maintenance |  |  |  | 94.5 | 61.86 | 5845.77
|  | Road Work concrete |  |  |  | 94.5 | 499.85 | 47235.825
[6 empty] | 94.5 | 250
PSW22 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Tar or bituminous paint Type II 2 coats for surfaces in contact with earth in all structures | m2 | 1420 | 1.05 |  |  | 1491
PSW23 | Concrete and Concrete structure | Construction of Box culvert N2 Size 2x1.5m concrete class 30 with reinforcement as per HDS 2017 including wing wall foundations bituminous paint excavation backfilling and as directed by Engineer | Membrane Waterproofing Geotextile 4mm thickness | m2 | 15500 | 1.05 |  |  | 16275
PSW25 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 300mm | m | 315 | 3.15 |  |  | 992.25
PSW26 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 400mm | m | 1270 | 2.1 |  |  | 2667
PSW27 | Drainage | Storm Sewer | Storm Sewer GRP Diamter 500mm | m | 345 | 1.575 |  |  | 543.375
PSW28 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 600mm | m | 865 | 1.575 |  |  | 1362.375
PSW29 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 700mm | m | 1090 | 2.1 |  |  | 2289
PSW30 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 800mm | m | 460 | 2.1 |  |  | 966
PSW31 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 900mm | m | 130 | 3.15 |  |  | 409.5
PSW32 | Drainage | Storm Sewer | Storm Sewer R.C Diamter 1200mm | m | 490 | 3.15 |  |  | 1543.5
PSW34 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1200mm Type A | No | 48 | 3.15 |  |  | 151.2
PSW35 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1500mm Type A | No | 21 | 4.2 |  |  | 88.2
PSW36 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 2000mm Type A | No | 9 | 4.2 |  |  | 37.8
PSW37 | Drainage | Manholes Inlets and Chambers | R.C Manholes Chamber Ring Dia. 1500mm Type B | No | 8 | 4.2 |  |  | 33.6
PSW38 | Drainage | Manholes Inlets and Chambers | Gully Grating and Frame DI HEavy Duty | No | 145 | 4.305 |  |  | 624.225
PSW39 | Drainage | Manholes Inlets and Chambers | UPVC Drainage pipe to drain gully to manhole 200mm Diamter | No | 2010 | 4.305 |  |  | 8653.05
PSW40 | Riprap | Riprap | Mortared stone riprap Class A including fillter membrane and fillter material 150 mm thickness. | m3 | 15315 | 0.84 |  |  | 12864.6
| Riprap | Riprap |  | m3 |  | 0.84 | 729.97 | 613.1748
| Polythene Sheet | Polythene sheet gauge 1200 |  |  |  | 2 | 1440 | 2880
PSW41 | Slope protection and Stablization | Existing Dyke Improvement | Remove the existing dyke use the suitable backfilling and compact in the new place in layers as per Oman specifications shift not suitable existing backfilling materials to damp yard etc. | Item | 1 | 52.5 |  |  | 52.5
A | TOTAL CONTRACT VALUE OF BILL NO. 6 | [6 empty] | 79299.5575 | 265674.675
B | SAVINGS | [6 empty] | 186375.1174
A-B=C | Contract Amount

## BILL NO 7. (3 NHU)
BILL NO 7. (3 NEW HOUSING UNITS) | [9 empty] | Omission |  | Addition
Item Code | Item Name | Item Details | Additional Information | UOM | BOQ-Quantity | Unit Price In Figure | BOQ Total Amount-OMR | REVISED QTY | REVISED AMOUNT (CLAIMABLE) | QUANTITIES | Amount | Quantities | Amount | ADDITION AMOUNT | APPENDIX
C1 | General Works | Demolishing and Clearing the Construction Area. | Demolishing the complete buildings up to foundations and removing the debris from the Construction Site as per Engineer/Employer Instruction (including cart-away from the Project Site) | LS | 1 | 2000 | 2000 | 1 | 2000
C2 | Substructure Works | Site Clearance | This shall include removing vegetation, undergrowth, bushes, hedges, trees, other temporary buildings, structures,... or the like all complete to clean the full plot. | LS | 1 | 1000 | 1000 | 1 | 1000
C3 | Substructure Works | Earth work and Excavation | Bulk Excavation to receive foundations in any kind of soil including hard soil and rock, earth sport, underground, surface or running water from whatever source if any, for the new foundation building area including removal of old buildings' foundations, cleaning the site, and removing all debris (not suitable for backfilling) from the project area to the damp yard, contractor to prepare all areas to receive new foundation safely as per drawings and soil report | M3 | 350 | 0.8 | 280 | 280 | 224 | 70 | 56
C4 | Substructure Works | Filling | Approved imported granular fill material compacted in layers in making up levels in the excavation area of the demolished buildings from foundation level up to levels on site plan. | M3 | 400 | 0.5 | 200 |  | 0 | 400 | 200
C5 | Substructure Works | Filling | Approved imported fill material compacted in layers to raise the levels | M3 | 200 | 0.5 | 100 |  | 0 | 200 | 100
C6 | Substructure Works | Filling | Approved, selected excavated material backfilled into excavations | M3 | 350 | 0.5 | 175 | 219.852 | 109.926 | 130.148 | 65.074
C7 | Substructure Works | Filling | 200 mm thick well compacted hardcore filling under floors | M3 | 35 | 0.5 | 17.5 |  | 0 | 35 | 17.5
A |  | SUM FOR PAGE1/42 |  |  |  |  | 3772.5 |  | 3333.926 |  | 438.574
C8 | Substructure Works | Anti-termite treatment | Anti-termite treatment to surfaces of ground or filling applied strictly in accordance with the manufacturers printed instructions including digging trenches, backfilling, etc. as required by the manufacturer and the provision of guarantee valid for 10 years | M2 | 150 | 1.5 | 225 | 97.76 | 146.64 | 52.24 | 78.36
C9 | Substructure Works | Poured Concrete - Plain insitu concrete, poured ordinary Portland Cement (OPC), concrete grade (C15), all in accordance with Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Blinding upto 100 mm thickness for the full area under the boundary of foundation. | M3 | 17.5 | 45 | 787.5 | 12.184 | 548.28 | 5.316 | 239.22
B |  | SUM FOR PAGE2/42 |  |  |  |  | 1012.5 |  | 694.92 |  | 317.58
C10 | Substructure Works | Reinforced insitu concrete, poured vibrated Sulphate Resistent Cement (OPC), concrete grade (C30), all in accordance with Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Footings | M3 | 45 | 50 | 2250 | 41.254 | 2062.7 | 3.746 | 187.3
C11 | Substructure Works | Plinth Beam | Plinth Beam | M3 | 14 | 50 | 700 | 10.829 | 541.45 | 3.171 | 158.55
C |  | SUM FOR PAGE3/42 |  |  |  |  | 2950 |  | 2604.15 |  | 345.85
C12 | Substructure Works | Reinforced insitu concrete, poured vibrated Sulphate Resistent Cement (OPC), concrete grade (C30), all in accordance with Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Steel fabric reinforcement, A-393 BRC mesh in two layers. All complete in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Beds (Slabs, Grade slabs) upto 200 mm thickness | M3 | 30 | 50 | 1500 | 20.112 | 1005.6 | 9.888 | 494.4
D |  | SUM FOR PAGE4/42 |  |  |  |  | 1500 |  | 1005.6 |  | 494.4
C13 | Substructure Works | Reinforced insitu concrete, poured vibrated ordinary Portland Cement (OPC), concrete grade (C40), all in accordance with Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Substructure columns | M3 | 4 | 50 | 200 | 3.463 | 173.15 | 0.537 | 26.85
C14 | Substructure Works | Concrete / Block work Protection | Polythene sheet, gauge 1200, all in accordance with Drawings and Specifications - to surfaces of structural members in contact with soil | M2 | 115 | 0.5 | 57.5 | 85.34 | 42.67 | 29.66 | 14.83
C15 | Substructure Works | Bitumenous Sheet | Bitumenous Paint base coat and 4mm membrane to the surfaces of concrete and block work( foundation + solid block work + short columns ) | M2 | 300 | 5 | 1500 |  | 0 | 300 | 1500
C16 | Substructure Works | Bitumenous Paint | Bitumenous paint 3 coats to the surfaces of concrete ( plinth beams ) | M2 | 145 | 0.5 | 72.5 |  | 0 | 145 | 72.5
E |  | SUM FOR PAGE 5/42 |  |  |  |  | 1830 |  | 215.82 |  | 1614.18
C17 | Substructure Works | Concrete solid block work, 10.5N/mm2 compressive strength, cement and sand mortar (1:3), with and including stiffener columns and stiffener beams, as required, all in accordance with Drawings and Specifications | 200mm thick walls | M2 | 120 | 6 | 720 | 70.922 | 425.532 | 49.078 | 294.468
C18 | Substructure Works | Block work Protection including Bitumenous Paint and Bitumenous Sheet | Protection to concrete and excavated area, masonry/block work in contact with soil, Bitumenous Paint base coat of approved bituminous paint, 4mm bituminous sheet, and including flexible board all in accordance with Drawings and Specifications - to surfaces of block work in contact with soil.up to bottom of plinth beams | M2 | 250 | 1 | 250 | 250 | 250 | 0 | 0
C19 | Substructure Works | The Contractor should read and quote as per the supply, laying, and all works are included and required approval & commissioning as per contract standards should be under the Contractor scope of work including required charges, also including DNP scope and guarantees for material. | Important Note | Item | 0 | 0 | 0 |  | 0
F |  | SUM FOR PAGE 6/42 |  |  |  |  | 970 |  | 675.532 |  | 294.468
C20 | Substructure Works | The Contractor is adviced to complete the project as per the drawing, boq and specification also need to complete if anything missing in the drawing but mentioned in the boq/specification and viceversa. Should the Tenderer fail to insert any item here, it will be deemed that this lump sum price for the tender includes all items and no subsequent claim for any additional items will be entertained | Important Note | Item | 0 | 0 | 0 |  | 0
C21 | Substructure Works | The Contractor is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum tender price for this section of the works. Should the Tenderer fail to insert any item here, it will be deemed that this lump sum price for the tender includes all items and no subsequent claim for any additional items will be entertained | Important Note | Item | 0 | 0 | 0 |  | 0
|  | SUM FOR PAGE 7/42 |  |  |  |  | 12035 |  | 8529.948 |  | 3505.052 |  | 0 | 0
C22 | Superstructure Works Concrete Works | Poured Concrete - Reinforced insitu concrete, poured vibrated Ordinary Portland Cement (OPC), concrete grade (C30), all in accordance with the Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Suspended slabs, waist slabs, landings,stair etc. not exceeding 250 mm thickness | M3 | 30 | 50 | 1500 | 30 | 1500
C23 | Superstructure Works Concrete Works | Poured Concrete - Reinforced insitu concrete, poured vibrated Ordinary Portland Cement (OPC), concrete grade (C30), all in accordance with the Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Columns | M3 | 10 | 50 | 500 | 10 | 500
H |  | SUM FOR PAGE 8/42 |  |  |  |  | 2000 |  | 2000 |  | 0
C24 | Superstructure Works Concrete Works | Poured Concrete - Reinforced insitu concrete, poured vibrated Ordinary Portland Cement (OPC), concrete grade (C30), all in accordance with the Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Beams | M3 | 15 | 50 | 750 | 15 | 750
C25 | Superstructure Works Concrete Works | Poured Concrete - Reinforced insitu concrete, poured vibrated Ordinary Portland Cement (OPC), concrete grade (C30), all in accordance with the Drawings and Specifications and including Reinforcement - High yield strength deformed bars, conforming to BS 4449 (grade 460) including cutting, bending, binding, binding wire, cover blocks, tests and all necessary fixing accessories, all in accordance with the Drawings and Specifications and including Formwork to give (as struck) finish - Providing and erecting formwork including all necessary staging, centering, shuttering, supports, cross bracing, de-shuttering carefully, making good the damaged surfaces wherever necessary, all complete as specified and as directed by the Engineer all in accordance with the Drawings and Specifications | Ramp and Entrances Stairs | M3 | 3 | 45 | 135 | 3 | 135
C26 | Superstructure Works Masonry | Internal Walls - Ordinary Portland cement concrete blocks, 7.5N/mm2 compressive strength, cement and sand mortar (1:3), with and including stiffener columns and stiffener beams, as required, all in accordance with the Drawings and Specifications | 200mm thick walls | M2 | 260 | 6 | 1560 | 260 | 1560
C27 | Superstructure Works Masonry | Sunken Slab Waterproofing | Providing and applying Sunken Slab Waterproof course with bituminous paint and bituminous membrane conforming to BS:6398 in horizontal joints laid strictly in compliance with approved manufacturers printed instructions and as directed by Engineer. | M2 | 20 | 2 | 40 | 20 | 40
I |  | SUM FOR PAGE 9/42 |  |  |  |  | 2485 |  | 2485 |  | 0
C28 | Superstructure Works Thermal and Moisture Protection | Backgrounds and Finishes - Roof screed, light weight concrete screed 1000 kg/m3, minimum 50 mm thick to a maximum of 125 mm thick | 50 mm (minimum) bed laid on concrete to falls and cross falls | M2 | 130 | 25 | 3250 | 130 | 3250
C29 | Superstructure Works Thermal and Moisture Protection | 4 mm thick torch applied acrylic polypropylene modified bitumen membrane with non-woven polyester reinforcement and polyethylene film waterproof membrane including primer to roofs as per the manufacturer printed instructions complete as specified. (Contractor to allow for 10 years guarantee and 24 hours flood test) | To roof decks, 4mm thick, on flat surface, laid to falls and cross falls | M2 | 130 | 1.5 | 195 | 130 | 195
C30 | Superstructure Works Thermal and Moisture Protection | Skirting 300 mm girth including turning into groove | In up stands/drops and around plinths (minimum 300 mm high) including dressing over fillet grooves, sealant, tantalized batten etc. complete, to roof deck | LM | 85 | 1 | 85 | 85 | 85
C31 | Superstructure Works Thermal and Moisture Protection | Insulation - Extruded high density polystyrene foam board insulation, with rigid closed cell structure, all in accordance with the specifications and drawings, external | to roof decks - 50 mm thick, laid on concrete, spot bonded to waterproofing | M2 | 130 | 2 | 260 | 130 | 260
I |  | SUM FOR PAGE 10/42 |  |  |  |  | 3790 |  | 3790
C32 | Superstructure Works Thermal and Moisture Protection | Roof Finishes | 300 x 300 x 30 mm white cement tiles bedded on and including cement mortar screed to falls and cross falls, jointed in cement mortar, movements joints etc., complete - to roof | M2 | 130 | 0.5 | 65 | 130 | 65
C33 | Superstructure Works Thermal and Moisture Protection | Roof Finishes | 100 x 30 mm white cement skirting to upstands | LM | 85 | 1 | 85 | 85 | 85
C34 | Superstructure Works Thermal and Moisture Protection | Roof Sundries | Allow for Providing dressing around 110mm/83mm UPVC rainwater outlets roof duct, gargoyle, extract fan, soil and vent pipe | No | 5 | 0 | 0 | 5 | 0
C36 | Superstructure Works Metal Works | Staircase hand rail | Stainless steel handrail as shown in the Architectural drawing, shop drawings with full sections details to be approved before supply. Note : all stainless steel material shall be of 316 grade. | LM | 10 | 15 | 150 | 10 | 150
C37 | Superstructure Works Metal Works | CAT Ladder | Supply and install a 3800mm high CAT steel Ladder as specified and detailed on the drawing, with anti-correlation epoxy pain. | No | 1 | 100 | 100 | 1 | 100
I |  | SUM FOR PAGE 11/42 |  |  |  |  | 400 |  | 400
C42 | Superstructure Works Doors and Windows | Wood Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, mouldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardwood, including paint (All locks shall be under master key system) as detailed on drawing Note : all stainless steel fittings shall be of 316 grade | Type D1, double leaf, overall size 1800x2500mm high | No | 1 | 355 | 355 | 1 | 355 | 1 | 355 | 1 | 355 |  | Replaced with Aluminium Door - Check Appendix C
C43 | Superstructure Works Doors and Windows | Wood Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, mouldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardwood, including paint (All locks shall be under master key system) as detailed on drawing Note : all stainless steel fittings shall be of 316 grade | Type D2, single leaf, overall size 1000x2500mm high | No | 1 | 410 | 410 | 1 | 410 | 1 | 410 | 1 | 410 |  | Replaced with Aluminium Door - Check Appendix C
C44 | Superstructure Works Doors and Windows | Wood Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, mouldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardwood, including paint (All locks shall be under master key system) as detailed on drawing Note : all stainless steel fittings shall be of 316 grade | Type D3, single leaf, overall size 1000x2100mm high | No | 4 | 400 | 1600 |  | 0 | 4 | 1600
C45 | Superstructure Works Doors and Windows | Wood Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, mouldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardwood, including paint (All locks shall be under master key system) as detailed on drawing Note : all stainless steel fittings shall be of 316 grade | Type D4, single leaf overall size 800x2100mm high | No | 2 | 400 | 800 |  | 0 | 2 | 800
C46 | Superstructure Works Doors and Windows | Wood Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, mouldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardwood, including paint (All locks shall be under master key system) as detailed on drawing Note : all stainless steel fittings shall be of 316 grade | Type D5, single leaf overall size 1000x2100mm high | No. | 1 | 400 | 400 | 1 | 400
C47 | Superstructure Works Doors and Windows | Wood Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, mouldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardwood, including paint (All locks shall be under master key system) as detailed on drawing Note : all stainless steel fittings shall be of 316 grade | Type D6, single leaf overall size 1000x2400mm high | No | 1 | 400 | 400 | 1 | 400
C48 | Superstructure Works Doors and Windows | WPC Solid Core Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, moldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardcore, including paint and 10 years guarantee (All locks shall be under master key system) as detailed on drawing Note: all stainless steel fittings shall be of 316-grade | Type D1, double leaf, overall size 1800x2500mm high | Item | 1 | 400 | 400 | 1 |  | 1 | 400
C49 | Superstructure Works Doors and Windows | WPC Solid Core Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, moldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardcore, including paint and 10 years guarantee (All locks shall be under master key system) as detailed on drawing Note: all stainless steel fittings shall be of 316-grade | Type D2, single leaf, overall size 1000x2500mm high | Item | 1 | 400 | 400 | 1 |  | 1 | 400
C50 | Superstructure Works Doors and Windows | WPC Solid Core Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, moldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardcore, including paint and 10 years guarantee (All locks shall be under master key system) as detailed on drawing Note: all stainless steel fittings shall be of 316-grade | Type D3, single leaf, overall size 1000x2100mm high | Item | 1 | 400 | 400 | 1 | 400
C51 | Superstructure Works Doors and Windows | WPC Solid Core Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, moldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardcore, including paint and 10 years guarantee (All locks shall be under master key system) as detailed on drawing Note: all stainless steel fittings shall be of 316-grade | Type D4, single leaf overall size 800x2100mm high | Item | 1 | 400 | 400 | 1 | 400
C52 | Superstructure Works Doors and Windows | WPC Solid Core Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, moldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardcore, including paint and 10 years guarantee (All locks shall be under master key system) as detailed on drawing Note: all stainless steel fittings shall be of 316-grade | Type D5, single leaf overall size 1000x2100mm high | Item | 1 | 400 | 400 | 1 |  | 1 | 400
C53 | Superstructure Works Doors and Windows | WPC Solid Core Doors -Door comprising profiled heads, jambs, frames, subframes, architraves, beadings, moldings, plinth block, ply linings, infill panels, mastic and other pointing, fixings, neoprene seal master lining and all ancillary items including fixing of ironmongery and final decoration for a complete installation all as specified and as detailed on drawing including required reinforcement cement concrete lintels and including Supply and fix ironmongery as specified in schedule and approved; fixed to hardcore, including paint and 10 years guarantee (All locks shall be under master key system) as detailed on drawing Note: all stainless steel fittings shall be of 316-grade | Type D6, single leaf overall size 1000x2400mm high | Item | 1 | 400 | 400 | 1 |  | 1 | 400
C54 | Superstructure Works Doors and Windows | Ironmongery - Supply and fix of ironmongery, with and including all necessary fixing accessories and screws to match, all in accordance with the specifications and drawings - to wood doors | Allow for grand master key and master key system | Item | 1 | 100 | 100 | 1 | 100
C55 | Superstructure Works Doors and Windows | UPVC windows -window sets complete with all necessary ironmongery as specified, including fixing to blockwork or concrete and mastic pointing all around, all as specified and detailed on drawing and including required reinforcement cement concrete lintels | Type W1, overall size 2000 x 1300mm high | No | 13 | 50 | 650 | 13 | 650
C56 | Superstructure Works Doors and Windows | UPVC windows -window sets complete with all necessary ironmongery as specified, including fixing to blockwork or concrete and mastic pointing all around, all as specified and detailed on drawing and including required reinforcement cement concrete lintels | Type W2, overall size 1200 x 900mm high, | No | 1 | 50 | 50 | 1 | 50
C57 | Superstructure Works Doors and Windows | UPVC ventilator -ventilator sets complete with all necessary ironmongery as specified, including fixing to blockwork or concrete and mastic pointing all around, all as specified and detailed on drawing and including required reinforcement cement concrete lintels | Type V, overall size 600 x 600mm high | No | 2 | 50 | 100 | 2 | 100
C58 | Superstructure Works Finishes | Backgrounds - Plaster, cement and sand (1:3), internal - To walls and columns, on concrete block base, internal including stainsteel mesh, butterfly angle between the concrete column and block work. | to receive internal painting | M2 | 600 | 1 | 600 | 600 | 600
C59 | Superstructure Works Finishes | Backgrounds - Plaster, cement and sand (1:4), external - To walls and columns, on concrete block base, external including stainsteel mesh, butterfly angle between the concrete column and block work. | to receive external painting | M2 | 480 | 1.5 | 720 | 480 | 720
C60 | Superstructure Works Finishes | Allow for laying of Marble Threshold as per the specifications, drawings and to approval of the Engineer. | Internal Floor Tile | NO | 1 | 500 | 500 | 1 | 500
C61 | Superstructure Works Finishes | Floor Tiles: FF1 Ceramic floor tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specification/instruction; internally | 600 x 600 x 8 mm Anti-Slip tiling to floor | M2 | 85 | 3 | 255 | 85 | 255
C62 | Superstructure Works Finishes | Floor Tiles: FF2 Ceramic floor tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specification/instruction; internally | 600 x 600 x 8 mm Anti-Slip tiling to floor | M2 | 12 | 3 | 36 | 12 | 36
C63 | Superstructure Works Finishes | Floor Tiles: FF3 Ceramic floor tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specification/instruction; internally | 600 x 200 x 8 mm Anti-Slip tiling to floor | M2 | 10 | 3 | 30 | 10 | 30
C64 | Superstructure Works Finishes | Floor Tiles: FF4 30mm tk. Granite laid on screed grouted with waterproof coloured compatible mortar to manufacturers specification/instruction; internally | 30mm thick Granite for Staircase and Steps | M2 | 20 | 4 | 80 | 20 | 80
C65 | Superstructure Works Finishes | Floor Tiles: FF9 Granite tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specification/instruction; internally | 30mm thick Granite for Entrance floor and Staircase and Steps | M2 | 5 | 4 | 20 | 5 | 20
C66 | Superstructure Works Finishes | Skirting Tiles: FF1 Ceramic tiles laid on screed grouted with waterproof coloured compatible mortar to manufacturers specification/instruction; internally | Ceramic Tiles 600 X 150 X 8 Anti Slip | LM | 100 | 3 | 300 | 100 | 300
C67 | Superstructure Works Finishes | Skirting Tiles: FF4 30mm tk. Granite laid on screed grouted with waterproof coloured compatible mortar to manufacturers specification/instruction; internally | 30mm thick Granite for Staircase and Steps | LM | 20 | 4 | 80 | 20 | 80
C69 | Superstructure Works Finishes | Allow for construction of Decorative projection, weather coat stoneshield with 10 years garantee as per the specifications, drawings and to approval of the Engineer | F1/F2 External Elevation | M2 | 470 | 5 | 2350 | 470 | 2350
C70 | Superstructure Works Finishes | Allow for construction of Decorative projection as per the specifications, drawings and to approval of the Engineer | F3 External Elevation | Item | 10 | 5 | 50 | 10 | 50
C71 | Superstructure Works Finishes | Wall Finishes - FF1 Painting and decorating, Eligance marble paint finish internal | Smooth Plaster, Painting, Anti Fungal and Water Resistance | M2 | 300 | 1 | 300 | 300 | 300
C72 | Superstructure Works Finishes | Wall Finishes - FF2 Ceramic Tiles 600 X 200 X 8 Anti Slip | Ceramic Tiles 600 X 200 X 20 Anti Slip | M2 | 40 | 3 | 120 | 40 | 120
C73 | Superstructure Works Finishes | Wall Finishes - FF3 Ceramic Tiles 600 X 200 X 8 Anti Slip | Ceramic Tiles 600 X 200 X 20 Anti Slip | M2 | 65 | 3 | 195 | 65 | 195
C74 | Superstructure Works Finishes | Wall Finishes - FF4 Smooth Plaster, Painting,Eligance marble paint finish Anti Fungal and Water Resistance | Smooth Plaster, Painting, Anti Fungal and Water Resistance | M2 | 160 | 1 | 160 | 160 | 160
C75 | Superstructure Works Finishes | Ceilings Finishes - FF1 Painting and decorating,Eligance marble paint finish internal | Smooth Plaster, Painting, Anti Fungal and Water Resistance | M2 | 85 | 1 | 85 | 85 | 85
C76 | Superstructure Works Finishes | Ceilings Finishes - FF2 Smooth Plaster, Painting,Eligance marble paint finish Anti Fungal and Water Resistance | Smooth Plaster, Painting, Anti Fungal and Water Resistance | M2 | 12 | 1 | 12 | 12 | 12
C77 | Superstructure Works Finishes | Ceilings Finishes - FF3 Smooth Plaster, Painting, Eligance marble paint finish Anti Fungal and Water Resistance | Smooth Plaster, Painting, Anti Fungal and Water Resistance | M2 | 10 | 1 | 10 | 10 | 10
C78 | Superstructure Works Finishes | Ceilings Finishes - FF4 Smooth Plaster, Painting, Eligance marble paint finish Anti Fungal and Water Resistance | Smooth Plaster, Painting, Anti Fungal and Water Resistance | M2 | 20 | 1 | 20 | 20 | 20
C79 | Superstructure Works Finishes | Allow for supply, fabricate and installation of Gas Cyclinder Stage as per the specifications, drawings and to approval of the Engineer. | Gas Cylinder Stage | Item | 1 | 75 | 75 | 1 | 75
C80 | Superstructure Works Finishes | Allow for core-cut, remove and smooth finish as per the specifications, drawings and to approval of the Engineer. | Drain Open to connect Sewage Tanker to the Holding Tank, size 550 X 400mm | Item | 1 | 100 | 100 | 1 | 100
C81 | Superstructure Works Finishes | Allow for supply, fabricate and installation of water point protection as per the specifications, drawings and to approval of the Engineer. | Water point protection | Item | 1 | 50 | 50 | 1 | 50
C82 | Superstructure Works Finishes | Allow for supply, fabricate and installation of Meter Panel protection as per the specifications, drawings and to approval of the Engineer. | Meter Panel protection | Item | 1 | 100 | 100 | 1 | 100
C83 | Superstructure Works Finishes | Allow for supply, fabricate and installation of Kitchen Stage including Stage Concrete, Stage Korean Top and Stage Area Ceramic Wall Tile as per the specifications, drawings and to approval of the Engineer. | Kitchen Stage Concrete, Korean Top, Ceramic Wall Tiles | Item | 1 | 500 | 500 | 1 | 500
C84 | Superstructure Works Finishes | Allow for supply, fabricate and installation of Kitchen Hood Range including Aluminum Kitchen Cabinet above, and Aluminum Kitchen Cabinet below all as per the specifications, drawings and to approval of the Engineer. | Kitchen Hood Range, Cabinet above and below Cabinet. | Item | 1 | 200 | 200 | 1 | 200
EW1 | External Works - General Site Works | Boundary wall | Allow for the Contractor to prepare RCC foundation, column, block work, plastering and painting as per the Architectural Drawing and as per Engineer / Employer Instruction to complete the Boundary Wall. | LM | 128 | 100 | 12800 | 128 | 12800
EW4 | External Works - General Site Works | Entrance Gate | Allow for the Contractor to supply, fabricate and installation of Wicket Gate solid WPC with 10 years garantee as per the Architectural Drawing and follow as per Engineer / Employer Instructions, including anti corrotion epoxy paint. | NO | 1 | 1500 | 1500 | 1 | 1500
EW5 | External Works - General Site Works | Wicket Gate | Single leaf Wicket Gate solid WPC | Item | 1 | 900 | 900 | 1 | 900
EW6 | External Works - General Site Works | Car Entrance Gate | Single leaf Car Entrance Gate soild WPC | Item | 1 | 1200 | 1200 | 1 | 1200
EW7 | External Works - General Site Works | Entrance Concrete Paver | Allow for the Contractor to prepare Concrete Paver as per the Architectural Drawing and place at the House Main Entrance. | No | 20 | 44 | 880 | 20 | 880
EW8 | External Works - General Site Works | Interlock Tile | Allow for connection Asphalt road to the site from the main drawing as per approval | M2 | 180 | 5 | 900 | 180 | 900
EW9 | External Works - General Site Works | Curb Stone | Allow for connection Asphalt road to the site from the main drawing as per approval | LM | 80 | 8 | 640 | 80 | 640
EW10 | External Works - General Site Works | Design and Build Shaded Car Parking of 20 numbers with Solar Panel Canopy | Allow for the Contractor to design and build the Shaded Car Park for houses with Solar Panel Canopy, as per Engineer / Employer Instruction. | Item | 1 | 1300 | 1300 |  | 0 | 1 | 1300
P2 | Sanitary Installation | ditto | 160mm diamater | M | 40 | 10 | 400 | 40 | 400
P3 | Sanitary Installation | ditto | 110mm diamater | M | 6 | 8 | 48 | 6 | 48
P4 | Sanitary Installation | ditto | 82mm diameter | M | 7 | 8 | 56 | 7 | 56
P5 | Sanitary Installation | ditto | 50mm diameter | M | 8 | 8 | 64 | 8 | 64
P6 | Sanitary Installation | ditto | 42mm diameter | M | 8 | 8 | 64 | 8 | 64
P7 | Sanitary Installation | vent cowl | Vent cowl with weathering apron 50mm diameter | No | 2 | 8 | 16 | 2 | 16
P8 | Sanitary Installation | Floor Drain trap | Floor Trap with 150 X 150 mm SS grating Cover | No | 3 | 25 | 75 | 3 | 75
P9 | Sanitary Installation | Gully Trap | 300 mm and 300 mm gully trap of approximate 300 mm depth set in concrete Grade 30 Nmm� joints to drain pipes complete with 300 mm and 300 mm medium duty cast iron cover and frame. | No | 2 | 30 | 60 | 2 | 60
P10 | Grease Trap | Grease Trap | 300 mm and 300 mm grease trap of approximate 300 mm depth set in concrete Grade 30 Nmm� joints to drain pipes complete with 300 mm and 300 mm medium duty cast iron cover and frame. | No | 1 | 30 | 30 | 1 | 30
P11 | Sanitary Installation | Inspection Chambers | Manhole size 600 and 600 mm internally upto 1.24m deep to invert | No | 7 | 180 | 1260 | 7 | 1260
P12 | Sanitary Installation | Manhole Cover | 600 and 600 mm medium duty double seal cast iron manhole cover and frame. | No | 7 | 110 | 770 | 7 | 770
P13 | Sanitary Installation | Holding tank with soak pit | Reinforced concrete grade 30 N mm2 holding tank size 4000 and 2000 and 2500 mm deep internally with concrete grade 15 N mm2 and 100mm thick blinding and 250mm thick concrete base slab and 200mm thick concrete wall and roof slab and including reinforcement and formwork and rendering and step irons and 3 coats of bitumen paint and 2 layer of 1000 gauge polythene sheet and excavation and dewatering backfilling and disposal of surplus excavated materials and 600 and 600 mm heavy duty double seal ductile iron cover and frame and Precast concrete soak pit size 2000 mm diameter and 2500 mm deep internally including reinforcement and excavation and dewatering and backfilling and disposal of surplus excavated materials 600 and 600 mm heavy duty ductile iron cover and frame et as detailed on drawing. | No | 1 | 5000 | 5000 | 1 | 5000
J |  | SUM FOR PAGE 32/42 |  |  |  |  | 42176 |  | 36876
P14 | Sanitary Wares and Fittings | Semi pedestal wash basin | 650 mm and 475 mm vitreous china white wash basin with semi pedestal and center tap hole and overflow and bottle trap including required complete Civil Works. | No | 2 | 85 | 170 | 2 | 170
P15 | Sanitary Wares and Fittings | Stainless Steel Sink | 1000 mm and 550 mm stainless steel sink single bowl single drainer with drainboard to BS 1244 complete with 2 piece tubular P trap chain and plug and waste and brackets including required complete Civil Works. | No | 1 | 120 | 120 | 1 | 120
P16 | Sanitary Wares and Fittings | European Water Closet | 400 mm and 685 mm vitreous china white concealed tank wall hung mounted EWC squatting pan built in wall toilet dual flush 3L or 6L concealed cistern and heavy duty auto closed seat and cover including required complete Civil Works. | No | 2 | 100 | 200 | 2 | 200
P17 | Sanitary Wares and Fittings | Faucet spray | Chromium plated approved ablution faucet with angle valve and hose and spray unit. | No | 2 | 25 | 50 | 2 | 50
P18 | Sanitary Wares and Fittings | Wash Basin Mixer | Single lever chrome plated wash basin mixer including pop up waste. | No | 2 | 40 | 80 | 2 | 80
P19 | Sanitary Wares and Fittings | Sink Mixer | Single lever chrome plated Sink mixer. | No | 1 | 40 | 40 | 1 | 40
P20 | Sanitary Wares and Fittings | Toilet tissue holder | Recessed type stainless steel Toilet tissue dispenser or holder with stainless steel hood. | No | 2 | 15 | 30 | 2 | 30
P21 | Sanitary Wares and Fittings | Towel rail | 610 and 75 and 75 mm towel rail | No | 2 | 15 | 30 | 2 | 30
P22 | Sanitary Wares and Fittings | Mirror | 450 and 600 mm mirror 6 mm thick and bevel edged and plywood backing fixed with chromium plated dome headed screws | No | 2 | 15 | 30 | 2 | 30
P23 | Sanitary Wares and Fittings | Bath shower | Single lever dual control bath shower mixer | No | 2 | 40 | 80 | 2 | 80
P24 | Sanitary Wares and Fittings | Bip tap | For internal and external. | No | 2 | 15 | 30 | 2 | 30
P26 | Sanitary Installation | Hpupvc pipe | 25 mm diameter pipe for air conditioner drainage pipe to ac drain pit. | M | 24 | 12 | 288 | 24 | 288
P28 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 15 mm diameter | M | 28 | 10 | 280 | 28 | 280
P29 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 20 mm diameter | M | 10 | 15 | 150 | 10 | 150
P30 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 25 mm diameter | M | 4 | 20 | 80 | 4 | 80
P31 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 32 mm diameter | M | 30 | 25 | 750 | 30 | 750
P32 | Water Supply installation | Cold and Hot water PPR C pipes with insulation | 40 mm diameter | M | 29 | 30 | 870 | 29 | 870
P34 | Water Supply installation | Cold and Hot water Valves | 15 mm diameter | No | 10 | 25 | 250 | 10 | 250
P35 | Water Supply installation | Cold and Hot water Valves | 20 mm diameter | No | 8 | 25 | 200 | 8 | 200
P36 | Water Supply installation | Cold and Hot water Valves | 32 mm diameter | No | 4 | 35 | 140 | 4 | 140
P37 | Water Supply installation | Cold and Hot water Valves | 32 mm diameter isolating value | No | 2 | 35 | 70 | 2 | 70
P38 | Water Supply installation | Cold and Hot water Valves | 40 mm diameter | No | 2 | 40 | 80 | 2 | 80
P40 | Water Supply installation | Water Tank | 600 US gallon capacity GRP type water storage tank with foundation epoxy coated frame ball valve overflows etc to approval | No | 1 | 2500 | 2500 | 1 | 2500
P41 | Water Supply installation | Water Heater | 50 liter capacity horizontal type copper tank high level wall mounted electrical water heater including all connections and fixing. | No | 2 | 150 | 300 | 2 | 300
P42 | Water Supply installation | Booster pump | Cold water pressurised booster pump set 1No Working pump and 1No standby pump for domestic water supply delivering 2 l per sec at 2.5 bar with Gate valve and Non return valve and float switch and pressue guage and pressure vessel 30 to 50 lit PN10 and water low level cut off relay etc with pump room all complete as detailed in the drawing to approval. | No | 1 | 1500 | 1500 |  |  | 1 | 1500
P44 | Rain Water Installation | Rain Water UPVC Pipes | 110mm diamater | M | 24 | 25 | 600 | 24 | 600
P45 | Rain Water Installation | Rain water Outlet | 110 mm diameter root terminal socket tail rain water outlet. | No | 4 | 25 | 100 | 4 | 100
P51 | Plumbing and Drainage System | Sundries | Allow for testing and commissioning of underground cable prior to and after backfilling. | Item | 1 | 500 | 500 | 1 | 500
F2 | Fire Fighting Installation | Fire Extinguisher | 2 Kg carbon dioxide fire extinguisher | No | 1 | 10 | 10 | 1 | 10
F3 | Fire Fighting Installation | Fire Extinguisher | 180 and 180 mm fire blanket | No | 1 | 15 | 15 | 1 | 15
F4 | Fire Fighting Installation | Fire alarm cable and conduits and panel and accessories installation | Automatic Multi detector point | No | 1 | 15 | 15 | 1 | 15
G1 | Gas supply line | Gas line | Supply and fix 18 mm diameter MS schedule 40 gas pipeline including pickup points and connection to Gas Stove | M | 10 | 50 | 500 | 10 | 500
M1 | Air Conditioning and Ventilation Installation | High level Wall mounted Split AC with DX unit | 12000 BTU HR capacity high level wall mounted split type air conditioner including connection to electrical outlet and concrete base foundation. | No | 1 | 450 | 450 | 1 | 450
M2 | Air Conditioning and Ventilation Installation | High level Wall mounted Split AC with DX unit | 18000 BTU HR capacity high level wall mounted split type air conditioner including connection to electrical outlet and concrete base foundation. | No | 4 | 600 | 2400 | 4 | 2400
E1 | SUB MAIN DISTRIBUTION BOARD | Sub Main Distribution Board | Sub Main Distribution panel board in weather proof Stainless steel enclosure IP 65 including 1nos 200A MCCB and 3 NOS 63A,63A,45A MCCB Outgoing Breakers and supports and Busbar and earthing and cable glands and Ammeters and Voltmeters and internal wiring interconnection 1PH 3PH KWH series meters and labels as per approved MHEW drawings | No | 1 | 600 | 600 | 1 | 600
E5 | Electrical Engineering Installation | Distribution Board | 63A TPN 10 way DBs | No | 1 | 50 | 50 | 1 | 50
E6 | Electrical Engineering Installation | Distribution Board | 63A TPN 10 way DBs | No | 1 | 50 | 50 | 1 | 50
E7 | Electrical Engineering Installation | Distribution Board | 45A TPN 6way DBs | No | 1 | 45 | 45 | 1 | 45
E9 | Electrical Engineering Installation | Cable | 4C and 35 mm� + 1C and 25 mm� ECC from SMDBs to DB1 | M | 25 | 15 | 375 | 25 | 375
E10 | Electrical Engineering Installation | Cable | 4C and 35 mm� + 1C and 25 mm� ECC from SMDBs to DB2 | M | 30 | 15 | 450 | 30 | 450
E11 | Electrical Engineering Installation | Cable | 4C and 25 mm� + 1C and 16 mm� ECC from SMDB to DB3 | M | 35 | 10 | 350 | 35 | 350
E19 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 13A DP twin switched socket outlet | No | 21 | 6 | 126 | 21 | 126
E20 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 30A cooker socket | No | 1 | 6 | 6 | 1 | 6
E21 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 20A DP flux outlet for AC | No | 5 | 6 | 30 | 5 | 30
E22 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 20A weatherproof DP flux outlet for WH | No | 2 | 6 | 12 | 2 | 12
E23 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 13 A unswitched fused spur unit outlet for EF | No | 3 | 6 | 18 | 3 | 18
E24 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 20A Dp switch for WH and AC | No | 7 | 6 | 42 | 7 | 42
E25 | Electrical Engineering Installation | Small Power Accessories and cable and Conduits Installation | 20A weatherproof TPN isolator for Booster pump | No | 1 | 12 | 12 | 1 | 12
E27 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Lighting switch 10A Double pole one way one gang | No | 3 | 6 | 18 | 3 | 18
E28 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Ditto one way two gang | No | 3 | 6 | 18 | 3 | 18
E29 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Ditto one way three gang | No | 11 | 6 | 66 | 11 | 66
E31 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 40w fluorescent fitting light fixture | No | 10 | 12 | 120 | 10 | 120
E32 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 40w fluorescent light fixture for toilet | No | 2 | 12 | 24 | 2 | 24
E33 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 40w led downlight | No | 7 | 12 | 84 | 7 | 84
E34 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 25w led wall mounted light fixture | No | 2 | 12 | 24 | 2 | 24
E35 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 25w led wall mounted light fixture | No | 3 | 12 | 36 | 3 | 36
E36 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 25w led wall mounted light fixture whether proof IP66 | No | 11 | 12 | 132 | 11 | 132
E37 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 7w led mirror light | No | 2 | 12 | 24 | 2 | 24
E38 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | 20w compound wall light with whether proof IP65 | No | 13 | 12 | 156 | 13 | 156
E39 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Ceiling fan | No | 5 | 15 | 75 | 5 | 75
E40 | Electrical Engineering Installation | Lighting Accessories and cable and conduits installation | Wall mounted exhaust fan | No | 3 | 10 | 30 | 3 | 30
GN1 | TV System Installation | TV System Installation | Cable and conduit to TV point in concealed installation from satellite | No | 4 | 25 | 100 | 4 | 100
GN2 | TV System Installation | Outlet | Flush mounted TV Satellite outlet | No | 1 | 25 | 25 | 1 | 25
GN3 | TV System Installation | TV System Installation | Allow for co axial cable in concealed conduit from dish antenna to satellite switcher with all necessary accessories and trunking and conduits and trays and supports etc. | Item | 1 | 100 | 100 | 1 | 100
GN4 | Telephone System | TV System Installation | Cable and conduits to telephone outlet points in concealed installation from telephone junction box to IP phone expansion module for reception | No | 4 | 50 | 200 | 4 | 200
GN5 | Telephone System | Outlet | Cat 6E telephone outlet | No | 4 | 10 | 40 |  |  |  | 40
GN6 | Telephone System | Junction box | Telephone junction box | No | 1 | 50 | 50 |  |  |  | 50
GN7 | Telephone System | Excavation | Supply and laying 80 pair telephone cable including trench excavationand backfilling and ducts and bedding caution tape etc all as per site conditions | Item | 1 | 75 | 75 |  | 0 | 1 | 75
GN8 | Telephone System | Cables | 80 pair external grade telephone cable from mantel terminal box to main telephone junction box at main building Electrical room. | Item | 1 | 50 | 50 |  | 0 | 1 | 50
GN9 | Telephone System | Draw Pits | 450 and 450 and 500 mm deep internal size telephone draw pit RCC wall and rendering internally and 75 mm PCC at bottom with 450 and 450 mm medium duty ductile iron cover and frame. | Item | 1 | 50 | 50 |  | 0 | 1 | 50
GN10 | Structured Cabling system | Accessories | Wi Fi access units including all accessories and fittings | item | 1 | 100 | 100 |  | 0 | 1 | 100
GN12 | Structured Cabling system | Cable | Cableconduits and accessories to RJ 45 Category 6A dual socket outlet | No | 4 | 10 | 40 |  | 0 | 4 | 40
GN13 | Structured Cabling system | Cable | Drop lead 3m long Category 6A | No | 2 | 50 | 100 |  | 0 | 2 | 100
GN14 | Structured Cabling system | Cable | Drop lead 6m long Category 6A | No | 2 | 75 | 150 |  | 0 | 2 | 150
GN15 | Structured Cabling system | patch panel | 16 Port Cat 6A Patch panel | No | 1 | 100 | 100 | 1 | 100 | 1 | 100
GN16 | Structured Cabling system | Structured Cabling system | 500mm single mode fiber LC SC Patch cords | No | 1 | 50 | 50 | 1 | 50 | 1 | 50
TOTAL 1 NOS HOUSING UNITS | [6 empty] | 79997 |  | 69036.948 |  | 11875.052 |  | 765 |  | See Appendix - C for the Additional Works
TOTAL 3 NOS HOUSING UNITS | [6 empty] | 239991 |  | 207110.844 |  | 35625.156 |  | 2295
[7 empty] | 17111 |  | 14956

## APPENDIX - C
CONSTRUCTION, COMPLETION AND MAINTENANCE OF PROPOSED (20NOS) HOUSING UNITS AND MAINTENANCE WORKS FOR THE EXISTING (32) HOUSES FOR THE MINISTRY
3 NEW HOUSING UNITS
APPENDIX - C
REVISED DOORS
| D1 | ALUM. DOOR | 1 | 355 | 355
| D2 | ALUM. DOOR | 1 | 410 | 410
|  |  | For 1 Unit |  | 765
|  |  | For 3 Units |  | 2295

## MSheet of 3 NHU (hidden)
NEW HOUSING UNITS - 03 NOS
BOQ ID | DESCRIPTION | UOM | Nos | No.of Items | L | B | D | QTY | REMARKS
C3 | EARTH WORK
| Excavation PL | M³ | 1 | 1 | 186.89 |  | 1.5 | 280.335
| Total | M³ | [5 empty] | 280.335
C9 | FOOTING PCC
Grid 1-1
| F1 | M³ | 2 | 1 | 2.4 | 2.1 | 0.1 | 1.008
| CF1 | M³ | 2 | 1 | 2.4 | 2.1 | 0.1 | 1.008
Grid 5-5
| F2 | M³ | 2 | 1 | 2.6 | 2.3 | 0.1 | 1.196
| F1 | M³ | 2 | 1 | 2.4 | 2.1 | 0.1 | 1.008
Grid 7-7
| F2 | M³ | 1 | 1 | 2.6 | 2.3 | 0.1 | 0.598
| F1 | M³ | 1 | 1 | 2.4 | 2.1 | 0.1 | 0.504
Grid 8-8
| F2 | M³ | 1 | 1 | 2.6 | 2.3 | 0.1 | 0.598
| F1 | M³ | 1 | 1 | 2.4 | 2.1 | 0.1 | 0.504
Grid 9-9
| F2 | M³ | 1 | 1 | 2.6 | 2.3 | 0.1 | 0.598
| F1 | M³ | 1 | 1 | 2.4 | 2.1 | 0.1 | 0.504
Grid 11
| F1 | M³ | 2 | 1 | 2.4 | 2.1 | 0.1 | 1.008
| Total | M³ | [5 empty] | 8.534
C10 | FOOTING RCC
Grid 1-1
| F1 | M³ | 2 | 1 | 2.2 | 1.9 | 0.5 | 4.18
| CF1 | M³ | 2 | 1 | 2.2 | 1.9 | 0.5 | 4.18
| Grid 5-5 |  |  |  | - | -
| F2 | M³ | 2 | 1 | 2.4 | 2.1 | 0.5 | 5.04
| F1 | M³ | 2 | 1 | 2.2 | 1.9 | 0.5 | 4.18
| Grid 7-7 |  |  |  | - | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 | 0.5 | 2.52
| F1 | M³ | 1 | 1 | 2.2 | 1.9 | 0.5 | 2.09
| Grid 8-8 |  |  |  | - | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 | 0.5 | 2.52
| F1 | M³ | 1 | 1 | 2.2 | 1.9 | 0.5 | 2.09
| Grid 9-9 |  |  |  | - | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 | 0.5 | 2.52
| F1 | M³ | 1 | 1 | 2.2 | 1.9 | 0.5 | 2.09
| Grid 11 |  |  |  | - | -
| F1 | M³ | 2 | 1 | 2.2 | 1.9 | 0.5 | 4.18
| Total | M³ | [5 empty] | 35.59
C13 | RCC - Short Column
Grid 1-1
| C1 | M³ | 4 | 1 | 0.5 | 0.2 | 1.9 | 0.76
| C4 | M³ | 2 | 1 | 0.03 |  | 1.9 | 0.119
| Grid 4-4 |  |  |  | - | -
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 1.9 | 0.266
| C1 | M³ | 2 | 1 | 0.5 | 0.2 | 1.9 | 0.38
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 1.9 | 0.228
| Grid 7-7 |  |  |  | - | -
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 1.9 | 0.266
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 1.9 | 0.19
| Grid 8-8 |  |  |  | - | -
| C2 | M³ | 1 | 1 | 0.7 | 0.2 | 1.9 | 0.266
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 1.9 | 0.19
| Grid 10-10 |  |  |  | - | -
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 1.9 | 0.19
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 1.9 | 0.228
| Grid 11 |  |  |  | - | -
| C1 | M³ | 2 | 1 | 0.5 | 0.2 | 1.9 | 0.38
| Total | M³ | [5 empty] | 3.463
C17 | SUBSTRUCTURAL BLOCK WORK
| PL | M² | 1 | 1 | 47.2 |  | 1.3 | 61.36
| Stair wall | M² | 1 | 1 | 11 |  | 1.3 | 14.3
Column Deductions
Grid 1-1
| C1 | M³ | 4 | -1 | 0.5 |  | 1.3 | -2.6
| Grid F-F |  |  |  | -
| C1 | M³ | 3 | -1 | 0.5 |  | 1.3 | -1.95
| Grid 11 |  |  |  | -
| C1 | M³ | 2 | -1 | 0.5 |  | 1.3 | -1.3
| Grid C-C |  |  |  | -
| C2 | M³ | 1 | -1 | 0.7 |  | 1.3 | -0.91
| C1 | M³ | 1 | -1 | 0.5 |  | 1.3 | -0.65
| Grid A-A |  |  |  | -
| C1 | M³ | 1 | -1 | 0.5 |  | 1.3 | -0.65
| C3 | M³ | 2 | -1 | 0.7 |  | 1.3 | -1.82
| Stair wall |  |  |  | -
| C1 | M³ | 2 | -1 | 0.5 |  | 1.3 | -1.3
| Total | M³ | [5 empty] | 64.48
C14 | WATERPROOFING WORK
Polythene sheet Protection Work - Footing Base
Grid 1-1
| F1 | M² | 2 | 1 | 2.4 | 2.1 |  | 10.08
| CF1 | M² | 2 | 1 | 2.4 | 2.1 |  | 10.08
| Grid 5-5 | M²
| F2 | M² | 2 | 1 | 2.6 | 2.3 |  | 11.96
| F1 | M² | 2 | 1 | 2.4 | 2.1 |  | 10.08
| Grid 7-7 | M²
| F2 | M² | 1 | 1 | 2.6 | 2.3 |  | 5.98
| F1 | M² | 1 | 1 | 2.4 | 2.1 |  | 5.04
| Grid 8-8 | M²
| F2 | M² | 1 | 1 | 2.6 | 2.3 |  | 5.98
| F1 | M² | 1 | 1 | 2.4 | 2.1 |  | 5.04
| Grid 9-9 | M²
| F2 | M² | 1 | 1 | 2.6 | 2.3 |  | 5.98
| F1 | M² | 1 | 1 | 2.4 | 2.1 |  | 5.04
| Grid 11 | M²
| F1 | M² | 2 | 1 | 2.4 | 2.1 |  | 10.08
| Total | M² | [5 empty] | 85.34
C14 | Polythene sheet Protection Work - Grade slab
| Entrance | M² | 1 | 1 | 2 | 1.4 |  | 2.8
| Lobby1 | M² | 1 | 1 | 2 | 2.2 |  | 4.4
| Lobby2 | M² | 1 | 1 | 2 | 2.2 |  | 4.4
| Lobby3 | M² | 1 | 1 | 2 | 3.4 |  | 6.8
| Living room Slab | M² | 1 | 1 | 3.8 | 4 |  | 15.2
| Bedroom 1 | M² | 1 | 1 | 3.8 | 4 |  | 15.2
| Lobby Toilet Slab | M² | 1 | 1 | 2.4 | 2 |  | 4.8
| Bedroom 2 Slab | M² | 1 | 1 | 3.8 | 4 |  | 15.2
| Kitchen | M² | 1 | 1 | 2.8 | 4 |  | 11.2
| Majilis Slab | M² | 1 | 1 | 4 | 4 |  | 16
| Majilis Toilet | M² | 1 | 1 | 2.4 | 1.2 |  | 2.88
| Majilis Wash | M² | 1 | 1 | 1.4 | 1.2 |  | 1.68
| Total | M² | [5 empty] | 100.56
Polythene sheet Protection Work - Step Footing PCC
| Grid 2-2 | M³ | 1 | 1 | 3.7 | 0.8 |  | 2.96
| Grid 4-4 | M³ | 1 | 1 | 1.5 | 0.8 |  | 1.2
| Grid 7-7 | M³ | 1 | 1 | 1.5 | 0.8 |  | 1.2
| Grid 10-10 | M³ | 1 | 1 | 1.9 | 0.8 |  | 1.52
| Grid 11-11 | M³ | 1 | 1 | 3.9 | 0.8 |  | 3.12
| Grid A-A | M³ | 1 | 1 | 4.3 | 0.8 |  | 3.44
| Grid C-C | M³ | 1 | 1 | 0.5 | 0.8 |  | 0.4
| Grid F-F | M³ | 1 | 1 | 6.3 | 0.8 |  | 5.04
| Total | M³ | [5 empty] | 18.88
C14 | SUBTOTAL
| Polythene sheet Protection Work - Footing Base | Nos | 1 |  |  |  | 85.34 | 85.34
| Polythene sheet Protection Work - Grade slab | Nos | 1 |  |  |  | 100.56 | 100.56
| Polythene sheet Protection Work - Step Footing PCC |  | 1 |  |  |  | 18.88 | 18.88
| SUBTOTAL Polythene Sheet WATERPROOFING | [6 empty] | 204.78
C18 | WATERPROOFING WORK
| Block Work Area | M² | 1 | 2 |  |  | 64.48 | 128.96
Footings Sides
Grid 1-1
| F1 | M³ | 1 | 1 | 2.2 | 1.9 | 0.5 | 4.1
| CF1 | M³ | 1 | 1 | 2.2 | 1.9 | 0.5 | 4.1
| Grid 5-5 |  | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 | 0.5 | 4.5
| F1 |  | - |  | 2.2 | 1.9
| Grid 7-7 | M³ | 2 | 1 |  |  | 0.4 | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 | 0.5 | 4.5
| F1 | M³ | 1 | 1 | 2.2 | 1.9 | 0.5 | 4.1
| Grid 8-8 |  | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 | 0.5 | 4.5
| F1 | M³ | 3 | 1 | 2.2 | 1.9 | 0.5 | 12.3
| Grid 9-9 |  | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 | 0.5 | 4.5
| F1 | M³ | 2 | 1 | 2.2 | 1.9 | 0.5 | 8.2
| Grid 11 |  | -
| F1 | M³ | 1 | 1 | 2.2 | 1.9 | 0.6 | 4.92
Footings Top
Grid 1-1
| F1 | M³ | 1 | 1 | 2.2 | 1.9 |  | 4.18
| CF1 | M³ | 1 | 1 | 2.2 | 1.9 |  | 4.18
| Grid 5-5 |  | - |  |  |  |  | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 |  | 5.04
| F1 |  | - |  | 2.2 | 1.9 |  | -
| Grid 7-7 | M³ | 2 | 1 |  |  |  | 2
| F2 | M³ | 1 | 1 | 2.4 | 2.1 |  | 5.04
| F1 | M³ | 1 | 1 | 2.2 | 1.9 |  | 4.18
| Grid 8-8 |  | - |  |  |  |  | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 |  | 5.04
| F1 | M³ | 3 | 1 | 2.2 | 1.9 |  | 12.54
| Grid 9-9 |  | - |  |  |  |  | -
| F2 | M³ | 1 | 1 | 2.4 | 2.1 |  | 5.04
| F1 | M³ | 2 | 1 | 2.2 | 1.9 |  | 8.36
| Grid 11 |  | - |  |  |  |  | -
| F1 | M³ | 1 | 1 | 2.2 | 1.9 |  | 4.18
Column Deduction
| Grid 1-1 |  | -
| C1 | M³ | 4 | -1 | 0.5 | 0.2 |  | -0.4
| C4 | M³ | 2 | -1 | 0.03 |  |  | -0.063
| Grid 4-4 |  | - | -1 | - | - |  | -
| C3 | M³ | 1 | -1 | 0.7 | 0.2 |  | -0.14
| C1 | M³ | 2 | -1 | 0.5 | 0.2 |  | -0.2
| C2 | M³ | 1 | -1 | 0.6 | 0.2 |  | -0.12
| Grid 7-7 |  | - | -1 | - | - |  | -
| C3 | M³ | 1 | -1 | 0.7 | 0.2 |  | -0.14
| C1 | M³ | 1 | -1 | 0.5 | 0.2 |  | -0.1
| Grid 8-8 |  | - | -1 | - | - |  | -
| C2 | M³ | 1 | -1 | 0.7 | 0.2 |  | -0.14
| C1 | M³ | 1 | -1 | 0.5 | 0.2 |  | -0.1
| Grid 10-10 |  | - | -1 | - | - |  | -
| C1 | M³ | 1 | -1 | 0.5 | 0.2 |  | -0.1
| C2 | M³ | 1 | -1 | 0.6 | 0.2 |  | -0.12
| Grid 11 |  | - | -1 | - | - |  | -
| C1 | M³ | 2 | -1 | 0.5 | 0.2 |  | -0.2
Footings Top - Block work area deduction
| F1 |  | 11 | -1 | 1.7 | 0.2 |  | -3.74
| F2 |  | 2 | -1 | 1.9 | 0.2 |  | -0.76
Column Sides
| Grid 1-1 |  | -
| C1 | M³ | 4 | 1 | 0.5 | 0.2 | 2 | 11.2
| C4 | M³ | 2 | 1 | 0.63 |  | 2 | 2.514
| Grid 4-4 |  | - |  | - | -
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 2 | 3.6
| C1 | M³ | 2 | 1 | 0.5 | 0.2 | 2 | 5.6
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2 | 3.2
| Grid 7-7 |  | - |  | - | - |  | -
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 2 | 3.6
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2 | 2.8
| Grid 8-8 |  | - |  | - | - |  | -
| C2 | M³ | 1 | 1 | 0.7 | 0.2 | 2 | 3.6
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2 | 2.8
| Grid 10-10 |  | - |  | - | - |  | -
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2 | 2.8
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2 | 3.2
| Grid 11 |  | - |  | - | - |  | -
| C1 | M³ | 2 | 1 | 0.5 | 0.2 | 2 | 5.6
| Total | M² | [5 empty] | 288.651
C6 | Foundation Back Filling
| Excavation PL | M³ | 1 | 1 | 186.89 |  | 1.5 | 280.34
| Deduction of PCC | M³ | -1 | 1 |  |  | 8.53 | -8.53
| Deduction Of Footing RCC | M³ | -1 | 1 | 35.59 |  |  | -35.59
| Deduction Of Column RCC | M³ | -1 | 1 | 3.46 |  |  | -3.46
| Deduction Of Block work | M³ | -1 | 1 | 64.48 |  | 0.2 | -12.9
| Total | M³ | [5 empty] | 219.85
C11 | Plinth Beam RCC
Plinth Beam RCC
| PB1 | M³ | 1 | 1 | 7.4 | 0.2 | 0.55 | 0.814
| PB2 | M³ | 1 | 1 | 77.1 | 0.2 | 0.55 | 8.481
| PB3 | M³ | 1 | 1 | 11.8 | 0.2 | 0.65 | 1.534
| Total | M³ | [5 empty] | 10.83
C8 | Anti Termite Treatment
| Entrance | M² | 1 | 1 | 2 | 1.4 |  | 2.8
| Lobby1 | M² | 1 | 1 | 2 | 2.2 |  | 4.4
| Lobby2 | M² | 1 | 1 | 2 | 2.2 |  | 4.4
| Lobby3 | M² | 1 | 1 | 2 | 3.4 |  | 6.8
| Living room Slab | M² | 1 | 1 | 3.8 | 4 |  | 15.2
| Bedroom 1 | M² | 1 | 1 | 3.8 | 4 |  | 15.2
| Lobby Toilet Slab | M² | 1 | 1 | 2.4 | 2 |  | 4.8
| Bedroom 2 Slab | M² | 1 | 1 | 3.8 | 4 |  | 15.2
| Kitchen | M² | 1 | 1 | 2.8 | 4 |  | 11.2
| Majilis Slab | M² | 1 | 1 | 4 | 4 |  | 16
| Majilis Toilet | M² | 1 | 1 | 2.4 | 1.2 |  | 2.88
| Majilis Wash | M² | 1 | 1 | 1.4 | 1.2 |  | 1.68
| Total | M² | [5 empty] | 97.76
C12 | Grade Slab RCC
| Entrance | M² | 1 | 1 | 2 | 1.4 | 0.2 | 0.56
| Lobby1 | M² | 1 | 1 | 2 | 2.2 | 0.2 | 0.88
| Lobby2 | M² | 1 | 1 | 2 | 2.2 | 0.2 | 0.88
| Lobby3 | M² | 1 | 1 | 2 | 3.4 | 0.2 | 1.36
| Living room Slab | M² | 1 | 1 | 3.8 | 4 | 0.2 | 3.04
| Bedroom 1 | M² | 1 | 1 | 3.8 | 4 | 0.2 | 3.04
| Lobby Toilet Slab | M² | 1 | 1 | 2.4 | 2 | 0.2 | 0.96
| Bedroom 2 Slab | M² | 1 | 1 | 3.8 | 4 | 0.2 | 3.04
| Kitchen | M² | 1 | 1 | 2.8 | 4 | 0.2 | 2.24
| Majilis Slab | M² | 1 | 1 | 4 | 4 | 0.2 | 3.2
| Majilis Toilet | M² | 1 | 1 | 2.4 | 1.2 | 0.2 | 0.576
| Majilis Wash | M² | 1 | 1 | 1.4 | 1.2 | 0.2 | 0.336
| Total | M³ | [5 empty] | 20.11
C23 | Column RCC
Grid 1-1
| C1 | M³ | 4 | 1 | 0.5 | 0.2 | 2.45 | 0.98
| C4 | M³ | 2 | 1 | 0.03 |  | 3 | 0.189
| Grid 4-4 |  |  |  | - | -
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 2.45 | 0.343
| C1 | M³ | 2 | 1 | 0.5 | 0.2 | 2.4 | 0.48
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.45 | 0.294
| Grid 7-7 |  |  |  | - | -
| C3 | M³ | 1 | 1 | 0.7 | 0.2 | 2.45 | 0.343
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.45 | 0.245
| Grid 8-8 |  |  |  | - | -
| C2 | M³ | 1 | 1 | 0.7 | 0.2 | 2.45 | 0.343
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.4 | 0.24
| Grid 10-10 |  |  |  | - | -
| C1 | M³ | 1 | 1 | 0.5 | 0.2 | 2.45 | 0.245
| C2 | M³ | 1 | 1 | 0.6 | 0.2 | 2.45 | 0.294
| Grid 11 |  |  |  | - | -
| C1 | M³ | 2 | 1 | 0.5 | 0.2 | 2.4 | 0.48
| Total | M³ | [5 empty] | 4.476
Step Footing PCC - Block work Foundation
| Grid 2-2 | M³ | 1 | 1 | 3.7 | 0.8 | 0.1 | 0.3
| Grid 4-4 | M³ | 1 | 1 | 1.5 | 0.8 | 0.1 | 0.12
| Grid 7-7 | M³ | 1 | 1 | 1.5 | 0.8 | 0.1 | 0.12
| Grid 10-10 | M³ | 1 | 1 | 1.9 | 0.8 | 0.1 | 0.15
| Grid 11-11 | M³ | 1 | 1 | 3.9 | 0.8 | 0.1 | 0.31
| Grid A-A | M³ | 1 | 1 | 4.3 | 0.8 | 0.1 | 0.34
| Grid C-C | M³ | 1 | 1 | 0.5 | 0.8 | 0.1 | 0.04
| Grid F-F | M³ | 1 | 1 | 6.3 | 0.8 | 0.1 | 0.5
| Total | M³ | [5 empty] | 1.89
Step Footing RCC - Block work Foundation
| Grid 2-2 | M³ | 1 | 1 | 3.7 | 0.24 |  | 0.89
| Grid 4-4 | M³ | 1 | 1 | 1.5 | 0.24 |  | 0.36
| Grid 7-7 | M³ | 1 | 1 | 1.5 | 0.24 |  | 0.36
| Grid 10-10 | M³ | 1 | 1 | 1.9 | 0.24 |  | 0.46
| Grid 11-11 | M³ | 1 | 1 | 3.9 | 0.24 |  | 0.94
| Grid A-A | M³ | 1 | 1 | 4.3 | 0.24 |  | 1.03
| Grid C-C | M³ | 1 | 1 | 0.5 | 0.24 |  | 0.12
| Grid F-F | M³ | 1 | 1 | 6.3 | 0.24 |  | 1.51
| Total | M³ | [5 empty] | 5.66
Plinth Beam PCC
| Grid 3-3 | M³ | 1 | 1 | 2 | 0.4 | 0.1 | 0.08
| Grid 4-4 | M³ | 1 | 1 | 6 | 0.4 | 0.1 | 0.24
| Grid 6-6 | M³ | 1 | 1 | 4 | 0.4 | 0.1 | 0.16
| Grid 7-7 | M³ | 1 | 1 | 2 | 0.4 | 0.1 | 0.08
| Grid 8-8 | M³ | 1 | 1 | 4 | 0.4 | 0.1 | 0.16
| Grid 9-9 | M³ | 1 | 1 | 2 | 0.4 | 0.1 | 0.08
| Grid 11-11 | M³ | 1 | 1 | 3.9 | 0.4 | 0.1 | 0.16
| Grid C-C | M³ | 1 | 1 | 7.2 | 0.4 | 0.1 | 0.29
| Grid D-D | M³ | 1 | 1 | 11.6 | 0.4 | 0.1 | 0.46
| Grid E-E | M³ | 1 | 1 | 1.2 | 0.4 | 0.1 | 0.05
| Total | M³ | [5 empty] | 1.76
C30 | Superstructure Block Work
| B1 | M² | 1 | 1 | 5.2 |  | 2.65 | 13.78
| B2 | M² | 1 | 1 | 61.9 |  | 2.65 | 164.04
| B3 | M² | 1 | 1 | 16.2 |  | 2.6 | 42.12
| Head Room | M² | 1 | 1 | 14.6 |  | 2.7 | 39.42
DEDUCTIONS
| W1 | M² | -1 | 13 | 1 |  | 1.6 | -20.8
| W2 | M² | -1 | 1 | 1 |  | 1.4 | -1.4
| V | M² | -1 | 2 | 0.8 |  | 1.2 | -1.92
| D1 | M² | -1 | 1 | 1.8 |  | 2.5 | -4.5
| D2 | M² | -1 | 1 | 1 |  | 2.5 | -2.5
| D3 | M² | -1 | 4 | 1 |  | 2.1 | -8.4
| D4 | M² | -1 | 2 | 0.8 |  | 2.1 | -3.36
| D5 | M² | -1 | 1 | 1 |  | 2.1 | -2.1
| D6 | M² | -1 | 1 | 1 |  | 2.5 | -2.5
| Total | M² | [5 empty] | 211.88
C24 | GF Roof Beams
| B1 | M³ | 1 | 1 | 5.2 | 0.2 | 0.55 | 0.57
| B2 | M³ | 1 | 1 | 61.9 | 0.2 | 0.55 | 6.81
| B3 | M³ | 1 | 1 | 16.2 | 0.2 | 0.6 | 1.94
| Total | M³ | [5 empty] | 9.33
C22 | GF Waist slab & Roof Slabs
| Entrance Slab | M³ | 1 | 1 | 4.55 |  | 0.15 | 0.683
| Living Room | M³ | 1 | 1 | 3.8 | 4 | 0.18 | 2.736
| Lobby | M³ | 1 | 1 | 2 | 2.2 | 0.15 | 0.66
| Majilis | M³ | 1 | 1 | 4 | 4 | 0.18 | 2.88
| Wash | M³ | 1 | 1 | 1.4 | 1.2 | 0.15 | 0.252
| Toilet | M³ | 1 | 1 | 2.4 | 1.2 | 0.15 | 0.432
| Kitchen | M³ | 1 | 1 | 2.8 | 4 | 0.18 | 2.016
| Lobby | M³ | 1 | 1 | 2 | 3.4 | 0.15 | 1.02
| Bedroom1 | M³ | 1 | 1 | 3.8 | 4 | 0.18 | 2.736
| Bedroom2 | M³ | 1 | 1 | 3.8 | 4 | 0.18 | 2.736
| Toilet 2 | M³ | 1 | 1 | 2.4 | 2 | 0.15 | 0.72
| Head room Slab | M³ | 1 | 1 | 5.7 | 2.2 | 0.18 | 2.257
| Staircase | M³ | 1 | 1 | 7.2 | 1 | 0.2 | 1.44
| Steps | M³ | 1 | 20 | 1 | 0.02 |  | 0.45
| Total | M³ | [5 empty] | 21.02

## RCC Holding TankSoak Pit (hidden)
BOQ ID | DESCRIPTION | UOM | Nos | No.of Items | L | B | D | QTY | REMARKS
QUANTITIES FOR A HOLDING TANK (4M x 2M x 2.5M)
| Earthwork Excavation | Cum | 1 | 1 | 4.6 | 2.6 | 3.05 | 36.478
| PCC | Cum | 1 | 1 | 4.6 | 2.6 | 0.1 | 1.196
| RCC Base Slab | Cum | 1 | 1 | 4.4 | 2.4 | 0.25 | 2.64
| RCC Wall | Cum | 1 | 1 | 12.8 | 2.5 | 0.2 | 6.4
| RCC Cover slab | Cum | 1 | 1 | 4.4 | 2.4 | 0.2 | 2.112
QUANTITIES FOR A 1M WIDE (DIAMETER) AND 2.5M DEPTH SOAK PIT
| Earthwork Excavation | Cum | 1 | 1 | 0.79 |  | 2.5 | 1.975
| Block work or concrete | Sqm | 1 | 1 | 3.14 | 0.2 | 2.4 | 1.5072
| Filling Material | Cum | 1 | 1 | 0.28 |  | 2.4 | 0.672
| 100mm tk RCC Cover Slab | Cum | 1 | 1 | 0.79 |  | 0.1 | 0.079
Concrete Qty Ratio
| Holding Tank | [6 empty] | 11.15
| Soakpit | [6 empty] | 1.59
| RATIO OF SOAKPIT | [6 empty] | 12.48% |  | 25%

## 3 NHU ADD. QTY (hidden)
S/N | DESCRIPTIONS | UNIT | Qty | Rate | Amount | Remark
3 New Housing Unit
200mm Hollow Block Wall (Superstructure Works)
Additional block work of 20cm to increase the level of the slab from 3.0m - 3.2m Height
C26 | 200mm Block | m² | 18.56 | 6 | 111.36 | In Ref. Bill No. 7, Item Code C26 with Rate 6.00/m²
Internal Walls Rendering
C58 | Backgrounds Plaster cement and sand 1:3 internal
| FF1 and FF2 Wall Plastering | m² | 19.56 | 1 | 19.56 | In Ref. Bill No. 7, Item Code C58 with Rate 1.00/m²
External Wall Rendering
C59 | Backgrounds Plaster cement and sand 1:4 external | m² | 18.56 | 1.5 | 27.84 | In Ref. Bill No. 7, Item Code C59 with Rate 1.50/m²
Painting/Decorating
Internal Wall Painting
C69 | FF1 and FF2 | m² | 19.56 | 5 | 97.8 | In Ref. to Bill No 7, Item Code C69 with Rate 5.00/m²
0
Tile Works
C72 & C73 | FF2 and FF3 (Kitchen, Toilet and Wash Area | m² | 7.04 | 3 | 21.12 | In Ref. to Bill No. 7, Item Code C72 and C73 with Rate 3.00/m²
External Wall painting
C69 | Painting/Decoration of wall | m² | 18.56 | 5 | 92.8 | In Ref. to Bill No 5, Item Code C69 with Rate 5.00/m²
| Total of 1 Unit |  |  |  | 370.48
| Total of 3 Unit |  |  |  | 1111.44

## 3 NHU ADD. MSheet (hidden)
S/N | Item/Description | Type | No | No of Items | L | B | D | QTY | Unit
3 New Housing Unit
1 | Block Work
Additional block work of 20cm to increase the level of the slab from 3.0m - 3.2m Height
| Grid 2 - 11 |  |  |  | 12.8
| Deduct Wall |  |  |  | -0.2
|  |  | 1 | 3 | 12.6 |  | 0.2 | 7.56 | m²
| Grid D - F |  | 1 | 4 | 4.2 |  | 0.2 | 3.36
| Grid C - D |  | 1 | 5 | 2.2 |  | 0.2 | 2.2
| Grid A - C |  | 1 | 4 | 4.2 |  | 0.2 | 3.36
| Grid 2 - 4 |  | 1 | 1 | 4 |  | 0.2 | 0.8
| Grid 4 - 7 |  | 1 | 1 | 2.4 |  | 0.2 | 0.48
| Grid 7 - 10 |  | 1 | 1 | 4 |  | 0.2 | 0.8
[8 empty] | 18.56 | m²
2 | Internal Plastering/Rendering
Internal Wall Plastering
Backgrounds Plaster cement and sand 1:3 internal To walls and columns on concrete block base internal including stainsteel mesh butterfly angle
Internal Painting
FF1
| Living Room |  | 1 | 2 | 4 |  | 0.2 | 1.6 | m²
|  |  | 1 | 2 |  | 3.8 | 0.2 | 1.52
| Majlis Area |  | 1 | 2 | 4 |  | 0.2 | 1.6
|  |  | 1 | 2 |  | 4 | 0.2 | 1.6
| Bedroom 1 |  | 1 | 2 | 4 |  | 0.2 | 1.6
|  |  | 1 | 2 |  | 3.8 | 0.2 | 1.52
| Bedroom 2 |  | 1 | 2 | 4 |  | 0.2 | 1.6
|  |  | 1 | 2 |  | 3.8 | 0.2 | 1.52
| Lobby Area |  | 1 | 2 | 3.4 |  | 0.2 | 1.36
|  |  | 1 | 2 |  | 2 | 0.2 | 0.8
| Entrance Lobby Area |  | 1 | 2 | 2.2 |  | 0.2 | 0.88
|  |  | 1 | 2 |  | 2 | 0.2 | 0.8
FF4
| Staircase Area |  | 1 | 2 | 5.7 |  | 0.2 | 2.28
|  |  | 1 | 2 |  | 2.2 | 0.2 | 0.88
[8 empty] | 19.56 | m²
3 | Exteral Plastering/Rendering
External Wall Plastering
Backgrounds Plaster cement and sand 1:3 internal To walls and columns on concrete block base internal including stainsteel mesh butterfly angle
| Grid 2 - 11 |  |  |  | 12.8
| Deduct Wall |  |  |  | -0.2
|  |  | 1 | 3 | 12.6 |  | 0.2 | 7.56 | m²
| Grid D - F |  | 1 | 4 | 4.2 |  | 0.2 | 3.36
| Grid C - D |  | 1 | 5 | 2.2 |  | 0.2 | 2.2
| Grid A - C |  | 1 | 4 | 4.2 |  | 0.2 | 3.36
| Grid 2 - 4 |  | 1 | 1 | 4 |  | 0.2 | 0.8
| Grid 4 - 7 |  | 1 | 1 | 2.4 |  | 0.2 | 0.48
| Grid 7 - 10 |  | 1 | 1 | 4 |  | 0.2 | 0.8
[8 empty] | 18.56 | m²
4 | Painting/Decoration
Internal Painting
FF1
| Living Room |  | 1 | 2 | 4 |  | 0.2 | 1.6 | m²
|  |  | 1 | 2 |  | 3.8 | 0.2 | 1.52
| Majlis Area |  | 1 | 2 | 4 |  | 0.2 | 1.6
|  |  | 1 | 2 |  | 4 | 0.2 | 1.6
| Bedroom 1 |  | 1 | 2 | 4 |  | 0.2 | 1.6
|  |  | 1 | 2 |  | 3.8 | 0.2 | 1.52
| Bedroom 2 |  | 1 | 2 | 4 |  | 0.2 | 1.6
|  |  | 1 | 2 |  | 3.8 | 0.2 | 1.52
| Lobby Area |  | 1 | 2 | 3.4 |  | 0.2 | 1.36
|  |  | 1 | 2 |  | 2 | 0.2 | 0.8
| Entrance Lobby Area |  | 1 | 2 | 2.2 |  | 0.2 | 0.88
|  |  | 1 | 2 |  | 2 | 0.2 | 0.8
FF4
| Staircase Area |  | 1 | 2 | 5.7 |  | 0.2 | 2.28
|  |  | 1 | 2 |  | 2.2 | 0.2 | 0.88
[8 empty] | 19.56 | m²
5 | Ceremic Tiles
FF2
Ceramic Tiles 600 X 200 X 8 Anti Slip
| Kitchen Area |  | 1 | 2 | 4 |  | 0.2 | 1.6 | m²
|  |  | 1 | 2 |  | 2.8 | 0.2 | 1.12
FF3
Ceramic Tiles
600 X 200 X 8 Anti Slip
| Toilet Area 1 |  | 1 | 2 | 2.4 |  | 0.2 | 0.96
|  |  | 1 | 2 |  | 1.2 | 0.2 | 0.48
| Toilet Area 2 |  | 1 | 2 | 2.4 |  | 0.2 | 0.96
|  |  | 1 | 2 |  | 2 | 0.2 | 0.8
| Wash Area |  | 1 | 2 | 1.4 |  | 0.2 | 0.56
|  |  | 1 | 2 |  | 1.4 | 0.2 | 0.56
[8 empty] | 7.04 | m²
6 | Exteral Painting/Decoration
Exteral Painting/Decoration
| Grid 2 - 11 |  |  |  | 12.8
| Deduct Wall |  |  |  | -0.2
|  |  | 1 | 3 | 12.6 |  | 0.2 | 7.56 | m²
| Grid D - F |  | 1 | 4 | 4.2 |  | 0.2 | 3.36
| Grid C - D |  | 1 | 5 | 2.2 |  | 0.2 | 2.2
| Grid A - C |  | 1 | 4 | 4.2 |  | 0.2 | 3.36
| Grid 2 - 4 |  | 1 | 1 | 4 |  | 0.2 | 0.8
| Grid 4 - 7 |  | 1 | 1 | 2.4 |  | 0.2 | 0.48
| Grid 7 - 10 |  | 1 | 1 | 4 |  | 0.2 | 0.8
[8 empty] | 18.56 | m²

## 20 NHU ADD MSheet (hidden)
S/N | Item/Description | Type | No | No of Items | L | B | D | QTY | Unit
20 New Housing Unit | [9 empty] | Epoxy Steel Bar (16mm Diameter)
| Holding Tank RCC | [8 empty] | Supervision | Unit | QTY | Rate | Amount
1 | Excavation | [8 empty] | Foreman | Ton | 1 | 6.5 | 7
[5 empty] | 4.4 | 2.4 |  |  |  | Skilled |  | 1 | 4.5 | 5
| Add Working Space | [8 empty] | Unskilled |  | 1 | 2.5 | 3
| 600mm to both side |  | 1 | 1 | 0.6 | 0.6
|  |  | 1 | 1 | 5 | 3 | 3 | 45 | m³ |  |  |  |  | 15
Materials
[10 empty] | 16mm Diameter | Ton | 1 | 360 | 360
[8 empty] | 45 | m³
2 | Leveling and Compacting | [8 empty] | Binding Wire |  | 1 | 4.5 | 4.5
[5 empty] | 4.4 | 2.4 | [7 empty] | 364.5
[5 empty] | 0.6 | 0.6 |  |  |  | Transportation | Ton | 1 | 10 | 10
|  |  | 1 | 1 | 5 | 3 |  | 15 | m²
[10 empty] | Cutting & Bending Tool | Ton | 1 | 40 | 40
Fixing to Structure
[8 empty] | 15 | m²
3 | Anti - Termite Treatment
| Bottom of the Excavated Area |  |  |  | 5 | 3 |  | 15 | m²
| Face of the Excavated Area |  | 1 | 2 | 5 |  | 3 | 30 |  | Direct Cost |  |  |  | 429.5
|  |  | 1 | 2 |  | 3 | 3 | 18 |  | Add
[10 empty] | Overhead | 10% |  |  | 42.95
472.45
[8 empty] | 63 | m² | Profit | 8% |  |  | 37.796
4 | Blinding PCC 100mm
|  |  | 1 | 1 | 5 | 3 | 0.1 | 1.5 | [5 empty] | 510.246
548.042
[10 empty] | Contigency | 5% |  |  | 27.4021
[8 empty] | 1.5 | m³
5 | Reinforced Cement Concrete RCC | [8 empty] | Total/Ton |  |  |  | 575.4441
[5 empty] | 4 | 2 |  |  |  | Total/kg |  |  |  | 0.57544
| Add 200mm wall to both side |  |  |  | 0.2 | 0.2
| Multiply by Thickness |  | 1 | 1 | 4.2 | 2.2 | 0.25 | 2.31 | m³
[8 empty] | 2.31 | m³
6 | RCC Wall of Holding Tank
[5 empty] | 4 | 2
| Add ½ wall to both side |  |  |  | 0.1 | 0.1
[5 empty] | 4.1 | 2.1
|  |  | 1 | 2 | 4.1 | 0.2 | 2.5 | 4.1 | m³
|  |  | 1 | 2 | 2.1 | 0.2 | 2.5 | 2.1
[8 empty] | 6.2 | m³
7 | Back filliing
| Excavated Volume |  | 1 | 1 | 5 | 3 | 3 | 45 | m³
Deduct
| Blinding 100mm |  | 1 | -1 | 4.7 | 2.6 | 0.1 | -1.222
| Plan Concrete Base |  | 1 | -1 | 4.2 | 2.2 | 0.25 | -2.31
| RCC Tank Wall |  | 1 | -2 | 4.1 | 0.2 | 2.5 | -4.1
|  |  | 1 | -2 | 2.1 | 0.2 | 2.5 | -2.1
| Holding Tank Void |  | 1 | -1 | 4 | 2 | 2.5 | -20
[8 empty] | 15.268 | m³
8 | RCC Holding Tank Slab
|  |  | 1 | 1 | 4.4 | 2.4 | 0.2 | 2.112
Deduct
| Manhole Cover |  | 1 | -1 | 0.6 | 0.6 | 0.2 | -0.072
[8 empty] | 2.04 | m³
9 | Reinforcement Bar @ Base
16mm Diameter Bar
| Length |  | Side A |  | 4.4 |  |  |  | m
| Add Bend |  |  |  | 0.4
| Deduct Cover |  |  |  | -0.8
4
| Number of runner Bar @ 0.15 c/c |  |  |  |  | 2.4
|  |  | 1 | 16 | 4 |  |  | 64
| Length |  | Side A |  |  | 2.4
| Add Bend |  |  |  |  | 0.4
| Deduct Cover |  |  |  |  | -0.08
[5 empty] | 4.4 | 2.72
Number of runner Bar @ 0.15 c/c
|  |  | 1 | 29.3333 | 2.72 |  |  | 79.7867
| Bottom Bar | [6 empty] | 143.7867
| Top Bars | [6 empty] | 143.7867
287.5733
| 16mm Diameter Bar | [6 empty] | 1.5802
| Kg - Ton | [6 empty] | 1000
[8 empty] | 0.45444 | Ton
10 | Reinforcement in RCC Holding Tank Wall
| Length | [5 empty] | 2.75 |  | m
| Add Bend | [5 empty] | 0.8
3.55
| Number @ 150mm c/c |  |  |  |  | 2.4
|  |  | 2 | 16 |  |  | 3.55 | 113.6
|  |  | 2 | 16 |  |  | 3.55 | 113.6
| Number of the Long Side of Holding Tank |  |  |  |  | 4.5
|  |  | 2 | 30 |  |  | 3.55 | 213
|  |  | 2 | 30 |  |  | 3.55 | 213
Runners
16mm Diameter Bar
| Inner Runner |  |  |  | 4.25
2.2
4.25
2.2
| Add lapping D50 |  |  |  | 0.8
13.7
| Number of Runner @ 150mm c/c | [5 empty] | 2.5
|  |  | 1 | 16.6667 | 13.7 |  |  | 228.3333
| Outer Runner |  |  |  | 4.5
2.2
4.25
2.2
0.8
| Deduct Cover |  |  |  | -0.16
13.79
2.5
|  |  | 1 | 16.6667 | 13.79 |  |  | 229.8333
1111.3667
| 16mm Diameter Bar | [6 empty] | 1.5802
| Kg - Ton | [6 empty] | 1000
[8 empty] | 1.7562 | Ton
11 | Reinforcement in Holding Tank Slab
| 16mm Diameter Bar |  |  |  | 4.4 |  |  |  | m
| Add Bend |  |  |  | 0.8
Deduct
| Cover |  |  |  | -0.08
[5 empty] | 5.12 | 2.4
| Add Bend |  |  |  |  | 0.8
Deduct
| Cover |  |  |  |  | -0.08
3.12
| Bottom Bar |  | 1 | 16 | 4.4 |  |  | 70.4
|  |  | 1 | 29.3333 | 3.12 |  |  | 91.52
| Top Bar |  | 1 | 16 | 4.4 |  |  | 70.4
|  |  | 1 | 29.3333 | 3.12 |  |  | 91.52
323.84
| 16mm Diameter Bar | [6 empty] | 1.5802
| Kg - Ton | [6 empty] | 1000
[8 empty] | 0.51175 | Ton
12 | Formwork
| Base of Holding tank |  | 1 | 2 | 4.5 |  | 0.25 | 2.25 | m²
|  |  | 1 | 2 | 2.4 |  | 0.25 | 1.2
[8 empty] | 3.45 | m²
13 | Formwork in Holding Tank Wall
| Internal Part |  | 1 | 1 | 4 |  | 2.5 | 10 | m²
|  |  | 1 | 1 | 2 |  | 2.5 | 5
| External Part |  | 1 | 1 | 4.5 |  | 2.5 | 11.25
|  |  | 1 | 1 | 2.4 |  | 2.5 | 6
[8 empty] | 32.25 | m²
14 | Formwork to Soffix of Holding Tank Slab
|  |  | 1 | 1 | 4 | 2 |  | 8 | m²
[8 empty] | 8 | m²
15 | Formwork to Edge of Holding Tank Slab
|  |  | 1 | 2 | 4.4 |  | 0.2 | 1.76 | m²
|  |  | 1 | 2 | 2.4 |  | 0.2 | 0.96
[8 empty] | 2.72 | m²
REINFORCEMENT BAR (EPOXY STEEL) SUBSTRUCTURAL WORK
C10 | Reinforcement Steel Bar
| Epoxy Steel Bars (Footing Base) | 16mm Epoxy Steel Bar
| F* | 1 | 2 | 6 | 1.6 |  |  | 19.2 | m
|  | 1 | 2 | 5 |  | 1.84 |  | 18.4
| F1 | 1 | 7 | 9 | 2.24 |  |  | 141.12
|  | 1 | 7 | 7 |  | 2.44 |  | 119.56
| F2 | 1 | 7 | 8 | 2.75 |  |  | 154
|  | 1 | 7 | 9 |  | 2.44 |  | 153.72
| F3 | 1 | 6 | 11 | 3.24 |  |  | 213.84
|  | 1 | 6 | 9.5 |  | 2.74 |  | 156.18
| F4 | 1 | 2 | 8.5 | 3.44 |  |  | 58.48
|  | 1 | 2 | 12 |  | 2.54 |  | 60.96
1095.46
16mm Diameter Bar | [7 empty] | 1.5802
Kg - Ton | [7 empty] | 1000
|  | Total Qty = | [5 empty] | 1.7311 | Tons
C13 | Short Reinforcement Steel Bar
12mm Epoxy Steel Bar
| Short column | [5 empty] | 1.5 |  | m
| Add Bending | [5 empty] | 0.5
| Add Lapping 50D | [5 empty] | 0.6
|  | C* | 1 | 4 | 6 |  | 2.6 | 62.4
62.4
12mm Diameter Bar | [7 empty] | 0.88889
Kg - Ton | [7 empty] | 1000
|  | Total Qty = | [5 empty] | 0.055467 | Tons
| Add Lapping | 16mm Epoxy Steel Bar
| 0.8 | C1 |  |  |  | 1.4
|  | C2 |  |  |  | 2
|  | C3 |  |  |  | 2
|  | C4 |  |  |  | 2
|  | C1 | 6 | 8 |  |  | 2.2 | 105.6 | m
|  | C2 | 10 | 10 |  |  | 2.8 | 280
|  | C3 | 3 | 10 |  |  | 2.8 | 84
|  | C4 | 3 | 12 |  |  | 2.8 | 100.8
570.4
16mm Diameter Bar | [7 empty] | 1.5802
Kg - Ton | [7 empty] | 1000
|  | Total Qty = | [5 empty] | 0.90137 | Tons
| Stirrups 8mm Steel Bar | 8mm Epoxy Steel Bar
|  | C* |  |  |  | 1.5
|  | C1 |  |  |  | 1.4
|  | C2 |  |  |  | 2
|  | C3 |  |  |  | 2
|  | C4 |  |  |  | 2
|  | C* | 4 | 7.5 | 0.89 |  |  | 26.7 | m
|  | C1 | 6 | 7 | 1.29 |  |  | 54.18
|  |  | 6 | 7 | 0.631 |  |  | 26.502
|  | C2 | 10 | 10 | 1.49 |  |  | 149
|  |  | 10 | 10 | 0.59 |  |  | 59
|  | C3 | 3 | 10 | 1.69 |  |  | 50.7
|  |  | 3 | 14 | 0.521 |  |  | 21.882
|  | C4 | 3 | 10 | 1.89 |  |  | 56.7
|  |  | 3 | 10 | 0.631 |  |  | 18.93
|  |  | 3 | 10 | 0.631 |  |  | 18.93
482.524
8mm Diameter Bar | [7 empty] | 0.39506
Kg - Ton | [7 empty] | 1000
|  | Total Qty = | [5 empty] | 0.19063 | Ton
C11 | Plinth Beam 16mm Reinforcement Bar
16mm Epoxy Steel Bar
|  | PB1 | 2 | 1 | 10 |  |  | 20 | m
|  | PB2 | 4 | 1 | 21.5 |  |  | 86
|  | PB3 | 7 | 1 | 36.6 |  |  | 256.2
|  | PB4 | 7 | 1 | 23 |  |  | 161
|  | PB5 | 8 | 1 | 21.2 |  |  | 169.6
|  | PB6 | 6 | 1 | 10.3 |  |  | 61.8
|  | PB7 | 8 | 1 | 13.8 |  |  | 110.4
865
16mm Diameter Bar | [7 empty] | 1.5802
Kg - Ton | [7 empty] | 1000
|  | Total Qty = | [5 empty] | 1.3669 | Ton
Plinth Beam 12mm Bar
12mm Epoxy Steel Bar
|  | PB1 | 2 | 1 | 10 |  |  | 20
|  | PB6 | 2 | 1 | 10.3 |  |  | 20.6 | m
|  | PB7 | 2 | 1 | 13.8 |  |  | 27.6
68.2
12mm Diameter Bar | [7 empty] | 0.88889
Kg - Ton | [7 empty] | 1000
|  | Total Qty = | [5 empty] | 0.060622 | Ton
Plinth Beam 8mm Bar
8mm Epoxy Steel Bar
|  | PB1 |  |  | 10
|  | PB2 |  |  | 21.5
|  | PB3 |  |  | 36.6
|  | PB4 |  |  | 23
|  | PB5 |  |  | 21.2
|  | PB6 |  |  | 10.3
|  | PB7 |  |  | 13.8
|  | PB1 | 4 | 50 | 1.21 |  |  | 242 | m
|  | PB2 | 4 | 107.5 | 1.41 |  |  | 606.3
|  | PB3 | 7 | 244 | 1.51 |  |  | 2579.08
|  | PB4 | 7 | 153.3333 | 1.61 |  |  | 1728.0667
|  | PB5 | 8 | 141.3333 | 1.61 |  |  | 1820.3733
|  | PB6 | 6 | 68.6667 | 1.81 |  |  | 745.72
|  | PB7 | 8 | 92 | 1.81 |  |  | 1332.16
9053.7
8mm Diameter Bar | [7 empty] | 0.39506
Kg - Ton | [7 empty] | 1000
|  | Total Qty = | [5 empty] | 3.5768 | Ton
Block System
1 | Excavation
[5 empty] | 4.4 | 2.4
Add Working Space
| 600mm to both side |  | 1 | 1 | 0.6 | 0.6
|  |  | 1 | 1 | 5 | 3 | 3 | 45 | m³
[8 empty] | 45 | m³
2 | Leveling and Compacting
[5 empty] | 4.4 | 2.4
[5 empty] | 0.6 | 0.6
|  |  | 1 | 1 | 5 | 3 |  | 15 | m²
[8 empty] | 15 | m²
3 | Anti - Termite Treatment
| Bottom of the Excavated Area |  |  |  | 5 | 3 |  | 15 | m²
| Face of the Excavated Area |  | 1 | 2 | 5 |  | 3 | 30
|  |  | 1 | 2 |  | 3 | 3 | 18
[8 empty] | 63 | m²
4 | Blinding PCC 100mm
|  |  | 1 | 1 | 5 | 3 | 0.1 | 1.5
[8 empty] | 1.5 | m³
5 | Block Wall
| Length |  |  |  | 4
| Add half wall to both side |  |  |  | 0.2
|  |  | 1 | 2 | 4.2 |  | 2.75 | 23.1
| Width |  |  |  |  | 2
| Add Half wall to both side |  |  |  |  | 0.2
|  |  | 1 | 2 |  | 2.2 | 2.75 | 12.1
[8 empty] | 35.2 | m²
6 | Back filling
| Excavated Volume |  | 1 | 1 | 5 | 3 | 3 | 45 | m³
Deduct
| Blinding 100mm |  | 1 | -1 | 4.7 | 2.6 | 0.1 | -1.222
| Tank Wall |  | 1 | -2 | 4.2 | 0.2 | 2.75 | -4.62
|  |  | 1 | -2 | 2.2 | 0.2 | 2.75 | -2.42
| Holding Tank Void |  | 1 | -1 | 4 | 2 | 2.75 | -22
[8 empty] | 14.738 | m³
8 | RCC Holding Tank Slab
|  |  | 1 | 1 | 4.4 | 2.4 | 0.2 | 2.112
Deduct
| Manhole Cover |  | 1 | -1 | 0.6 | 0.6 | 0.2 | -0.072
[8 empty] | 2.04 | m³
9 | Reinforcement in Holding Tank Slab
| 16mm Diameter Bar |  |  |  | 4.4 |  |  |  | m
| Add Bend |  |  |  | 0.8
Deduct
| Cover |  |  |  | -0.08
[5 empty] | 5.12 | 2.4
| Add Bend |  |  |  |  | 0.8
Deduct
| Cover |  |  |  |  | -0.08
3.12
| Bottom Bar |  | 1 | 16 | 4.4 |  |  | 70.4
|  |  | 1 | 29.3333 | 3.12 |  |  | 91.52
| Top Bar |  | 1 | 16 | 4.4 |  |  | 70.4
|  |  | 1 | 29.3333 | 3.12 |  |  | 91.52
323.84
| 16mm Diameter Bar | [6 empty] | 1.5802
| Kg - Ton | [6 empty] | 1000
[8 empty] | 0.51175 | Ton
10 | Formwork to Soffix of Holding Tank Slab
|  |  | 1 | 1 | 4 | 2 |  | 8 | m²
[8 empty] | 8 | m²
11 | Formwork to Edge of Holding Tank Slab
|  |  | 1 | 2 | 4.4 |  | 0.2 | 1.76 | m²
|  |  | 1 | 2 | 2.4 |  | 0.2 | 0.96
[8 empty] | 2.72 | m²
12 | Rendering/Plastering
| Internal Wall Rendering |  | 1 | 2 | 4 |  | 2.75 | 22
|  |  | 1 | 2 |  | 2 | 2.75 | 11
[8 empty] | 33 | m²
13 | Rendering/Plastering
| External Wall Rendering |  | 1 | 2 | 4.4 |  | 2.75 | 24.2
|  |  | 1 | 2 |  | 2.4 | 2.75 | 13.2
[8 empty] | 37.4 | m²
1 | Block Work
Additional block work of 10cm to all windows opening for proper fixing of the UPVC materials to blockwork or concrete and mastic pointing all around the window.
| Win 1 |  |  | 8 |  | 2 | 0.1 | 1.6 | m²
| Win 2 |  |  | 1 |  | 0.9 | 0.1 | 0.09
| Win 3 |  |  | 3 |  | 0.6 | 0.1 | 0.18
| Win 4 |  |  | 1 |  | 1 | 0.1 | 0.1
[8 empty] | 1.97 | m²
2 | Plastering/Rendering
InternalLY
| Win 1 |  | 1 | 8 |  | 2 | 0.1 | 1.6 | m²
| Win 2 |  | 1 | 1 |  | 0.9 | 0.1 | 0.09
| Win 3 |  | 1 | 3 |  | 0.6 | 0.1 | 0.18
| Win 4 |  | 1 | 1 |  | 1 | 0.1 | 0.1
[8 empty] | 1.97 | m²
3 | Plastering/Rendering
Externally
| Win 1 |  | 1 | 8 |  | 2 | 0.1 | 1.6 | m²
| Win 2 |  | 1 | 1 |  | 0.9 | 0.1 | 0.09
| Win 3 |  | 1 | 3 |  | 0.6 | 0.1 | 0.18
| Win 4 |  | 1 | 1 |  | 1 | 0.1 | 0.1
[8 empty] | 1.97 | m²
4 | Paiting/Decoration
InternalLY
| Win 1 |  | 1 | 8 |  | 2 | 0.1 | 1.6 | m²
| Win 2 |  | 1 | 1 |  | 0.9 | 0.1 | 0.09
| Win 3 |  | 1 | 3 |  | 0.6 | 0.1 | 0.18
| Win 4 |  | 1 | 1 |  | 1 | 0.1 | 0.1
[8 empty] | 1.97 | m²
5 | Painting/Decoration
Externally
| Win 1 |  | 1 | 8 |  | 2 | 0.1 | 1.6 | m²
| Win 2 |  | 1 | 1 |  | 0.9 | 0.1 | 0.09
| Win 3 |  | 1 | 3 |  | 0.6 | 0.1 | 0.18
| Win 4 |  | 1 | 1 |  | 1 | 0.1 | 0.1
[8 empty] | 1.97 | m²

## STEEL WORK RATE (hidden)
Epoxy Steel Bar (16mm Diameter) |  |  |  |  | Epoxy Steel Bar (12mm Diameter) |  |  |  |  | Epoxy Steel Bar (8mm Diameter) |  |  |  |  | Material
Supervision | Unit | QTY | Rate | Amount | Supervision | Unit | QTY | Rate | Amount | Supervision | Unit | QTY | Rate | Amount | 16mm Diameter | Ton | 1 | 300
Foreman | Ton | 1 | 6.5 | 7 | Foreman | Ton | 1 | 6.5 | 7 | Foreman | Ton | 1 | 6.5 | 7
Skilled |  | 1 | 4.5 | 5 | Skilled |  | 1 | 4.5 | 5 | Skilled |  | 1 | 4.5 | 5 | Cutting and Bending |  |  | 40
Unskilled |  | 1 | 2.5 | 3 | Unskilled |  | 1 | 2.5 | 3 | Unskilled |  | 1 | 2.5 | 3 | Fixxing to Structure
|  |  |  | 15 |  |  |  |  | 15 |  |  |  |  | 15 | Wastage | 5% |  | 15
Materials |  |  |  |  | Materials |  |  |  |  | Materials
16mm Diameter | Ton | 1 | 330 | 330 | 16mm Diameter | Ton | 1 | 350 | 350 | 16mm Diameter | Ton | 1 | 350 | 350 | Transporatation | Ton | 1 | 10
Binding Wire |  | 1 | 4.5 | 4.5 | Binding Wire |  | 1 | 4.5 | 4.5 | Binding Wire |  | 1 | 4.5 | 4.5 | Supervision | Ton | 1 | 15
Equipment
|  |  |  | 334.5 |  |  |  |  | 354.5 |  |  |  |  | 354.5 | Small Tools
Transportation | Ton | 1 | 10 | 10 | Transportation | Ton | 1 | 10 | 10 | Transportation | Ton | 1 | 10 | 10 |  |  |  | 380
[15 empty] | P&O | 15% |  | 57
Cutting & Bending Tool | Ton | 1 | 40 | 40 | Cutting & Bending Tool | Ton | 1 | 40 | 40 | Cutting & Bending Tool | Ton | 1 | 40 | 40
Fixing to Structure |  |  |  |  | Fixing to Structure |  |  |  |  | Fixing to Structure | [7 empty] | 437
[18 empty] | 0.437 | per kg
Wastage | Ton | 5% |  | 16.5 | Wastage | Ton | 5% |  | 17.5 | Wastage | Ton | 5% |  | 17.5 | Per m³ of Concrete (Rule of Thumb)
Typical reinforcement:
Direct Cost |  |  |  | 416 | Direct Cost |  |  |  | 437 | Direct Cost |  |  |  | 437 | Slab: 80–120 kg/m³
Add |  |  |  |  | Add |  |  |  |  | Add |  |  |  |  | Beam: 120–180 kg/m³
Overhead | 10% |  |  | 41.6 | Overhead | 10% |  |  | 43.7 | Overhead | 10% |  |  | 43.7 | Column: 150–250 kg/m³
|  |  |  | 457.6 |  |  |  |  | 480.7 |  |  |  |  | 480.7
Profit | 8% |  |  | 36.608 | Profit | 8% |  |  | 38.456 | Profit | 8% |  |  | 38.456
|  |  |  | 494.208 |  |  |  |  | 519.156 |  |  |  |  | 519.156
|  |  |  | 530.816 |  |  |  |  | 557.612 |  |  |  |  | 557.612 | 100.3242
Contigency | 5% |  |  | 26.5408 | Contigency | 5% |  |  | 27.8806 | Contigency | 5% |  |  | 27.8806
Total/Ton |  |  |  | 557.3568 | Total/Ton |  |  |  | 585.4926 | Total/Ton |  |  |  | 585.4926
Total/kg |  |  |  | 0.55736 | Total/kg |  |  |  | 0.58549 | Total/kg |  |  |  | 0.58549
Normal Steel Bar (16mm Diameter) |  |  |  |  | Normal Steel Bar (12mm Diameter) |  |  |  |  | Normal Steel Bar (8mm Diameter)
Supervision | Unit | QTY | Rate | Amount | Supervision | Unit | QTY | Rate | Amount | Supervision | Unit | QTY | Rate | Amount
Foreman | Ton | 1 | 6.5 | 7 | Foreman | Ton | 1 | 6.5 | 7 | Foreman | Ton | 1 | 6.5 | 7
Skilled |  | 1 | 4.5 | 5 | Skilled |  | 1 | 4.5 | 5 | Skilled |  | 1 | 4.5 | 5
Unskilled |  | 1 | 2.5 | 3 | Unskilled |  | 1 | 2.5 | 3 | Unskilled |  | 1 | 2.5 | 3
|  |  |  | 15 |  |  |  |  | 15 |  |  |  |  | 15
Materials |  |  |  |  | Materials |  |  |  |  | Materials
16mm Diameter | Ton | 1 | 290 | 290 | 16mm Diameter | Ton | 1 | 290 | 290 | 16mm Diameter | Ton | 1 | 300 | 300
Binding Wire |  | 1 | 4.5 | 4.5 | Binding Wire |  | 1 | 4.5 | 4.5 | Binding Wire |  | 1 | 4.5 | 4.5
|  |  |  | 294.5 |  |  |  |  | 294.5 |  |  |  |  | 304.5
Transportation | Ton | 1 | 10 | 10 | Transportation | Ton | 1 | 10 | 10 | Transportation | Ton | 1 | 10 | 10
Cutting & Bending Tool | Ton | 1 | 40 | 40 | Cutting & Bending Tool | Ton | 1 | 40 | 40 | Cutting & Bending Tool | Ton | 1 | 40 | 40
Fixing to Structure |  |  |  |  | Fixing to Structure |  |  |  |  | Fixing to Structure
Wastage | Ton | 5% |  | 14.5 | Wastage | Ton | 5% |  | 14.5 | Wastage | Ton | 5% |  | 15
Direct Cost |  |  |  | 374 | Direct Cost |  |  |  | 374 | Direct Cost |  |  |  | 384.5
Add |  |  |  |  | Add |  |  |  |  | Add
Overhead | 10% |  |  | 37.4 | Overhead | 10% |  |  | 37.4 | Overhead | 10% |  |  | 38.45
|  |  |  | 411.4 |  |  |  |  | 411.4 |  |  |  |  | 422.95
Profit | 8% |  |  | 32.912 | Profit | 8% |  |  | 32.912 | Profit | 8% |  |  | 33.836
|  |  |  | 444.312 |  |  |  |  | 444.312 |  |  |  |  | 456.786
|  |  |  | 477.224 |  |  |  |  | 477.224 |  |  |  |  | 490.622
Contigency | 5% |  |  | 23.8612 | Contigency | 5% |  |  | 23.8612 | Contigency | 5% |  |  | 24.5311
Total/Ton |  |  |  | 501.0852 | Total/Ton |  |  |  | 501.0852 | Total/Ton |  |  |  | 515.1531
Total/kg |  |  |  | 0.50109 | Total/kg |  |  |  | 0.50109 | Total/kg |  |  |  | 0.51515

## QTY ON (Add Work On Bill. No. 5 (hidden)
Bill Code | Items | No | L | W | D | Qty | Unit
C1 | RCC COLUMN C35
| Columns | 2 | 0.2 | 0.2 | 3 | 0.24 | m³
| Lintel | 1 | 0.2 | 0.2 | 2 | 0.08
| Entrance | 4 | 0.3 | 0.2 | 1.5 | 0.36
[6 empty] | 0.68 | m³
C30 | Block wall in Salah Area
| Area | 1 |  | 1.2 | 3 | 3.6
[6 empty] | 3.6 | m²
C19 | Plastering/Rendering
| Internal | 1 |  | 1.2 | 3 | 3.6
| External | 1 |  | 1.2 | 3 | 3.6
[6 empty] | 7.2 | m²
C20 | Painting
| Internal | 1 |  | 1.2 | 3 | 3.6
| External | 1 |  | 1.2 | 3 | 3.6
[6 empty] | 7.2 | m²
C16 | Bedroom
Bedroom flooring preparing the surface to receive antislip ceramic tiles and supplying and fixing antislip ceramic tiles matching with existing floors
| Bedroom 1 | 1 | 4 | 3.8 |  | 15.2
| Bedroom 2 | 1 | 4 | 3.8 |  | 15.2
[6 empty] | 30.4 | m²
C77 Ref. Bill No. 4 | Skirting to Bedroom
| Bedroom 1 and 2 | 2 | 4 |  |  | 8
|  | 2 | 3.8 |  |  | 7.6
|  | 2 | 4 |  |  | 8
|  | 2 | 3.8 |  |  | 7.6
Deduct Opening
| Door 3 | 2 | -1 |  |  | -2
[6 empty] | 29.2 | m²
C16 | Lobby Area
|  | 1 | 3.4 | 2 |  | 6.8
|  | 2 | 2.2 | 2 |  | 8.8
[6 empty] | 15.6 | m²
C77 Ref. Bill No. 4 | Skirting to Lobby Area
|  | 2 | 3.4 |  |  | 6.8
|  | 2 | 2 |  |  | 4
|  | 4 | 2.2 |  |  | 8.8
|  | 4 | 2 |  |  | 8
Deduct Opening
|  | 2 | -1.6 |  |  | -3.2
| Door 1 | 1 | -1.8 |  |  | -1.8
|  | 1 | -2.2 |  |  | -2.2
|  | 1 | -2 |  |  | -2
| Door 3 | 3 | -1 |  |  | -3
| Door 4 | 1 | -0.8 |  |  | -0.8
| Salah Opening | 1 | -1.2 |  |  | -1.2
[6 empty] | 13.4 | m

## MShheet (29 MHU) (hidden)
Bill Code | Items | No | L | W | D | Qty | Unit
C1 | RCC COLUMN C35
| Columns | 2 | 0.2 | 0.2 | 3 | 0.24 | m³
| Lintel | 1 | 0.2 | 0.2 | 2 | 0.08
| Entrance | 4 | 0.3 | 0.2 | 1.5 | 0.36
[6 empty] | 0.68 | m³
C30 | Block wall in Salah Area
| Area | 1 |  | 1.2 | 3 | 3.6
[6 empty] | 3.6 | m²
C19 | Plastering/Rendering
| Internal | 1 |  | 1.2 | 3 | 3.6
| External | 1 |  | 1.2 | 3 | 3.6
[6 empty] | 7.2 | m²
C20 | Painting
| Internal | 1 |  | 1.2 | 3 | 3.6
| External | 1 |  | 1.2 | 3 | 3.6
[6 empty] | 7.2 | m²
C16 | Bedroom
Bedroom flooring preparing the surface to receive antislip ceramic tiles and supplying and fixing antislip ceramic tiles matching with existing floors
| Bedroom 1 | 1 | 4 | 3.8 |  | 15.2
| Bedroom 2 | 1 | 4 | 3.8 |  | 15.2
[6 empty] | 30.4 | m²
C77 Ref. Bill No. 4 | Skirting to Bedroom
| Bedroom 1 and 2 | 2 | 4 |  |  | 8
|  | 2 | 3.8 |  |  | 7.6
|  | 2 | 4 |  |  | 8
|  | 2 | 3.8 |  |  | 7.6
Deduct Opening
| Door 3 | 2 | -1 |  |  | -2
[6 empty] | 29.2 | m²
C16 | Lobby Area
|  | 1 | 3.4 | 2 |  | 6.8
|  | 2 | 2.2 | 2 |  | 8.8
[6 empty] | 15.6 | m²
C77 Ref. Bill No. 4 | Skirting to Lobby Area
|  | 2 | 3.4 |  |  | 6.8
|  | 2 | 2 |  |  | 4
|  | 4 | 2.2 |  |  | 8.8
|  | 4 | 2 |  |  | 8
Deduct Opening
|  | 2 | -1.6 |  |  | -3.2
| Door 1 | 1 | -1.8 |  |  | -1.8
|  | 1 | -2.2 |  |  | -2.2
|  | 1 | -2 |  |  | -2
| Door 3 | 3 | -1 |  |  | -3
| Door 4 | 1 | -0.8 |  |  | -0.8
| Salah Opening | 1 | -1.2 |  |  | -1.2
[6 empty] | 13.4 | m

## 29 MHU ADD. WORKS RATE (hidden)
| Door (Reference to Bill No. 5) | [5 empty] | Tile Works (Reference to Bill No. 5)
C12 |  | Unit | QTY | Rate | Amount |  | Bedroom
[6 empty] | C16 | Reference to Bill No. 5 |  |  |  | 472.5
|  | Nr | 29 | 9975 | 289275 |  | Total Area of Salah & Majlis | m² | 31.2
[7 empty] | Per Sqm |  | 30.4 | 15.1442 | 460.3846
6 No. per Unit
| Door 1 - 1800 x 2100mm | Nr | 1 | 9975 |  |  | Lobby
| Door 2 - 1000 x 2100mm | Nr | 1 |  | 1425 |  | Reference to Bill No. 5 | m² |  |  | 472.5
| Door 3 - 1000 x 2100mm | Nr | 4 |  |  |  | Total Area of Salah & Majlis |  | 31.2
| Door 6 - 800 x 2100mm | Nr | 1
[7 empty] | Per Sqm |  | 15.6 | 15.1442 | 236.25
Platering (Reference to Bill No. 5)
C19 | Internal Wall | Unit | QTY | Bill Price | New Rate
| Total Area | m² | 205.14 |  |  |  | Skirting (Reference to Bill No. 4)
| Rate |  |  | 1260 |  | C77 | Skirting (Reference to Bill No. 4) | m |  | 1.658
| Per Sqm |  | 3.6 | 6.1421 | 22.1117 |  | Bedroom Skirting | m | 29.2 | 1.658 | 48.4136
C20 | External Wall | [5 empty] | Lobby Skirting | m | 13.4 | 1.658 | 22.2172
| Total Area | m² | 241.38
| Rate |  |  | 787.5
| Per Sqm |  | 3.6 | 3.2625 | 11.745
Demolising & Reconstruct of columns (Reference to Bill No. 5)
C1 | Volumns of Concrete For RCC SLab, RCC Beam and RCC Column
| Column | m³ | 3.68
| Slab |  | 24.08
| Beam |  | 9.33
37.09
| Reference to Bill No. 5, Item Code C1 |  |  | 262.5
| Rate/1m³ | m³ | 0.68 | 7.0774 | 4.8126

## ADD. WORK ON CHANNEL -Msheet (hidden)
QUANTITY TAKE-OFF SHEET PROPOSED CHANNEL – BEHIND MAINTENANCE HOUSE
Item | Ref. | Description | No. | Length (m) | Width (m) | Depth/ Height (m) | Area (m²) | Volume (m³) | Unit
SECTION 1 – EARTHWORKS
A |  | CHANNEL EXCAVATION
A.1 | Sh.2/3 | Bulk excavation for proposed drainage channel to formation level; in any material encountered; channel trapezoidal x-section (bottom w=1.50m, top w=1.00m, D=1.00m) with 0.30m working space each side; depositing excavated material to spoil heap on site for later re-use or disposal. [Exc. width at top = 1.5+2×0.3 = 2.10m; avg x-sect = 2.100m²] | 1 | 300 | 2.1 | 1 |  | 630 | m³
A.2 | Sh.2/3 | Extra over Item A.1 for trimming, shaping and compacting sides and bottom of excavation to required profile and levels. | 1 | 300 |  |  |  | 300 | m
A.3 | Sh.2/3 | Disposal of surplus excavated material off-site by tipper truck; allowing for loading, transport and tipping at approved disposal area. [Assume 60% surplus after re-use = 378.0 m³] | 1 |  |  |  |  | 378 | m³
SECTION 2 – FILLING / COMPACTION
B |  | FILLING
B.1 | Sh.2/3 | Selected granular fill (approved material from excavation) compacted in 150mm layers to 95% MDD; backfilling working space between channel lining and excavation face. [2 sides × 0.3m × 1.0m depth × 300.0m length] | 1 | 300 | 0.6 | 1 |  | 180 | m³
B.2 | Sh.2/3 | Filling with selected material and compacting to finished ground level (FGL) as shown on long section; nominal average depth 0.05m over channel corridor width (approx. 5.5m). [Nominal avg fill depth = 0.05m; corridor w ≈ 5.5m; L=300.0m] | 1 | 300 | 5.5 | 0.05 |  | 82.5 | m³
SECTION 3 – LEAN-MIX CONCRETE BLINDING
C |  | BLINDING CONCRETE
C.1 | Sh.3 | Lean-mix concrete blinding C10/15; 50mm thick; to channel bed and toe of walls (width = 1.7m incl. under walls). | 1 | 300 | 1.7 | 0.05 |  | 25.5 | m³
SECTION 4 – REINFORCED CONCRETE CHANNEL LINING
D |  | CONCRETE WORKS
D.1 | Sh.3 | Reinforced concrete C25/30; channel bed slab; 100mm thick × 1.5m wide. | 1 | 300 | 1.5 | 0.1 |  | 45 | m³
D.2 | Sh.3 | Reinforced concrete C25/30; channel side walls; 2 No. sloping walls; 100mm thick; slant height = 1.031m (z=0.25H:1V). | 2 | 300 | 0.1 | 1.031 |  | 61.86 | m³
|  | TOTAL CONCRETE LINING VOLUME (Items D.1 + D.2) | [5 empty] | 106.86 | m³
SECTION 5 – FORMWORK
E |  | FORMWORK
E.1 | Sh.3 | Sawn formwork; fair face finish; to outer faces of channel side walls; slant height 1.031m; 2 sides. | 2 | 300 |  | 1.031 | 618.6 |  | m²
E.2 | Sh.3 | Sawn formwork; to ends of channel bed and walls at inlet and outlet (2 No. end shutters). | 2 |  |  |  | 0.71 |  | m²
SECTION 6 – REINFORCEMENT
F |  | BRC MESH REINFORCEMENT
F.1 | Sh.3 | High-tensile deformed wire mesh reinforcement A10 - 10mm 200 x 200mm spacing placed on channel lining. [Weight: 7.7 kg/m³ × 618.6 m³ = 4.760 kg; confirm with structural drawing] | 1 |  |  |  |  | 4.7632 | kg
SECTION 7 – SURFACE TREATMENT / JOINTS
G |  | SURFACE FINISH & JOINTS
G.1 | Sh.3 | Steel-trowel finish to internal face of channel lining (bed + 2 walls). [Width = 1.5+2×1.031 = 3.562m × 300.0m] | 1 | 300 | 3.562 |  | 1068.6 |  | m²
G.2 | Sh.3 | Sawn contraction joints 5mm wide × full depth of lining; sealed with polysulphide sealant; at 5m centres. [300.0m ÷ 5m = 60 No. joints] | 60 | [5 empty] | No.